## Summary
0580-Security Technology Salutation after eliminating Passenger Checking Roles ¦ Rev 1: baseline schedule, cost loading and BOQ mapping
Project number and name | 0580-Security Technology Salutation after eliminating Passenger Checking Roles
Source of cost | Signed contract with ETECHS (1 November 2026): Annex 3 price table (Revised-02) and clause 15 payment milestones
Contract price | 62000000
Project start (NTP milestone) | 2026-11-01
Contract term end (36 months) | 2029-10-31
Activities | 591
Tasks (2 resources each) | 500
Milestones | 91
Cost loaded in P6 (SAR)
Difference to contract price
Progress points loaded
Working calendar | Sunday to Thursday, 8 hours; KSA official holidays; Eid dates are estimates to be updated
How to read | Station_BOQ gives the BOQ value of each station; Payment_Milestones applies the contract payment conditions; BOQ_Mapping shows each activity cost; Distribution_Keys explains the keys; S_Curve shows cost against progress; Invoicing_Monthly lists every invoice by month, milestone and station.

## Station_BOQ
Annex 3 price table: BOQ value by station (SAR, excluding VAT)
A1-A6 are priced per station. Shared packages (design, PM, FAT, spares, training, cloud) are priced per railway and allocated to stations pro rata to A1-A6 hardware value.
Station | Railway | A1 CCTV | A2 Video mgmt and wall | A3 Access and intercom | A4 UPS | A5 Poles, cabinets, network | A6 Civil works | Hardware subtotal | Design and engineering | Project management | FAT | Commissioning spares | Training | Cloud (12 mo) | Shared total | Station value | Share of price
Riyadh (Thumamah) (NRY) | NSR | 338989 | 417141 | 44085 | 56211 | 860619 | 745743 |  | 82837.4 | 744951.9774 | 34510.3761 | 66982.1302 | 6573.9871 | 82141.8981
Makkah (HMK) | HHR | 1650175 | 552237 | 44085 | 110563 | 2715976 | 571639 |  | 337786.5094 | 3026065.6855 | 64944.1468 | 175360.1568 | 21649.3271 | 439615.133
Riyadh (Malaz) (ERY) | EWR | 276849 | 350866 | 44085 | 50114 | 548042 | 701825 |  | 86494.6877 | 779124.2822 | 56538.4266 | 106509.2034 | 18847.2549 | 72225.5095
Jeddah (HJD) | HHR | 1391206 | 652091 | 44085 | 102666 | 2840354 | 521718 |  | 332247.8681 | 2976447.681 | 63879.2661 | 172484.7992 | 21294.3459 | 432406.8209
Dammam (EDM) | EWR | 276849 | 412102 | 44085 | 50114 | 548042 | 701813 |  | 89180.3565 | 803316.1702 | 58293.9505 | 109816.3249 | 19432.4641 | 74468.1189
Al Qassim (NQS) | NSR | 338989 | 359215 | 44085 | 56211 | 860619 | 745743 |  | 80889.0231 | 727430.3359 | 33698.6749 | 65406.6772 | 6419.3637 | 80209.8797
Hufuf (EHF) | EWR | 192155 | 349033 | 44085 | 50114 | 508774 | 659866 |  | 79135.9446 | 712838.4144 | 51728.2843 | 97447.6773 | 17243.7795 | 66080.7509
Al Majma'ah (NMJ) | NSR | 338989 | 359215 | 44085 | 56211 | 860619 | 745743 |  | 80889.0231 | 727430.3359 | 33698.6749 | 65406.6772 | 6419.3637 | 80209.8797
KAEC (HKA) | HHR | 962039 | 406364 | 44085 | 82168 | 1552977 | 187054 |  | 193568.9178 | 1734090.1529 | 37216.3123 | 100490.324 | 12406.1699 | 251921.9185
Madinah (HMD) | HHR | 934319 | 409184 | 44085 | 74329 | 1480427 | 291036 |  | 193490.7048 | 1733389.4806 | 37201.2747 | 100449.7201 | 12401.1571 | 251820.1276
Abqaiq (EAB) | EWR | 111083 | 286032 | 44085 | 50114 | 411979 | 375936 |  | 56115.0112 | 505471.1332 | 36680.3387 | 69099.7944 | 12227.5015 | 46857.6207
Hail (NHL) | NSR | 338989 | 359215 | 44085 | 56211 | 860619 | 745743 |  | 80889.0231 | 727430.3359 | 33698.6749 | 65406.6772 | 6419.3637 | 80209.8797
Al Jouf (NJF) | NSR | 338989 | 359215 | 44085 | 56211 | 877550 | 745743 |  | 81458.5077 | 732551.6789 | 33935.9244 | 65867.1612 | 6464.5581 | 80774.583
Al Qurayyat (NQR) | NSR | 338989 | 359215 | 44085 | 56211 | 860619 | 745743 |  | 80889.0231 | 727430.3359 | 33698.6749 | 65406.6772 | 6419.3637 | 80209.8797
Total
Contract price (Annex 3) |  | 62000000
Difference (should be zero within SAR 5)

## Payment_Milestones
Contract clause 15 payment milestones applied to each station price
MS1 Mobilization is 20% of the TOTAL price. MS2 to MS7 are prorated per station on the station share of the price.
Milestone | Description | Share of price | Amount (SAR)
MS1 | Mobilization | 20%
MS2 | Engineering submittal | 10%
MS3 | SAR approval of engineering | 10%
MS4 | Material delivery | 20%
MS5 | Installation | 20%
MS6 | Testing and commissioning (SAT) | 10%
MS7 | Final acceptance and handover | 10%
Total
Station | Station share | MS2 amount | MS3 amount | MS4 amount | MS5 amount | MS6 amount | MS7 amount | Stations total MS2-MS7
Riyadh (Thumamah) (NRY)
Makkah (HMK)
Riyadh (Malaz) (ERY)
Jeddah (HJD)
Dammam (EDM)
Al Qassim (NQS)
Hufuf (EHF)
Al Majma'ah (NMJ)
KAEC (HKA)
Madinah (HMD)
Abqaiq (EAB)
Hail (NHL)
Al Jouf (NJF)
Al Qurayyat (NQR)
Total
Check: MS1 + stations MS2-MS7 = total price

## BOQ_Mapping
Activity cost mapping: how each activity cost was distributed from the BOQ
BOQ ID uses the Annex 3 section codes A1 to A6; the shared per-railway packages carry derived IDs SH-xx. Cost = milestone amount (payment condition x station share of the BOQ) x distribution key. Column M recomputes it with formulas; column N is the whole-riyal value loaded in P6.
BOQ ID | BOQ Description | Activity ID | Activity name | WBS | EPC phase | Station | Payment milestone | Milestone % | Station price share | Milestone amount (SAR) | Distribution key | Cost recomputed | Cost in P6 (SAR) | Difference | Distribution basis | Primary BOQ source | Progress points | Progress % of project | Start | Finish | Duration (work days)
TOTAL | Contract price (Annex 3 total, SAR 62,000,000): 20% mobilization payment, clause 15 | PRJ-A1010 | Performance security, insurance and key personnel approval | PM.MOB | Mobilization | PRJ | MS1 | 20% |  |  | 0.15 |  | 1859999 |  | MS1 Mobilization 20% of the total price (SAR 12,400,000) x key 15% | Contract price (62,000,000) x 20% mobilization payment (contract clause 15) | 400 |  | 2026-11-01 | 2026-11-12 | 10
TOTAL | Contract price (Annex 3 total, SAR 62,000,000): 20% mobilization payment, clause 15 | PRJ-A1020 | Initial baseline programme (Primavera) covering mobilization and survey | PM.MOB | Mobilization | PRJ | MS1 | 20% |  |  | 0.1 |  | 1239999 |  | MS1 Mobilization 20% of the total price (SAR 12,400,000) x key 10% | Contract price (62,000,000) x 20% mobilization payment (contract clause 15) | 200 |  | 2026-11-01 | 2026-11-09 | 7
- | No BOQ cost: administrative or review step with no payment milestone | PRJ-A1030 | SAR review and approval of initial baseline | PM.MOB | Mobilization | PRJ |  | 0% |  | 0 | 0 | 0 | 0 |  | No payment milestone attached (administrative approval or review step) | - | 200 |  | 2026-11-10 | 2026-11-30 | 15
TOTAL | Contract price (Annex 3 total, SAR 62,000,000): 20% mobilization payment, clause 15 | PRJ-A1040 | Mobilization: site establishment, offices, personnel and tools | PM.MOB | Mobilization | PRJ | MS1 | 20% |  |  | 0.45 |  | 5579999 |  | MS1 Mobilization 20% of the total price (SAR 12,400,000) x key 45% | Contract price (62,000,000) x 20% mobilization payment (contract clause 15) | 700 |  | 2026-11-08 | 2026-12-10 | 25
TOTAL | Contract price (Annex 3 total, SAR 62,000,000): 20% mobilization payment, clause 15 | PRJ-A1050 | Mobilization submittals: QC programme and ITP, HSE, security, procurement and shipping plan | PM.MOB | Mobilization | PRJ | MS1 | 20% |  |  | 0.3 |  | 3719999 |  | MS1 Mobilization 20% of the total price (SAR 12,400,000) x key 30% | Contract price (62,000,000) x 20% mobilization payment (contract clause 15) | 600 |  | 2026-11-08 | 2026-12-03 | 20
- | No BOQ cost: administrative or review step with no payment milestone | PRJ-A1060 | Site access permits for the surveys of all stations: application and approval (two months) | PM.MOB | Mobilization | PRJ |  | 0% |  | 0 | 0 | 0 | 0 |  | No payment milestone attached (administrative approval or review step) | - | 100 |  | 2026-11-01 | 2026-12-31 | 45
- | No BOQ cost: administrative or review step with no payment milestone | PRJ-A2010 | Detailed baseline programme (after mobilization) | PM.MOB | Project management | PRJ |  | 0% |  | 0 | 0 | 0 | 0 |  | No payment milestone attached (administrative approval or review step) | - | 300 |  | 2027-01-03 | 2027-01-21 | 15
- | No BOQ cost: administrative or review step with no payment milestone | PRJ-A2020 | SAR review and approval of detailed baseline | PM.MOB | Project management | PRJ |  | 0% |  | 0 | 0 | 0 | 0 |  | No payment milestone attached (administrative approval or review step) | - | 200 |  | 2027-01-24 | 2027-02-11 | 15
- | No BOQ cost: administrative or review step with no payment milestone | PRJ-C1010 | Contract closeout pack and handover documentation | PM.CLO | Project management | PRJ |  | 0% |  | 0 | 0 | 0 | 0 |  | No payment milestone attached (administrative approval or review step) | - | 1301 |  | 2029-09-13 | 2029-09-27 | 10
SH-DES | Design and engineering package (per railway, allocated to the station) | NRY-E1010 | Survey: submittal of site survey and as-found report - Riyadh (Thumamah) | ENG.NRY.SRV.SUB | Engineering | NRY | MS2 | 10% |  |  | 0.069 |  | 24017 |  | MS2 Engineering submittal 10% x station price share 5.61% ¦ Design stage key 6.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 31 |  | 2027-01-03 | 2027-01-12 | 8
SH-DES | Design and engineering package (per railway, allocated to the station) | NRY-E1020 | Survey: SAR approval of survey report - Riyadh (Thumamah) | ENG.NRY.SRV.APR | Engineering | NRY | MS3 | 10% |  |  | 0.05 |  | 17404 |  | MS3 SAR approval of engineering 10% x station price share 5.61% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 33 |  | 2027-01-13 | 2027-02-02 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NRY-E1030 | Concept design: submittal - Riyadh (Thumamah) | ENG.NRY.CNC.SUB | Engineering | NRY | MS2 | 10% |  |  | 0.098 |  | 34112 |  | MS2 Engineering submittal 10% x station price share 5.61% ¦ Design stage key 9.8% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 22 |  | 2027-01-13 | 2027-01-24 | 8
SH-DES | Design and engineering package (per railway, allocated to the station) | NRY-E1040 | Concept design: SAR review and approval - Riyadh (Thumamah) | ENG.NRY.CNC.APR | Engineering | NRY | MS3 | 10% |  |  | 0.1 |  | 34808 |  | MS3 SAR approval of engineering 10% x station price share 5.61% ¦ Design stage key 10.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 41 |  | 2027-01-25 | 2027-02-14 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NRY-E1050 | Preliminary design: submittal - Riyadh (Thumamah) | ENG.NRY.PRE.SUB | Engineering | NRY | MS2 | 10% |  |  | 0.196 |  | 68223 |  | MS2 Engineering submittal 10% x station price share 5.61% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 55 |  | 2027-01-25 | 2027-02-11 | 14
SH-DES | Design and engineering package (per railway, allocated to the station) | NRY-E1060 | Preliminary design: SAR review and approval - Riyadh (Thumamah) | ENG.NRY.PRE.APR | Engineering | NRY | MS3 | 10% |  |  | 0.2 |  | 69616 |  | MS3 SAR approval of engineering 10% x station price share 5.61% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 59 |  | 2027-02-14 | 2027-03-14 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NRY-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Riyadh (Thumamah) | ENG.NRY.DET.SUB | Engineering | NRY | MS2 | 10% |  |  | 0.392 |  | 136447 |  | MS2 Engineering submittal 10% x station price share 5.61% ¦ Design stage key 39.2% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 113 |  | 2027-02-14 | 2027-03-23 | 22
SH-DES | Design and engineering package (per railway, allocated to the station) | NRY-E1080 | Detailed design: SAR review and approval - Riyadh (Thumamah) | ENG.NRY.DET.APR | Engineering | NRY | MS3 | 10% |  |  | 0.4 |  | 139231 |  | MS3 SAR approval of engineering 10% x station price share 5.61% ¦ Design stage key 40.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 77 |  | 2027-03-24 | 2027-04-13 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NRY-E1090 | IFC and shop drawings: submittal - Riyadh (Thumamah) | ENG.NRY.IFC.SUB | Engineering | NRY | MS2 | 10% |  |  | 0.196 |  | 68223 |  | MS2 Engineering submittal 10% x station price share 5.61% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 51 |  | 2027-03-24 | 2027-04-08 | 12
SH-DES | Design and engineering package (per railway, allocated to the station) | NRY-E1100 | IFC and shop drawings: SAR approval and release - Riyadh (Thumamah) | ENG.NRY.IFC.APR | Engineering | NRY | MS3 | 10% |  |  | 0.2 |  | 69616 |  | MS3 SAR approval of engineering 10% x station price share 5.61% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 63 |  | 2027-04-11 | 2027-04-29 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NRY-E1110 | HCIS Stage 3 and 4 documents: preparation - Riyadh (Thumamah) | ENG.NRY.HCS.SUB | Engineering | NRY | MS2 | 10% |  |  | 0.049 |  | 17056 |  | MS2 Engineering submittal 10% x station price share 5.61% ¦ Design stage key 4.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 24 |  | 2027-02-25 | 2027-04-08 | 26
SH-DES | Design and engineering package (per railway, allocated to the station) | NRY-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Riyadh (Thumamah) | ENG.NRY.HCS.APR | Engineering | NRY | MS3 | 10% |  |  | 0.05 |  | 17404 |  | MS3 SAR approval of engineering 10% x station price share 5.61% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 14 |  | 2027-04-11 | 2027-04-29 | 15
SH-DES, SH-TRN | Design and engineering package (per railway, allocated to the station) and Training (per railway, allocated): documentation and training share | NRY-E1130 | As-built and O&M documentation: submittal - Riyadh (Thumamah) | ENG.NRY.ASB.SUB | Engineering | NRY | MS7 | 10% |  |  | 0.15 |  | 52212 |  | MS7 Final acceptance and handover 10% x station price share 5.61% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 41 |  | 2027-11-04 | 2027-12-13 | 28
SH-DES | Design and engineering package (per railway, allocated to the station): documentation share | NRY-E1140 | As-built and O&M documentation: SAR review and approval - Riyadh (Thumamah) | ENG.NRY.ASB.APR | Engineering | NRY | MS7 | 10% |  |  | 0.05 |  | 17404 |  | MS7 Final acceptance and handover 10% x station price share 5.61% ¦ Fixed key 5% | Annex 3 documentation share | 22 |  | 2027-12-14 | 2028-01-03 | 15
- | No BOQ cost: administrative or review step with no payment milestone | NRY-X1010 | Enabling works: site preparation, setting out, temporary works and utilities clearance - Riyadh (Thumamah) | CON.NRY.ENA | Construction | NRY | MS5 | 20% |  |  | 0.012112 |  | 8432 |  | MS5 Installation 20% x station price share 5.61% ¦ BOQ civil share 30.3% x 4% (enabling: site preparation) | Annex 3 A6 Civil works (SAR 745,743) | 54 |  | 2027-05-02 | 2027-05-13 | 10
- | No BOQ cost: administrative or review step with no payment milestone | NRY-X1020 | Enabling works: cable routes, duct-bank and cabinet plinth preparation - Riyadh (Thumamah) | CON.NRY.ENA | Construction | NRY | MS5 | 20% |  |  | 0.018168 |  | 12648 |  | MS5 Installation 20% x station price share 5.61% ¦ BOQ civil share 30.3% x 6% (enabling: routes, ducts, plinths) | Annex 3 A6 Civil works (SAR 745,743) | 81 |  | 2027-05-23 | 2027-06-10 | 15
A1 | A1 CCTV system | NRY-P1010 | Manufacture CCTV cameras and analytics - Riyadh (Thumamah) | PRO.NRY.CCT | Procurement | NRY | MS4 | 20% |  |  | 0.14807 |  | 103080 |  | MS4 Material delivery 20% x station price share 5.61% ¦ BOQ section share 19.7% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 338,989) | 255 |  | 2027-05-02 | 2027-07-12 | 47
A2 | A2 Video management and video wall | NRY-P1020 | Manufacture video management servers, storage and video wall - Riyadh (Thumamah) | PRO.NRY.VMS | Procurement | NRY | MS4 | 20% |  |  | 0.18221 |  | 126844 |  | MS4 Material delivery 20% x station price share 5.61% ¦ BOQ section share 24.3% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 417,141) | 314 |  | 2027-05-02 | 2027-07-12 | 47
A3 | A3 Access control and intercom | NRY-P1030 | Manufacture access control and intercom equipment - Riyadh (Thumamah) | PRO.NRY.ACC | Procurement | NRY | MS4 | 20% |  |  | 0.019256 |  | 13405 |  | MS4 Material delivery 20% x station price share 5.61% ¦ BOQ section share 2.6% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 33 |  | 2027-05-02 | 2027-07-12 | 47
A4, A5 | A4 UPS and A5 Poles, cabinets and network | NRY-P1040 | Manufacture UPS, network switches and field cabinets - Riyadh (Thumamah) | PRO.NRY.UPN | Procurement | NRY | MS4 | 20% |  |  | 0.40047 |  | 278789 |  | MS4 Material delivery 20% x station price share 5.61% ¦ BOQ section share 53.4% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 916,830) | 691 |  | 2027-05-02 | 2027-07-12 | 47
SH-FAT | Factory acceptance test (per railway, allocated) | NRY-P1050 | Factory acceptance test at vendor premises - Riyadh (Thumamah) | PRO.NRY.LOG | Procurement | NRY | MS4 | 20% |  |  | 0.05 |  | 34808 |  | MS4 Material delivery 20% x station price share 5.61% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 216 |  | 2027-07-13 | 2027-07-26 | 10
A1-A5 | A1 to A5 equipment sections: logistics (shipping, customs, delivery) share | NRY-P1060 | Shipping and customs clearance - Riyadh (Thumamah) | PRO.NRY.LOG | Procurement | NRY | MS4 | 20% |  |  | 0.15 |  | 104424 |  | MS4 Material delivery 20% x station price share 5.61% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 431 |  | 2027-07-27 | 2027-08-25 | 22
SH-SPR | Commissioning spares (per railway, allocated) | NRY-P1070 | Delivery to station and receiving inspection - Riyadh (Thumamah) | PRO.NRY.LOG | Procurement | NRY | MS4 | 20% |  |  | 0.05 |  | 34808 |  | MS4 Material delivery 20% x station price share 5.61% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 216 |  | 2027-08-26 | 2027-09-01 | 5
A6 | A6 Civil works | NRY-C1010 | Civil: platform trenches and duct banks - Riyadh (Thumamah) | CON.NRY.CIV | Construction | NRY | MS5 | 20% |  |  | 0.1514 |  | 105400 |  | MS5 Installation 20% x station price share 5.61% ¦ BOQ civil share 30.3% x 50% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 745,743) | 350 |  | 2027-06-13 | 2027-08-30 | 57
A6 | A6 Civil works | NRY-C1020 | Civil: camera and ALPR pole foundations and poles - Riyadh (Thumamah) | CON.NRY.CIV | Construction | NRY | MS5 | 20% |  |  | 0.12112 |  | 84320 |  | MS5 Installation 20% x station price share 5.61% ¦ BOQ civil share 30.3% x 40% (poles) | Annex 3 A6 Civil works (SAR 745,743) | 269 |  | 2027-08-03 | 2027-10-05 | 45
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NRY-C2010 | Install UPS, network switches and field cabinets - Riyadh (Thumamah) | CON.NRY.INS | Construction | NRY | MS5 | 20% |  |  | 0.13944 |  | 97072 |  | MS5 Installation 20% x station price share 5.61% ¦ Installation key 20% x (1 - civil share 30.3%) | Annex 3 equipment sections A1-A5 (installation share) | 162 |  | 2027-09-02 | 2027-09-20 | 13
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NRY-C2020 | Cabling and termination (power, fibre, data) - Riyadh (Thumamah) | CON.NRY.INS | Construction | NRY | MS5 | 20% |  |  | 0.20916 |  | 145607 |  | MS5 Installation 20% x station price share 5.61% ¦ Installation key 30% x (1 - civil share 30.3%) | Annex 3 equipment sections A1-A5 (installation share) | 323 |  | 2027-09-08 | 2027-10-10 | 22
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NRY-C2030 | Install and aim CCTV cameras - Riyadh (Thumamah) | CON.NRY.INS | Construction | NRY | MS5 | 20% |  |  | 0.1743 |  | 121339 |  | MS5 Installation 20% x station price share 5.61% ¦ Installation key 25% x (1 - civil share 30.3%) | Annex 3 equipment sections A1-A5 (installation share) | 269 |  | 2027-10-11 | 2027-11-03 | 18
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NRY-C2040 | Install video management, video wall and control-room equipment - Riyadh (Thumamah) | CON.NRY.INS | Construction | NRY | MS5 | 20% |  |  | 0.10458 |  | 72804 |  | MS5 Installation 20% x station price share 5.61% ¦ Installation key 15% x (1 - civil share 30.3%) | Annex 3 equipment sections A1-A5 (installation share) | 162 |  | 2027-09-21 | 2027-10-12 | 15
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NRY-C2050 | Install access control and intercom - Riyadh (Thumamah) | CON.NRY.INS | Construction | NRY | MS5 | 20% |  |  | 0.06972 |  | 48536 |  | MS5 Installation 20% x station price share 5.61% ¦ Installation key 10% x (1 - civil share 30.3%) | Annex 3 equipment sections A1-A5 (installation share) | 108 |  | 2027-09-28 | 2027-10-14 | 13
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | NRY-T1010 | Pre-commissioning and loop checks - Riyadh (Thumamah) | COM.NRY.TST | Commissioning and handover | NRY | MS6 | 10% |  |  | 0.388 |  | 135054 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.61% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 162 |  | 2027-11-04 | 2027-11-10 | 5
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | NRY-T1020 | Site acceptance test (SAT) and commissioning - Riyadh (Thumamah) | COM.NRY.TST | Commissioning and handover | NRY | MS6 | 10% |  |  | 0.582 |  | 202582 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.61% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 189 |  | 2027-11-11 | 2027-11-22 | 8
SH-TRN | Training (per railway, allocated) | NRY-T2010 | Operator and maintenance training - Riyadh (Thumamah) | COM.NRY.TRN | Commissioning and handover | NRY | MS7 | 10% |  |  | 0.15 |  | 52212 |  | MS7 Final acceptance and handover 10% x station price share 5.61% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 108 |  | 2027-11-23 | 2027-12-06 | 10
A1-A5 | A1 to A5 equipment sections: trial operation share | NRY-T2020 | Trial operation (maximum 45 days) - Riyadh (Thumamah) | COM.NRY.TOA | Commissioning and handover | NRY | MS7 | 10% |  |  | 0.35 |  | 121828 |  | MS7 Final acceptance and handover 10% x station price share 5.61% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 162 |  | 2027-11-23 | 2028-01-03 | 30
A1-A5 | A1 to A5 equipment sections: handover share | NRY-T3010 | Taking-over application, SAR review and handover - Riyadh (Thumamah) | COM.NRY.TOA | Commissioning and handover | NRY | MS7 | 10% |  |  | 0.3 |  | 104424 |  | MS7 Final acceptance and handover 10% x station price share 5.61% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 162 |  | 2028-01-04 | 2028-02-02 | 22
A1-A5 | A1 to A5 equipment sections: mock-up approval share (carved from the testing share) | NRY-T1030 | Mock-up approval: site visit and SAR approval of the executed works (roll-out to other stations) - Riyadh (Thumamah) | COM.NRY.MOK | Commissioning and handover | NRY | MS6 | 10% |  |  | 0.03 |  | 10442 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.61% ¦ Mock-up approval key 3% of the SAT milestone (no separate Annex 3 item; carved from the testing share) | Annex 3 equipment sections A1-A5 (testing share) | 27 |  | 2027-11-04 | 2027-12-05 | 22
SH-DES | Design and engineering package (per railway, allocated to the station) | HMK-E1010 | Survey: submittal of site survey and as-found report - Makkah | ENG.HMK.SRV.SUB | Engineering | HMK | MS2 | 10% |  |  | 0.069 |  | 67000 |  | MS2 Engineering submittal 10% x station price share 15.66% ¦ Design stage key 6.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 124 |  | 2027-01-03 | 2027-02-04 | 25
SH-DES | Design and engineering package (per railway, allocated to the station) | HMK-E1020 | Survey: SAR approval of survey report - Makkah | ENG.HMK.SRV.APR | Engineering | HMK | MS3 | 10% |  |  | 0.05 |  | 48550 |  | MS3 SAR approval of engineering 10% x station price share 15.66% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 53 |  | 2027-02-07 | 2027-02-28 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HMK-E1030 | Concept design: submittal - Makkah | ENG.HMK.CNC.SUB | Engineering | HMK | MS2 | 10% |  |  | 0.098 |  | 95159 |  | MS2 Engineering submittal 10% x station price share 15.66% ¦ Design stage key 9.8% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 51 |  | 2027-02-07 | 2027-02-14 | 6
SH-DES | Design and engineering package (per railway, allocated to the station) | HMK-E1040 | Concept design: SAR review and approval - Makkah | ENG.HMK.CNC.APR | Engineering | HMK | MS3 | 10% |  |  | 0.1 |  | 97101 |  | MS3 SAR approval of engineering 10% x station price share 15.66% ¦ Design stage key 10.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 126 |  | 2027-02-15 | 2027-03-15 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HMK-E1050 | Preliminary design: submittal - Makkah | ENG.HMK.PRE.SUB | Engineering | HMK | MS2 | 10% |  |  | 0.196 |  | 190318 |  | MS2 Engineering submittal 10% x station price share 15.66% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 127 |  | 2027-02-15 | 2027-03-01 | 10
SH-DES | Design and engineering package (per railway, allocated to the station) | HMK-E1060 | Preliminary design: SAR review and approval - Makkah | ENG.HMK.PRE.APR | Engineering | HMK | MS3 | 10% |  |  | 0.2 |  | 194202 |  | MS3 SAR approval of engineering 10% x station price share 15.66% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 191 |  | 2027-03-02 | 2027-03-29 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HMK-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Makkah | ENG.HMK.DET.SUB | Engineering | HMK | MS2 | 10% |  |  | 0.392 |  | 380636 |  | MS2 Engineering submittal 10% x station price share 15.66% ¦ Design stage key 39.2% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 274 |  | 2027-03-02 | 2027-03-30 | 16
SH-DES | Design and engineering package (per railway, allocated to the station) | HMK-E1080 | Detailed design: SAR review and approval - Makkah | ENG.HMK.DET.APR | Engineering | HMK | MS3 | 10% |  |  | 0.4 |  | 388404 |  | MS3 SAR approval of engineering 10% x station price share 15.66% ¦ Design stage key 40.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 257 |  | 2027-03-31 | 2027-04-20 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HMK-E1090 | IFC and shop drawings: submittal - Makkah | ENG.HMK.IFC.SUB | Engineering | HMK | MS2 | 10% |  |  | 0.196 |  | 190318 |  | MS2 Engineering submittal 10% x station price share 15.66% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 101 |  | 2027-03-31 | 2027-04-08 | 7
SH-DES | Design and engineering package (per railway, allocated to the station) | HMK-E1100 | IFC and shop drawings: SAR approval and release - Makkah | ENG.HMK.IFC.APR | Engineering | HMK | MS3 | 10% |  |  | 0.2 |  | 194202 |  | MS3 SAR approval of engineering 10% x station price share 15.66% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 217 |  | 2027-04-11 | 2027-04-29 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HMK-E1110 | HCIS Stage 3 and 4 documents: preparation - Makkah | ENG.HMK.HCS.SUB | Engineering | HMK | MS2 | 10% |  |  | 0.049 |  | 47579 |  | MS2 Engineering submittal 10% x station price share 15.66% ¦ Design stage key 4.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 56 |  | 2027-03-17 | 2027-04-08 | 17
SH-DES | Design and engineering package (per railway, allocated to the station) | HMK-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Makkah | ENG.HMK.HCS.APR | Engineering | HMK | MS3 | 10% |  |  | 0.05 |  | 48550 |  | MS3 SAR approval of engineering 10% x station price share 15.66% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 50 |  | 2027-04-11 | 2027-04-29 | 15
SH-DES, SH-TRN | Design and engineering package (per railway, allocated to the station) and Training (per railway, allocated): documentation and training share | HMK-E1130 | As-built and O&M documentation: submittal - Makkah | ENG.HMK.ASB.SUB | Engineering | HMK | MS7 | 10% |  |  | 0.15 |  | 145651 |  | MS7 Final acceptance and handover 10% x station price share 15.66% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 133 |  | 2028-03-08 | 2028-05-16 | 45
SH-DES | Design and engineering package (per railway, allocated to the station): documentation share | HMK-E1140 | As-built and O&M documentation: SAR review and approval - Makkah | ENG.HMK.ASB.APR | Engineering | HMK | MS7 | 10% |  |  | 0.05 |  | 48550 |  | MS7 Final acceptance and handover 10% x station price share 15.66% ¦ Fixed key 5% | Annex 3 documentation share | 44 |  | 2028-05-17 | 2028-06-06 | 15
- | No BOQ cost: administrative or review step with no payment milestone | HMK-X1010 | Enabling works: site preparation, setting out, temporary works and utilities clearance - Makkah | CON.HMK.ENA | Construction | HMK | MS5 | 20% |  |  | 0.0040508 |  | 7867 |  | MS5 Installation 20% x station price share 15.66% ¦ BOQ civil share 10.1% x 4% (enabling: site preparation) | Annex 3 A6 Civil works (SAR 571,639) | 150 |  | 2027-05-02 | 2027-05-13 | 10
- | No BOQ cost: administrative or review step with no payment milestone | HMK-X1020 | Enabling works: cable routes, duct-bank and cabinet plinth preparation - Makkah | CON.HMK.ENA | Construction | HMK | MS5 | 20% |  |  | 0.0060762 |  | 11800 |  | MS5 Installation 20% x station price share 15.66% ¦ BOQ civil share 10.1% x 6% (enabling: routes, ducts, plinths) | Annex 3 A6 Civil works (SAR 571,639) | 226 |  | 2027-05-23 | 2027-06-10 | 15
A1 | A1 CCTV system | HMK-P1010 | Manufacture CCTV cameras and analytics - Makkah | PRO.HMK.CCT | Procurement | HMK | MS4 | 20% |  |  | 0.24396 |  | 473780 |  | MS4 Material delivery 20% x station price share 15.66% ¦ BOQ section share 32.5% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 1,650,175) | 1175 |  | 2027-05-02 | 2027-08-29 | 81
A2 | A2 Video management and video wall | HMK-P1020 | Manufacture video management servers, storage and video wall - Makkah | PRO.HMK.VMS | Procurement | HMK | MS4 | 20% |  |  | 0.081643 |  | 158552 |  | MS4 Material delivery 20% x station price share 15.66% ¦ BOQ section share 10.9% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 552,237) | 393 |  | 2027-05-02 | 2027-08-29 | 81
A3 | A3 Access control and intercom | HMK-P1030 | Manufacture access control and intercom equipment - Makkah | PRO.HMK.ACC | Procurement | HMK | MS4 | 20% |  |  | 0.0065175 |  | 12657 |  | MS4 Material delivery 20% x station price share 15.66% ¦ BOQ section share 0.9% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 31 |  | 2027-05-02 | 2027-08-29 | 81
A4, A5 | A4 UPS and A5 Poles, cabinets and network | HMK-P1040 | Manufacture UPS, network switches and field cabinets - Makkah | PRO.HMK.UPN | Procurement | HMK | MS4 | 20% |  |  | 0.41788 |  | 811524 |  | MS4 Material delivery 20% x station price share 15.66% ¦ BOQ section share 55.7% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 2,826,539) | 2011 |  | 2027-05-02 | 2027-08-29 | 81
SH-FAT | Factory acceptance test (per railway, allocated) | HMK-P1050 | Factory acceptance test at vendor premises - Makkah | PRO.HMK.LOG | Procurement | HMK | MS4 | 20% |  |  | 0.05 |  | 97101 |  | MS4 Material delivery 20% x station price share 15.66% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 601 |  | 2027-08-30 | 2027-09-12 | 10
A1-A5 | A1 to A5 equipment sections: logistics (shipping, customs, delivery) share | HMK-P1060 | Shipping and customs clearance - Makkah | PRO.HMK.LOG | Procurement | HMK | MS4 | 20% |  |  | 0.15 |  | 291303 |  | MS4 Material delivery 20% x station price share 15.66% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 1204 |  | 2027-09-13 | 2027-11-01 | 35
SH-SPR | Commissioning spares (per railway, allocated) | HMK-P1070 | Delivery to station and receiving inspection - Makkah | PRO.HMK.LOG | Procurement | HMK | MS4 | 20% |  |  | 0.05 |  | 97101 |  | MS4 Material delivery 20% x station price share 15.66% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 601 |  | 2027-11-02 | 2027-11-08 | 5
A6 | A6 Civil works | HMK-C1010 | Civil: platform trenches and duct banks - Makkah | CON.HMK.CIV | Construction | HMK | MS5 | 20% |  |  | 0.050635 |  | 98335 |  | MS5 Installation 20% x station price share 15.66% ¦ BOQ civil share 10.1% x 50% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 571,639) | 977 |  | 2027-06-13 | 2027-08-17 | 48
A6 | A6 Civil works | HMK-C1020 | Civil: camera and ALPR pole foundations and poles - Makkah | CON.HMK.CIV | Construction | HMK | MS5 | 20% |  |  | 0.040508 |  | 78668 |  | MS5 Installation 20% x station price share 15.66% ¦ BOQ civil share 10.1% x 40% (poles) | Annex 3 A6 Civil works (SAR 571,639) | 752 |  | 2027-07-26 | 2027-09-14 | 37
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | HMK-C2010 | Install UPS, network switches and field cabinets - Makkah | CON.HMK.INS | Construction | HMK | MS5 | 20% |  |  | 0.17975 |  | 349070 |  | MS5 Installation 20% x station price share 15.66% ¦ Installation key 20% x (1 - civil share 10.1%) | Annex 3 equipment sections A1-A5 (installation share) | 451 |  | 2027-11-09 | 2027-12-12 | 24
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | HMK-C2020 | Cabling and termination (power, fibre, data) - Makkah | CON.HMK.INS | Construction | HMK | MS5 | 20% |  |  | 0.26962 |  | 523604 |  | MS5 Installation 20% x station price share 15.66% ¦ Installation key 30% x (1 - civil share 10.1%) | Annex 3 equipment sections A1-A5 (installation share) | 902 |  | 2027-11-21 | 2028-01-16 | 41
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | HMK-C2030 | Install and aim CCTV cameras - Makkah | CON.HMK.INS | Construction | HMK | MS5 | 20% |  |  | 0.22468 |  | 436337 |  | MS5 Installation 20% x station price share 15.66% ¦ Installation key 25% x (1 - civil share 10.1%) | Annex 3 equipment sections A1-A5 (installation share) | 752 |  | 2028-01-17 | 2028-03-07 | 32
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | HMK-C2040 | Install video management, video wall and control-room equipment - Makkah | CON.HMK.INS | Construction | HMK | MS5 | 20% |  |  | 0.13481 |  | 261802 |  | MS5 Installation 20% x station price share 15.66% ¦ Installation key 15% x (1 - civil share 10.1%) | Annex 3 equipment sections A1-A5 (installation share) | 451 |  | 2027-12-13 | 2028-01-19 | 28
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | HMK-C2050 | Install access control and intercom - Makkah | CON.HMK.INS | Construction | HMK | MS5 | 20% |  |  | 0.089873 |  | 174535 |  | MS5 Installation 20% x station price share 15.66% ¦ Installation key 10% x (1 - civil share 10.1%) | Annex 3 equipment sections A1-A5 (installation share) | 301 |  | 2027-12-23 | 2028-01-25 | 24
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | HMK-T1010 | Pre-commissioning and loop checks - Makkah | COM.HMK.TST | Commissioning and handover | HMK | MS6 | 10% |  |  | 0.4 |  | 388404 |  | MS6 Testing and commissioning (SAT) 10% x station price share 15.66% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 451 |  | 2028-03-08 | 2028-03-23 | 12
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | HMK-T1020 | Site acceptance test (SAT) and commissioning - Makkah | COM.HMK.TST | Commissioning and handover | HMK | MS6 | 10% |  |  | 0.6 |  | 582605 |  | MS6 Testing and commissioning (SAT) 10% x station price share 15.66% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 601 |  | 2028-03-26 | 2028-04-18 | 18
SH-TRN | Training (per railway, allocated) | HMK-T2010 | Operator and maintenance training - Makkah | COM.HMK.TRN | Commissioning and handover | HMK | MS7 | 10% |  |  | 0.15 |  | 145651 |  | MS7 Final acceptance and handover 10% x station price share 15.66% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 301 |  | 2028-04-19 | 2028-05-09 | 10
A1-A5 | A1 to A5 equipment sections: trial operation share | HMK-T2020 | Trial operation (maximum 45 days) - Makkah | COM.HMK.TOA | Commissioning and handover | HMK | MS7 | 10% |  |  | 0.35 |  | 339853 |  | MS7 Final acceptance and handover 10% x station price share 15.66% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 451 |  | 2028-04-19 | 2028-06-06 | 30
A1-A5 | A1 to A5 equipment sections: handover share | HMK-T3010 | Taking-over application, SAR review and handover - Makkah | COM.HMK.TOA | Commissioning and handover | HMK | MS7 | 10% |  |  | 0.3 |  | 291303 |  | MS7 Final acceptance and handover 10% x station price share 15.66% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 451 |  | 2028-06-07 | 2028-07-06 | 22
SH-DES | Design and engineering package (per railway, allocated to the station) | ERY-E1010 | Survey: submittal of site survey and as-found report - Riyadh (Malaz) | ENG.ERY.SRV.SUB | Engineering | ERY | MS2 | 10% |  |  | 0.069 |  | 21331 |  | MS2 Engineering submittal 10% x station price share 4.99% ¦ Design stage key 6.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 27 |  | 2027-01-03 | 2027-01-12 | 8
SH-DES | Design and engineering package (per railway, allocated to the station) | ERY-E1020 | Survey: SAR approval of survey report - Riyadh (Malaz) | ENG.ERY.SRV.APR | Engineering | ERY | MS3 | 10% |  |  | 0.05 |  | 15458 |  | MS3 SAR approval of engineering 10% x station price share 4.99% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 29 |  | 2027-01-13 | 2027-02-02 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | ERY-E1030 | Concept design: submittal - Riyadh (Malaz) | ENG.ERY.CNC.SUB | Engineering | ERY | MS2 | 10% |  |  | 0.098 |  | 30297 |  | MS2 Engineering submittal 10% x station price share 4.99% ¦ Design stage key 9.8% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 20 |  | 2027-01-13 | 2027-01-24 | 8
SH-DES | Design and engineering package (per railway, allocated to the station) | ERY-E1040 | Concept design: SAR review and approval - Riyadh (Malaz) | ENG.ERY.CNC.APR | Engineering | ERY | MS3 | 10% |  |  | 0.1 |  | 30915 |  | MS3 SAR approval of engineering 10% x station price share 4.99% ¦ Design stage key 10.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 37 |  | 2027-01-25 | 2027-02-14 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | ERY-E1050 | Preliminary design: submittal - Riyadh (Malaz) | ENG.ERY.PRE.SUB | Engineering | ERY | MS2 | 10% |  |  | 0.196 |  | 60594 |  | MS2 Engineering submittal 10% x station price share 4.99% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 49 |  | 2027-01-25 | 2027-02-11 | 14
SH-DES | Design and engineering package (per railway, allocated to the station) | ERY-E1060 | Preliminary design: SAR review and approval - Riyadh (Malaz) | ENG.ERY.PRE.APR | Engineering | ERY | MS3 | 10% |  |  | 0.2 |  | 61830 |  | MS3 SAR approval of engineering 10% x station price share 4.99% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 52 |  | 2027-02-14 | 2027-03-14 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | ERY-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Riyadh (Malaz) | ENG.ERY.DET.SUB | Engineering | ERY | MS2 | 10% |  |  | 0.392 |  | 121188 |  | MS2 Engineering submittal 10% x station price share 4.99% ¦ Design stage key 39.2% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 100 |  | 2027-02-14 | 2027-03-23 | 22
SH-DES | Design and engineering package (per railway, allocated to the station) | ERY-E1080 | Detailed design: SAR review and approval - Riyadh (Malaz) | ENG.ERY.DET.APR | Engineering | ERY | MS3 | 10% |  |  | 0.4 |  | 123661 |  | MS3 SAR approval of engineering 10% x station price share 4.99% ¦ Design stage key 40.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 68 |  | 2027-03-24 | 2027-04-13 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | ERY-E1090 | IFC and shop drawings: submittal - Riyadh (Malaz) | ENG.ERY.IFC.SUB | Engineering | ERY | MS2 | 10% |  |  | 0.196 |  | 60594 |  | MS2 Engineering submittal 10% x station price share 4.99% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 45 |  | 2027-03-24 | 2027-04-08 | 12
SH-DES | Design and engineering package (per railway, allocated to the station) | ERY-E1100 | IFC and shop drawings: SAR approval and release - Riyadh (Malaz) | ENG.ERY.IFC.APR | Engineering | ERY | MS3 | 10% |  |  | 0.2 |  | 61830 |  | MS3 SAR approval of engineering 10% x station price share 4.99% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 56 |  | 2027-04-11 | 2027-04-29 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | ERY-E1110 | HCIS Stage 3 and 4 documents: preparation - Riyadh (Malaz) | ENG.ERY.HCS.SUB | Engineering | ERY | MS2 | 10% |  |  | 0.049 |  | 15148 |  | MS2 Engineering submittal 10% x station price share 4.99% ¦ Design stage key 4.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 21 |  | 2027-02-25 | 2027-04-08 | 26
SH-DES | Design and engineering package (per railway, allocated to the station) | ERY-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Riyadh (Malaz) | ENG.ERY.HCS.APR | Engineering | ERY | MS3 | 10% |  |  | 0.05 |  | 15458 |  | MS3 SAR approval of engineering 10% x station price share 4.99% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 12 |  | 2027-04-11 | 2027-04-29 | 15
SH-DES, SH-TRN | Design and engineering package (per railway, allocated to the station) and Training (per railway, allocated): documentation and training share | ERY-E1130 | As-built and O&M documentation: submittal - Riyadh (Malaz) | ENG.ERY.ASB.SUB | Engineering | ERY | MS7 | 10% |  |  | 0.15 |  | 46373 |  | MS7 Final acceptance and handover 10% x station price share 4.99% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 36 |  | 2027-10-19 | 2027-11-24 | 27
SH-DES | Design and engineering package (per railway, allocated to the station): documentation share | ERY-E1140 | As-built and O&M documentation: SAR review and approval - Riyadh (Malaz) | ENG.ERY.ASB.APR | Engineering | ERY | MS7 | 10% |  |  | 0.05 |  | 15458 |  | MS7 Final acceptance and handover 10% x station price share 4.99% ¦ Fixed key 5% | Annex 3 documentation share | 20 |  | 2027-11-25 | 2027-12-15 | 15
- | No BOQ cost: administrative or review step with no payment milestone | ERY-X1010 | Enabling works: site preparation, setting out, temporary works and utilities clearance - Riyadh (Malaz) | CON.ERY.ENA | Construction | ERY | MS5 | 20% |  |  | 0.014237 |  | 8803 |  | MS5 Installation 20% x station price share 4.99% ¦ BOQ civil share 35.6% x 4% (enabling: site preparation) | Annex 3 A6 Civil works (SAR 701,825) | 48 |  | 2027-05-02 | 2027-05-06 | 5
- | No BOQ cost: administrative or review step with no payment milestone | ERY-X1020 | Enabling works: cable routes, duct-bank and cabinet plinth preparation - Riyadh (Malaz) | CON.ERY.ENA | Construction | ERY | MS5 | 20% |  |  | 0.021356 |  | 13205 |  | MS5 Installation 20% x station price share 4.99% ¦ BOQ civil share 35.6% x 6% (enabling: routes, ducts, plinths) | Annex 3 A6 Civil works (SAR 701,825) | 72 |  | 2027-05-09 | 2027-05-27 | 10
A1 | A1 CCTV system | ERY-P1010 | Manufacture CCTV cameras and analytics - Riyadh (Malaz) | PRO.ERY.CCT | Procurement | ERY | MS4 | 20% |  |  | 0.1635 |  | 101092 |  | MS4 Material delivery 20% x station price share 4.99% ¦ BOQ section share 21.8% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 276,849) | 250 |  | 2027-05-02 | 2027-07-06 | 43
A2 | A2 Video management and video wall | ERY-P1020 | Manufacture video management servers, storage and video wall - Riyadh (Malaz) | PRO.ERY.VMS | Procurement | ERY | MS4 | 20% |  |  | 0.20721 |  | 128120 |  | MS4 Material delivery 20% x station price share 4.99% ¦ BOQ section share 27.6% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 350,866) | 317 |  | 2027-05-02 | 2027-07-06 | 43
A3 | A3 Access control and intercom | ERY-P1030 | Manufacture access control and intercom equipment - Riyadh (Malaz) | PRO.ERY.ACC | Procurement | ERY | MS4 | 20% |  |  | 0.026035 |  | 16098 |  | MS4 Material delivery 20% x station price share 4.99% ¦ BOQ section share 3.5% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 40 |  | 2027-05-02 | 2027-07-06 | 43
A4, A5 | A4 UPS and A5 Poles, cabinets and network | ERY-P1040 | Manufacture UPS, network switches and field cabinets - Riyadh (Malaz) | PRO.ERY.UPN | Procurement | ERY | MS4 | 20% |  |  | 0.35325 |  | 218418 |  | MS4 Material delivery 20% x station price share 4.99% ¦ BOQ section share 47.1% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 598,156) | 541 |  | 2027-05-02 | 2027-07-06 | 43
SH-FAT | Factory acceptance test (per railway, allocated) | ERY-P1050 | Factory acceptance test at vendor premises - Riyadh (Malaz) | PRO.ERY.LOG | Procurement | ERY | MS4 | 20% |  |  | 0.05 |  | 30915 |  | MS4 Material delivery 20% x station price share 4.99% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 191 |  | 2027-07-07 | 2027-07-20 | 10
A1-A5 | A1 to A5 equipment sections: logistics (shipping, customs, delivery) share | ERY-P1060 | Shipping and customs clearance - Riyadh (Malaz) | PRO.ERY.LOG | Procurement | ERY | MS4 | 20% |  |  | 0.15 |  | 92746 |  | MS4 Material delivery 20% x station price share 4.99% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 383 |  | 2027-07-21 | 2027-08-17 | 20
SH-SPR | Commissioning spares (per railway, allocated) | ERY-P1070 | Delivery to station and receiving inspection - Riyadh (Malaz) | PRO.ERY.LOG | Procurement | ERY | MS4 | 20% |  |  | 0.05 |  | 30915 |  | MS4 Material delivery 20% x station price share 4.99% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 191 |  | 2027-08-18 | 2027-08-24 | 5
A6 | A6 Civil works | ERY-C1010 | Civil: platform trenches and duct banks - Riyadh (Malaz) | CON.ERY.CIV | Construction | ERY | MS5 | 20% |  |  | 0.17797 |  | 110038 |  | MS5 Installation 20% x station price share 4.99% ¦ BOQ civil share 35.6% x 50% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 701,825) | 311 |  | 2027-05-30 | 2027-08-12 | 55
A6 | A6 Civil works | ERY-C1020 | Civil: camera and ALPR pole foundations and poles - Riyadh (Malaz) | CON.ERY.CIV | Construction | ERY | MS5 | 20% |  |  | 0.14237 |  | 88030 |  | MS5 Installation 20% x station price share 4.99% ¦ BOQ civil share 35.6% x 40% (poles) | Annex 3 A6 Civil works (SAR 701,825) | 239 |  | 2027-07-18 | 2027-09-14 | 43
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | ERY-C2010 | Install UPS, network switches and field cabinets - Riyadh (Malaz) | CON.ERY.INS | Construction | ERY | MS5 | 20% |  |  | 0.12881 |  | 79646 |  | MS5 Installation 20% x station price share 4.99% ¦ Installation key 20% x (1 - civil share 35.6%) | Annex 3 equipment sections A1-A5 (installation share) | 144 |  | 2027-08-25 | 2027-09-08 | 11
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | ERY-C2020 | Cabling and termination (power, fibre, data) - Riyadh (Malaz) | CON.ERY.INS | Construction | ERY | MS5 | 20% |  |  | 0.19322 |  | 119468 |  | MS5 Installation 20% x station price share 4.99% ¦ Installation key 30% x (1 - civil share 35.6%) | Annex 3 equipment sections A1-A5 (installation share) | 287 |  | 2027-08-31 | 2027-09-27 | 19
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | ERY-C2030 | Install and aim CCTV cameras - Riyadh (Malaz) | CON.ERY.INS | Construction | ERY | MS5 | 20% |  |  | 0.16102 |  | 99557 |  | MS5 Installation 20% x station price share 4.99% ¦ Installation key 25% x (1 - civil share 35.6%) | Annex 3 equipment sections A1-A5 (installation share) | 239 |  | 2027-09-28 | 2027-10-18 | 15
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | ERY-C2040 | Install video management, video wall and control-room equipment - Riyadh (Malaz) | CON.ERY.INS | Construction | ERY | MS5 | 20% |  |  | 0.09661 |  | 59734 |  | MS5 Installation 20% x station price share 4.99% ¦ Installation key 15% x (1 - civil share 35.6%) | Annex 3 equipment sections A1-A5 (installation share) | 144 |  | 2027-09-09 | 2027-09-28 | 13
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | ERY-C2050 | Install access control and intercom - Riyadh (Malaz) | CON.ERY.INS | Construction | ERY | MS5 | 20% |  |  | 0.064407 |  | 39823 |  | MS5 Installation 20% x station price share 4.99% ¦ Installation key 10% x (1 - civil share 35.6%) | Annex 3 equipment sections A1-A5 (installation share) | 96 |  | 2027-09-15 | 2027-09-30 | 11
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | ERY-T1010 | Pre-commissioning and loop checks - Riyadh (Malaz) | COM.ERY.TST | Commissioning and handover | ERY | MS6 | 10% |  |  | 0.4 |  | 123661 |  | MS6 Testing and commissioning (SAT) 10% x station price share 4.99% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 144 |  | 2027-10-19 | 2027-10-25 | 5
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | ERY-T1020 | Site acceptance test (SAT) and commissioning - Riyadh (Malaz) | COM.ERY.TST | Commissioning and handover | ERY | MS6 | 10% |  |  | 0.6 |  | 185491 |  | MS6 Testing and commissioning (SAT) 10% x station price share 4.99% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 191 |  | 2027-10-26 | 2027-11-03 | 7
SH-TRN | Training (per railway, allocated) | ERY-T2010 | Operator and maintenance training - Riyadh (Malaz) | COM.ERY.TRN | Commissioning and handover | ERY | MS7 | 10% |  |  | 0.15 |  | 46373 |  | MS7 Final acceptance and handover 10% x station price share 4.99% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 96 |  | 2027-11-04 | 2027-11-17 | 10
A1-A5 | A1 to A5 equipment sections: trial operation share | ERY-T2020 | Trial operation (maximum 45 days) - Riyadh (Malaz) | COM.ERY.TOA | Commissioning and handover | ERY | MS7 | 10% |  |  | 0.35 |  | 108203 |  | MS7 Final acceptance and handover 10% x station price share 4.99% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 144 |  | 2027-11-04 | 2027-12-15 | 30
A1-A5 | A1 to A5 equipment sections: handover share | ERY-T3010 | Taking-over application, SAR review and handover - Riyadh (Malaz) | COM.ERY.TOA | Commissioning and handover | ERY | MS7 | 10% |  |  | 0.3 |  | 92746 |  | MS7 Final acceptance and handover 10% x station price share 4.99% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 144 |  | 2027-12-16 | 2028-01-16 | 22
SH-DES | Design and engineering package (per railway, allocated to the station) | HJD-E1010 | Survey: submittal of site survey and as-found report - Jeddah | ENG.HJD.SRV.SUB | Engineering | HJD | MS2 | 10% |  |  | 0.069 |  | 65901 |  | MS2 Engineering submittal 10% x station price share 15.40% ¦ Design stage key 6.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 117 |  | 2027-02-25 | 2027-04-01 | 21
SH-DES | Design and engineering package (per railway, allocated to the station) | HJD-E1020 | Survey: SAR approval of survey report - Jeddah | ENG.HJD.SRV.APR | Engineering | HJD | MS3 | 10% |  |  | 0.05 |  | 47754 |  | MS3 SAR approval of engineering 10% x station price share 15.40% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 58 |  | 2027-04-04 | 2027-04-22 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HJD-E1030 | Concept design: submittal - Jeddah | ENG.HJD.CNC.SUB | Engineering | HJD | MS2 | 10% |  |  | 0.098 |  | 93599 |  | MS2 Engineering submittal 10% x station price share 15.40% ¦ Design stage key 9.8% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 50 |  | 2027-04-04 | 2027-04-11 | 6
SH-DES | Design and engineering package (per railway, allocated to the station) | HJD-E1040 | Concept design: SAR review and approval - Jeddah | ENG.HJD.CNC.APR | Engineering | HJD | MS3 | 10% |  |  | 0.1 |  | 95509 |  | MS3 SAR approval of engineering 10% x station price share 15.40% ¦ Design stage key 10.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 124 |  | 2027-04-12 | 2027-05-02 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HJD-E1050 | Preliminary design: submittal - Jeddah | ENG.HJD.PRE.SUB | Engineering | HJD | MS2 | 10% |  |  | 0.196 |  | 187197 |  | MS2 Engineering submittal 10% x station price share 15.40% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 125 |  | 2027-04-12 | 2027-04-25 | 10
SH-DES | Design and engineering package (per railway, allocated to the station) | HJD-E1060 | Preliminary design: SAR review and approval - Jeddah | ENG.HJD.PRE.APR | Engineering | HJD | MS3 | 10% |  |  | 0.2 |  | 191018 |  | MS3 SAR approval of engineering 10% x station price share 15.40% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 188 |  | 2027-04-26 | 2027-05-23 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HJD-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Jeddah | ENG.HJD.DET.SUB | Engineering | HJD | MS2 | 10% |  |  | 0.392 |  | 374395 |  | MS2 Engineering submittal 10% x station price share 15.40% ¦ Design stage key 39.2% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 269 |  | 2027-04-26 | 2027-05-24 | 16
SH-DES | Design and engineering package (per railway, allocated to the station) | HJD-E1080 | Detailed design: SAR review and approval - Jeddah | ENG.HJD.DET.APR | Engineering | HJD | MS3 | 10% |  |  | 0.4 |  | 382035 |  | MS3 SAR approval of engineering 10% x station price share 15.40% ¦ Design stage key 40.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 252 |  | 2027-05-25 | 2027-06-14 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HJD-E1090 | IFC and shop drawings: submittal - Jeddah | ENG.HJD.IFC.SUB | Engineering | HJD | MS2 | 10% |  |  | 0.196 |  | 187197 |  | MS2 Engineering submittal 10% x station price share 15.40% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 109 |  | 2027-05-25 | 2027-06-03 | 8
SH-DES | Design and engineering package (per railway, allocated to the station) | HJD-E1100 | IFC and shop drawings: SAR approval and release - Jeddah | ENG.HJD.IFC.APR | Engineering | HJD | MS3 | 10% |  |  | 0.2 |  | 191018 |  | MS3 SAR approval of engineering 10% x station price share 15.40% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 204 |  | 2027-06-06 | 2027-06-24 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HJD-E1110 | HCIS Stage 3 and 4 documents: preparation - Jeddah | ENG.HJD.HCS.SUB | Engineering | HJD | MS2 | 10% |  |  | 0.049 |  | 46799 |  | MS2 Engineering submittal 10% x station price share 15.40% ¦ Design stage key 4.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 57 |  | 2027-05-04 | 2027-06-03 | 18
SH-DES | Design and engineering package (per railway, allocated to the station) | HJD-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Jeddah | ENG.HJD.HCS.APR | Engineering | HJD | MS3 | 10% |  |  | 0.05 |  | 47754 |  | MS3 SAR approval of engineering 10% x station price share 15.40% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 47 |  | 2027-06-06 | 2027-06-24 | 15
SH-DES, SH-TRN | Design and engineering package (per railway, allocated to the station) and Training (per railway, allocated): documentation and training share | HJD-E1130 | As-built and O&M documentation: submittal - Jeddah | ENG.HJD.ASB.SUB | Engineering | HJD | MS7 | 10% |  |  | 0.15 |  | 143263 |  | MS7 Final acceptance and handover 10% x station price share 15.40% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 127 |  | 2028-04-06 | 2028-06-08 | 41
SH-DES | Design and engineering package (per railway, allocated to the station): documentation share | HJD-E1140 | As-built and O&M documentation: SAR review and approval - Jeddah | ENG.HJD.ASB.APR | Engineering | HJD | MS7 | 10% |  |  | 0.05 |  | 47754 |  | MS7 Final acceptance and handover 10% x station price share 15.40% ¦ Fixed key 5% | Annex 3 documentation share | 47 |  | 2028-06-11 | 2028-06-29 | 15
- | No BOQ cost: administrative or review step with no payment milestone | HJD-X1010 | Enabling works: site preparation, setting out, temporary works and utilities clearance - Jeddah | CON.HJD.ENA | Construction | HJD | MS5 | 20% |  |  | 0.0037587 |  | 7180 |  | MS5 Installation 20% x station price share 15.40% ¦ BOQ civil share 9.4% x 4% (enabling: site preparation) | Annex 3 A6 Civil works (SAR 521,718) | 148 |  | 2027-06-27 | 2027-07-01 | 5
- | No BOQ cost: administrative or review step with no payment milestone | HJD-X1020 | Enabling works: cable routes, duct-bank and cabinet plinth preparation - Jeddah | CON.HJD.ENA | Construction | HJD | MS5 | 20% |  |  | 0.005638 |  | 10770 |  | MS5 Installation 20% x station price share 15.40% ¦ BOQ civil share 9.4% x 6% (enabling: routes, ducts, plinths) | Annex 3 A6 Civil works (SAR 521,718) | 222 |  | 2027-07-04 | 2027-07-15 | 10
A1 | A1 CCTV system | HJD-P1010 | Manufacture CCTV cameras and analytics - Jeddah | PRO.HJD.CCT | Procurement | HJD | MS4 | 20% |  |  | 0.20742 |  | 396208 |  | MS4 Material delivery 20% x station price share 15.40% ¦ BOQ section share 27.7% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 1,391,206) | 982 |  | 2027-06-27 | 2027-10-17 | 80
A2 | A2 Video management and video wall | HJD-P1020 | Manufacture video management servers, storage and video wall - Jeddah | PRO.HJD.VMS | Procurement | HJD | MS4 | 20% |  |  | 0.097222 |  | 185712 |  | MS4 Material delivery 20% x station price share 15.40% ¦ BOQ section share 13.0% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 652,091) | 460 |  | 2027-06-27 | 2027-10-17 | 80
A3 | A3 Access control and intercom | HJD-P1030 | Manufacture access control and intercom equipment - Jeddah | PRO.HJD.ACC | Procurement | HJD | MS4 | 20% |  |  | 0.0065728 |  | 12555 |  | MS4 Material delivery 20% x station price share 15.40% ¦ BOQ section share 0.9% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 31 |  | 2027-06-27 | 2027-10-17 | 80
A4, A5 | A4 UPS and A5 Poles, cabinets and network | HJD-P1040 | Manufacture UPS, network switches and field cabinets - Jeddah | PRO.HJD.UPN | Procurement | HJD | MS4 | 20% |  |  | 0.43879 |  | 838156 |  | MS4 Material delivery 20% x station price share 15.40% ¦ BOQ section share 58.5% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 2,943,020) | 2077 |  | 2027-06-27 | 2027-10-17 | 80
SH-FAT | Factory acceptance test (per railway, allocated) | HJD-P1050 | Factory acceptance test at vendor premises - Jeddah | PRO.HJD.LOG | Procurement | HJD | MS4 | 20% |  |  | 0.05 |  | 95509 |  | MS4 Material delivery 20% x station price share 15.40% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 592 |  | 2027-10-18 | 2027-10-31 | 10
A1-A5 | A1 to A5 equipment sections: logistics (shipping, customs, delivery) share | HJD-P1060 | Shipping and customs clearance - Jeddah | PRO.HJD.LOG | Procurement | HJD | MS4 | 20% |  |  | 0.15 |  | 286526 |  | MS4 Material delivery 20% x station price share 15.40% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 1184 |  | 2027-11-01 | 2027-12-19 | 35
SH-SPR | Commissioning spares (per railway, allocated) | HJD-P1070 | Delivery to station and receiving inspection - Jeddah | PRO.HJD.LOG | Procurement | HJD | MS4 | 20% |  |  | 0.05 |  | 95509 |  | MS4 Material delivery 20% x station price share 15.40% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 592 |  | 2027-12-20 | 2027-12-26 | 5
A6 | A6 Civil works | HJD-C1010 | Civil: platform trenches and duct banks - Jeddah | CON.HJD.CIV | Construction | HJD | MS5 | 20% |  |  | 0.046984 |  | 89747 |  | MS5 Installation 20% x station price share 15.40% ¦ BOQ civil share 9.4% x 50% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 521,718) | 961 |  | 2027-07-18 | 2027-09-15 | 44
A6 | A6 Civil works | HJD-C1020 | Civil: camera and ALPR pole foundations and poles - Jeddah | CON.HJD.CIV | Construction | HJD | MS5 | 20% |  |  | 0.037587 |  | 71798 |  | MS5 Installation 20% x station price share 15.40% ¦ BOQ civil share 9.4% x 40% (poles) | Annex 3 A6 Civil works (SAR 521,718) | 739 |  | 2027-08-25 | 2027-10-13 | 35
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | HJD-C2010 | Install UPS, network switches and field cabinets - Jeddah | CON.HJD.INS | Construction | HJD | MS5 | 20% |  |  | 0.18121 |  | 346136 |  | MS5 Installation 20% x station price share 15.40% ¦ Installation key 20% x (1 - civil share 9.4%) | Annex 3 equipment sections A1-A5 (installation share) | 444 |  | 2027-12-27 | 2028-01-23 | 20
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | HJD-C2020 | Cabling and termination (power, fibre, data) - Jeddah | CON.HJD.INS | Construction | HJD | MS5 | 20% |  |  | 0.27181 |  | 519205 |  | MS5 Installation 20% x station price share 15.40% ¦ Installation key 30% x (1 - civil share 9.4%) | Annex 3 equipment sections A1-A5 (installation share) | 887 |  | 2028-01-05 | 2028-02-28 | 34
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | HJD-C2030 | Install and aim CCTV cameras - Jeddah | CON.HJD.INS | Construction | HJD | MS5 | 20% |  |  | 0.22651 |  | 432670 |  | MS5 Installation 20% x station price share 15.40% ¦ Installation key 25% x (1 - civil share 9.4%) | Annex 3 equipment sections A1-A5 (installation share) | 739 |  | 2028-02-29 | 2028-04-05 | 27
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | HJD-C2040 | Install video management, video wall and control-room equipment - Jeddah | CON.HJD.INS | Construction | HJD | MS5 | 20% |  |  | 0.1359 |  | 259602 |  | MS5 Installation 20% x station price share 15.40% ¦ Installation key 15% x (1 - civil share 9.4%) | Annex 3 equipment sections A1-A5 (installation share) | 444 |  | 2028-01-24 | 2028-03-02 | 24
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | HJD-C2050 | Install access control and intercom - Jeddah | CON.HJD.INS | Construction | HJD | MS5 | 20% |  |  | 0.090603 |  | 173068 |  | MS5 Installation 20% x station price share 15.40% ¦ Installation key 10% x (1 - civil share 9.4%) | Annex 3 equipment sections A1-A5 (installation share) | 296 |  | 2028-02-02 | 2028-03-07 | 20
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | HJD-T1010 | Pre-commissioning and loop checks - Jeddah | COM.HJD.TST | Commissioning and handover | HJD | MS6 | 10% |  |  | 0.4 |  | 382035 |  | MS6 Testing and commissioning (SAT) 10% x station price share 15.40% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 444 |  | 2028-04-06 | 2028-04-19 | 10
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | HJD-T1020 | Site acceptance test (SAT) and commissioning - Jeddah | COM.HJD.TST | Commissioning and handover | HJD | MS6 | 10% |  |  | 0.6 |  | 573052 |  | MS6 Testing and commissioning (SAT) 10% x station price share 15.40% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 592 |  | 2028-04-20 | 2028-05-18 | 16
SH-TRN | Training (per railway, allocated) | HJD-T2010 | Operator and maintenance training - Jeddah | COM.HJD.TRN | Commissioning and handover | HJD | MS7 | 10% |  |  | 0.15 |  | 143263 |  | MS7 Final acceptance and handover 10% x station price share 15.40% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 296 |  | 2028-05-21 | 2028-06-01 | 10
A1-A5 | A1 to A5 equipment sections: trial operation share | HJD-T2020 | Trial operation (maximum 45 days) - Jeddah | COM.HJD.TOA | Commissioning and handover | HJD | MS7 | 10% |  |  | 0.35 |  | 334281 |  | MS7 Final acceptance and handover 10% x station price share 15.40% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 444 |  | 2028-05-21 | 2028-06-29 | 30
A1-A5 | A1 to A5 equipment sections: handover share | HJD-T3010 | Taking-over application, SAR review and handover - Jeddah | COM.HJD.TOA | Commissioning and handover | HJD | MS7 | 10% |  |  | 0.3 |  | 286526 |  | MS7 Final acceptance and handover 10% x station price share 15.40% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 444 |  | 2028-07-02 | 2028-07-31 | 22
SH-DES | Design and engineering package (per railway, allocated to the station) | EDM-E1010 | Survey: submittal of site survey and as-found report - Dammam | ENG.EDM.SRV.SUB | Engineering | EDM | MS2 | 10% |  |  | 0.069 |  | 21994 |  | MS2 Engineering submittal 10% x station price share 5.14% ¦ Design stage key 6.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 28 |  | 2027-06-13 | 2027-06-22 | 8
SH-DES | Design and engineering package (per railway, allocated to the station) | EDM-E1020 | Survey: SAR approval of survey report - Dammam | ENG.EDM.SRV.APR | Engineering | EDM | MS3 | 10% |  |  | 0.05 |  | 15938 |  | MS3 SAR approval of engineering 10% x station price share 5.14% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 30 |  | 2027-06-23 | 2027-07-13 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | EDM-E1030 | Concept design: submittal - Dammam | ENG.EDM.CNC.SUB | Engineering | EDM | MS2 | 10% |  |  | 0.098 |  | 31238 |  | MS2 Engineering submittal 10% x station price share 5.14% ¦ Design stage key 9.8% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 23 |  | 2027-06-23 | 2027-07-06 | 10
SH-DES | Design and engineering package (per railway, allocated to the station) | EDM-E1040 | Concept design: SAR review and approval - Dammam | ENG.EDM.CNC.APR | Engineering | EDM | MS3 | 10% |  |  | 0.1 |  | 31875 |  | MS3 SAR approval of engineering 10% x station price share 5.14% ¦ Design stage key 10.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 35 |  | 2027-07-07 | 2027-07-27 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | EDM-E1050 | Preliminary design: submittal - Dammam | ENG.EDM.PRE.SUB | Engineering | EDM | MS2 | 10% |  |  | 0.196 |  | 62475 |  | MS2 Engineering submittal 10% x station price share 5.14% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 54 |  | 2027-07-07 | 2027-07-28 | 16
SH-DES | Design and engineering package (per railway, allocated to the station) | EDM-E1060 | Preliminary design: SAR review and approval - Dammam | ENG.EDM.PRE.APR | Engineering | EDM | MS3 | 10% |  |  | 0.2 |  | 63750 |  | MS3 SAR approval of engineering 10% x station price share 5.14% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 51 |  | 2027-07-29 | 2027-08-18 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | EDM-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Dammam | ENG.EDM.DET.SUB | Engineering | EDM | MS2 | 10% |  |  | 0.392 |  | 124950 |  | MS2 Engineering submittal 10% x station price share 5.14% ¦ Design stage key 39.2% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 110 |  | 2027-07-29 | 2027-09-02 | 26
SH-DES | Design and engineering package (per railway, allocated to the station) | EDM-E1080 | Detailed design: SAR review and approval - Dammam | ENG.EDM.DET.APR | Engineering | EDM | MS3 | 10% |  |  | 0.4 |  | 127500 |  | MS3 SAR approval of engineering 10% x station price share 5.14% ¦ Design stage key 40.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 64 |  | 2027-09-05 | 2027-09-26 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | EDM-E1090 | IFC and shop drawings: submittal - Dammam | ENG.EDM.IFC.SUB | Engineering | EDM | MS2 | 10% |  |  | 0.196 |  | 62475 |  | MS2 Engineering submittal 10% x station price share 5.14% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 46 |  | 2027-09-05 | 2027-09-20 | 12
SH-DES | Design and engineering package (per railway, allocated to the station) | EDM-E1100 | IFC and shop drawings: SAR approval and release - Dammam | ENG.EDM.IFC.APR | Engineering | EDM | MS3 | 10% |  |  | 0.2 |  | 63750 |  | MS3 SAR approval of engineering 10% x station price share 5.14% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 58 |  | 2027-09-21 | 2027-10-12 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | EDM-E1110 | HCIS Stage 3 and 4 documents: preparation - Dammam | ENG.EDM.HCS.SUB | Engineering | EDM | MS2 | 10% |  |  | 0.049 |  | 15619 |  | MS2 Engineering submittal 10% x station price share 5.14% ¦ Design stage key 4.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 23 |  | 2027-08-12 | 2027-09-20 | 28
SH-DES | Design and engineering package (per railway, allocated to the station) | EDM-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Dammam | ENG.EDM.HCS.APR | Engineering | EDM | MS3 | 10% |  |  | 0.05 |  | 15938 |  | MS3 SAR approval of engineering 10% x station price share 5.14% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 12 |  | 2027-09-21 | 2027-10-12 | 15
SH-DES, SH-TRN | Design and engineering package (per railway, allocated to the station) and Training (per railway, allocated): documentation and training share | EDM-E1130 | As-built and O&M documentation: submittal - Dammam | ENG.EDM.ASB.SUB | Engineering | EDM | MS7 | 10% |  |  | 0.15 |  | 47813 |  | MS7 Final acceptance and handover 10% x station price share 5.14% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 37 |  | 2028-03-30 | 2028-05-14 | 27
SH-DES | Design and engineering package (per railway, allocated to the station): documentation share | EDM-E1140 | As-built and O&M documentation: SAR review and approval - Dammam | ENG.EDM.ASB.APR | Engineering | EDM | MS7 | 10% |  |  | 0.05 |  | 15938 |  | MS7 Final acceptance and handover 10% x station price share 5.14% ¦ Fixed key 5% | Annex 3 documentation share | 21 |  | 2028-05-15 | 2028-06-04 | 15
- | No BOQ cost: administrative or review step with no payment milestone | EDM-X1010 | Enabling works: site preparation, setting out, temporary works and utilities clearance - Dammam | CON.EDM.ENA | Construction | EDM | MS5 | 20% |  |  | 0.013808 |  | 8803 |  | MS5 Installation 20% x station price share 5.14% ¦ BOQ civil share 34.5% x 4% (enabling: site preparation) | Annex 3 A6 Civil works (SAR 701,813) | 49 |  | 2027-10-13 | 2027-10-19 | 5
- | No BOQ cost: administrative or review step with no payment milestone | EDM-X1020 | Enabling works: cable routes, duct-bank and cabinet plinth preparation - Dammam | CON.EDM.ENA | Construction | EDM | MS5 | 20% |  |  | 0.020713 |  | 13204 |  | MS5 Installation 20% x station price share 5.14% ¦ BOQ civil share 34.5% x 6% (enabling: routes, ducts, plinths) | Annex 3 A6 Civil works (SAR 701,813) | 74 |  | 2027-10-20 | 2027-11-02 | 10
A1 | A1 CCTV system | EDM-P1010 | Manufacture CCTV cameras and analytics - Dammam | PRO.EDM.CCT | Procurement | EDM | MS4 | 20% |  |  | 0.15598 |  | 99436 |  | MS4 Material delivery 20% x station price share 5.14% ¦ BOQ section share 20.8% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 276,849) | 246 |  | 2027-10-13 | 2027-12-12 | 43
A2 | A2 Video management and video wall | EDM-P1020 | Manufacture video management servers, storage and video wall - Dammam | PRO.EDM.VMS | Procurement | EDM | MS4 | 20% |  |  | 0.23218 |  | 148015 |  | MS4 Material delivery 20% x station price share 5.14% ¦ BOQ section share 31.0% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 412,102) | 367 |  | 2027-10-13 | 2027-12-12 | 43
A3 | A3 Access control and intercom | EDM-P1030 | Manufacture access control and intercom equipment - Dammam | PRO.EDM.ACC | Procurement | EDM | MS4 | 20% |  |  | 0.024838 |  | 15834 |  | MS4 Material delivery 20% x station price share 5.14% ¦ BOQ section share 3.3% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 39 |  | 2027-10-13 | 2027-12-12 | 43
A4, A5 | A4 UPS and A5 Poles, cabinets and network | EDM-P1040 | Manufacture UPS, network switches and field cabinets - Dammam | PRO.EDM.UPN | Procurement | EDM | MS4 | 20% |  |  | 0.337 |  | 214841 |  | MS4 Material delivery 20% x station price share 5.14% ¦ BOQ section share 44.9% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 598,156) | 532 |  | 2027-10-13 | 2027-12-12 | 43
SH-FAT | Factory acceptance test (per railway, allocated) | EDM-P1050 | Factory acceptance test at vendor premises - Dammam | PRO.EDM.LOG | Procurement | EDM | MS4 | 20% |  |  | 0.05 |  | 31875 |  | MS4 Material delivery 20% x station price share 5.14% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 197 |  | 2027-12-13 | 2027-12-26 | 10
A1-A5 | A1 to A5 equipment sections: logistics (shipping, customs, delivery) share | EDM-P1060 | Shipping and customs clearance - Dammam | PRO.EDM.LOG | Procurement | EDM | MS4 | 20% |  |  | 0.15 |  | 95625 |  | MS4 Material delivery 20% x station price share 5.14% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 395 |  | 2027-12-27 | 2028-01-23 | 20
SH-SPR | Commissioning spares (per railway, allocated) | EDM-P1070 | Delivery to station and receiving inspection - Dammam | PRO.EDM.LOG | Procurement | EDM | MS4 | 20% |  |  | 0.05 |  | 31875 |  | MS4 Material delivery 20% x station price share 5.14% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 197 |  | 2028-01-24 | 2028-01-30 | 5
A6 | A6 Civil works | EDM-C1010 | Civil: platform trenches and duct banks - Dammam | CON.EDM.CIV | Construction | EDM | MS5 | 20% |  |  | 0.1726 |  | 110036 |  | MS5 Installation 20% x station price share 5.14% ¦ BOQ civil share 34.5% x 50% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 701,813) | 321 |  | 2027-11-03 | 2028-01-18 | 55
A6 | A6 Civil works | EDM-C1020 | Civil: camera and ALPR pole foundations and poles - Dammam | CON.EDM.CIV | Construction | EDM | MS5 | 20% |  |  | 0.13808 |  | 88029 |  | MS5 Installation 20% x station price share 5.14% ¦ BOQ civil share 34.5% x 40% (poles) | Annex 3 A6 Civil works (SAR 701,813) | 247 |  | 2027-12-22 | 2028-02-27 | 43
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | EDM-C2010 | Install UPS, network switches and field cabinets - Dammam | CON.EDM.INS | Construction | EDM | MS5 | 20% |  |  | 0.13096 |  | 83486 |  | MS5 Installation 20% x station price share 5.14% ¦ Installation key 20% x (1 - civil share 34.5%) | Annex 3 equipment sections A1-A5 (installation share) | 148 |  | 2028-01-31 | 2028-02-14 | 11
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | EDM-C2020 | Cabling and termination (power, fibre, data) - Dammam | CON.EDM.INS | Construction | EDM | MS5 | 20% |  |  | 0.19644 |  | 125229 |  | MS5 Installation 20% x station price share 5.14% ¦ Installation key 30% x (1 - civil share 34.5%) | Annex 3 equipment sections A1-A5 (installation share) | 296 |  | 2028-02-06 | 2028-03-08 | 19
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | EDM-C2030 | Install and aim CCTV cameras - Dammam | CON.EDM.INS | Construction | EDM | MS5 | 20% |  |  | 0.1637 |  | 104358 |  | MS5 Installation 20% x station price share 5.14% ¦ Installation key 25% x (1 - civil share 34.5%) | Annex 3 equipment sections A1-A5 (installation share) | 247 |  | 2028-03-09 | 2028-03-29 | 15
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | EDM-C2040 | Install video management, video wall and control-room equipment - Dammam | CON.EDM.INS | Construction | EDM | MS5 | 20% |  |  | 0.098219 |  | 62615 |  | MS5 Installation 20% x station price share 5.14% ¦ Installation key 15% x (1 - civil share 34.5%) | Annex 3 equipment sections A1-A5 (installation share) | 148 |  | 2028-02-15 | 2028-03-09 | 13
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | EDM-C2050 | Install access control and intercom - Dammam | CON.EDM.INS | Construction | EDM | MS5 | 20% |  |  | 0.065479 |  | 41743 |  | MS5 Installation 20% x station price share 5.14% ¦ Installation key 10% x (1 - civil share 34.5%) | Annex 3 equipment sections A1-A5 (installation share) | 99 |  | 2028-02-28 | 2028-03-13 | 11
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | EDM-T1010 | Pre-commissioning and loop checks - Dammam | COM.EDM.TST | Commissioning and handover | EDM | MS6 | 10% |  |  | 0.4 |  | 127500 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.14% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 148 |  | 2028-03-30 | 2028-04-05 | 5
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | EDM-T1020 | Site acceptance test (SAT) and commissioning - Dammam | COM.EDM.TST | Commissioning and handover | EDM | MS6 | 10% |  |  | 0.6 |  | 191251 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.14% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 197 |  | 2028-04-06 | 2028-04-16 | 7
SH-TRN | Training (per railway, allocated) | EDM-T2010 | Operator and maintenance training - Dammam | COM.EDM.TRN | Commissioning and handover | EDM | MS7 | 10% |  |  | 0.15 |  | 47813 |  | MS7 Final acceptance and handover 10% x station price share 5.14% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 99 |  | 2028-04-17 | 2028-05-07 | 10
A1-A5 | A1 to A5 equipment sections: trial operation share | EDM-T2020 | Trial operation (maximum 45 days) - Dammam | COM.EDM.TOA | Commissioning and handover | EDM | MS7 | 10% |  |  | 0.35 |  | 111563 |  | MS7 Final acceptance and handover 10% x station price share 5.14% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 148 |  | 2028-04-17 | 2028-06-04 | 30
A1-A5 | A1 to A5 equipment sections: handover share | EDM-T3010 | Taking-over application, SAR review and handover - Dammam | COM.EDM.TOA | Commissioning and handover | EDM | MS7 | 10% |  |  | 0.3 |  | 95625 |  | MS7 Final acceptance and handover 10% x station price share 5.14% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 148 |  | 2028-06-05 | 2028-07-04 | 22
SH-DES | Design and engineering package (per railway, allocated to the station) | NQS-E1010 | Survey: submittal of site survey and as-found report - Al Qassim | ENG.NQS.SRV.SUB | Engineering | NQS | MS2 | 10% |  |  | 0.069 |  | 23453 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 6.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 30 |  | 2027-08-04 | 2027-08-15 | 8
SH-DES | Design and engineering package (per railway, allocated to the station) | NQS-E1020 | Survey: SAR approval of survey report - Al Qassim | ENG.NQS.SRV.APR | Engineering | NQS | MS3 | 10% |  |  | 0.05 |  | 16995 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 32 |  | 2027-08-16 | 2027-09-05 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NQS-E1030 | Concept design: submittal - Al Qassim | ENG.NQS.CNC.SUB | Engineering | NQS | MS2 | 10% |  |  | 0.098 |  | 33309 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 9.8% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 23 |  | 2027-08-16 | 2027-08-26 | 9
SH-DES | Design and engineering package (per railway, allocated to the station) | NQS-E1040 | Concept design: SAR review and approval - Al Qassim | ENG.NQS.CNC.APR | Engineering | NQS | MS3 | 10% |  |  | 0.1 |  | 33989 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 10.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 39 |  | 2027-08-29 | 2027-09-16 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NQS-E1050 | Preliminary design: submittal - Al Qassim | ENG.NQS.PRE.SUB | Engineering | NQS | MS2 | 10% |  |  | 0.196 |  | 66619 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 57 |  | 2027-08-29 | 2027-09-19 | 16
SH-DES | Design and engineering package (per railway, allocated to the station) | NQS-E1060 | Preliminary design: SAR review and approval - Al Qassim | ENG.NQS.PRE.APR | Engineering | NQS | MS3 | 10% |  |  | 0.2 |  | 67978 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 54 |  | 2027-09-20 | 2027-10-11 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NQS-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Al Qassim | ENG.NQS.DET.SUB | Engineering | NQS | MS2 | 10% |  |  | 0.392 |  | 133238 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 39.2% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 116 |  | 2027-09-20 | 2027-10-25 | 25
SH-DES | Design and engineering package (per railway, allocated to the station) | NQS-E1080 | Detailed design: SAR review and approval - Al Qassim | ENG.NQS.DET.APR | Engineering | NQS | MS3 | 10% |  |  | 0.4 |  | 135957 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 40.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 70 |  | 2027-10-26 | 2027-11-15 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NQS-E1090 | IFC and shop drawings: submittal - Al Qassim | ENG.NQS.IFC.SUB | Engineering | NQS | MS2 | 10% |  |  | 0.196 |  | 66619 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 52 |  | 2027-10-26 | 2027-11-11 | 13
SH-DES | Design and engineering package (per railway, allocated to the station) | NQS-E1100 | IFC and shop drawings: SAR approval and release - Al Qassim | ENG.NQS.IFC.APR | Engineering | NQS | MS3 | 10% |  |  | 0.2 |  | 67978 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 60 |  | 2027-11-14 | 2027-12-02 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NQS-E1110 | HCIS Stage 3 and 4 documents: preparation - Al Qassim | ENG.NQS.HCS.SUB | Engineering | NQS | MS2 | 10% |  |  | 0.049 |  | 16655 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 4.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 24 |  | 2027-10-04 | 2027-11-11 | 29
SH-DES | Design and engineering package (per railway, allocated to the station) | NQS-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Al Qassim | ENG.NQS.HCS.APR | Engineering | NQS | MS3 | 10% |  |  | 0.05 |  | 16995 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 13 |  | 2027-11-14 | 2027-12-02 | 15
SH-DES, SH-TRN | Design and engineering package (per railway, allocated to the station) and Training (per railway, allocated): documentation and training share | NQS-E1130 | As-built and O&M documentation: submittal - Al Qassim | ENG.NQS.ASB.SUB | Engineering | NQS | MS7 | 10% |  |  | 0.15 |  | 50984 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 40 |  | 2028-06-14 | 2028-07-23 | 28
SH-DES | Design and engineering package (per railway, allocated to the station): documentation share | NQS-E1140 | As-built and O&M documentation: SAR review and approval - Al Qassim | ENG.NQS.ASB.APR | Engineering | NQS | MS7 | 10% |  |  | 0.05 |  | 16995 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 5% | Annex 3 documentation share | 22 |  | 2028-07-24 | 2028-08-13 | 15
- | No BOQ cost: administrative or review step with no payment milestone | NQS-X1010 | Enabling works: site preparation, setting out, temporary works and utilities clearance - Al Qassim | CON.NQS.ENA | Construction | NQS | MS5 | 20% |  |  | 0.012404 |  | 8432 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 4% (enabling: site preparation) | Annex 3 A6 Civil works (SAR 745,743) | 53 |  | 2027-12-05 | 2027-12-09 | 5
- | No BOQ cost: administrative or review step with no payment milestone | NQS-X1020 | Enabling works: cable routes, duct-bank and cabinet plinth preparation - Al Qassim | CON.NQS.ENA | Construction | NQS | MS5 | 20% |  |  | 0.018606 |  | 12648 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 6% (enabling: routes, ducts, plinths) | Annex 3 A6 Civil works (SAR 745,743) | 79 |  | 2027-12-12 | 2027-12-23 | 10
A1 | A1 CCTV system | NQS-P1010 | Manufacture CCTV cameras and analytics - Al Qassim | PRO.NQS.CCT | Procurement | NQS | MS4 | 20% |  |  | 0.15324 |  | 104169 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 20.4% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 338,989) | 258 |  | 2027-12-05 | 2028-02-07 | 47
A2 | A2 Video management and video wall | NQS-P1020 | Manufacture video management servers, storage and video wall - Al Qassim | PRO.NQS.VMS | Procurement | NQS | MS4 | 20% |  |  | 0.16238 |  | 110385 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 21.7% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 359,215) | 273 |  | 2027-12-05 | 2028-02-07 | 47
A3 | A3 Access control and intercom | NQS-P1030 | Manufacture access control and intercom equipment - Al Qassim | PRO.NQS.ACC | Procurement | NQS | MS4 | 20% |  |  | 0.019928 |  | 13547 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 2.7% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 34 |  | 2027-12-05 | 2028-02-07 | 47
A4, A5 | A4 UPS and A5 Poles, cabinets and network | NQS-P1040 | Manufacture UPS, network switches and field cabinets - Al Qassim | PRO.NQS.UPN | Procurement | NQS | MS4 | 20% |  |  | 0.41445 |  | 281736 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 55.3% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 916,830) | 698 |  | 2027-12-05 | 2028-02-07 | 47
SH-FAT | Factory acceptance test (per railway, allocated) | NQS-P1050 | Factory acceptance test at vendor premises - Al Qassim | PRO.NQS.LOG | Procurement | NQS | MS4 | 20% |  |  | 0.05 |  | 33989 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 211 |  | 2028-02-08 | 2028-02-28 | 10
A1-A5 | A1 to A5 equipment sections: logistics (shipping, customs, delivery) share | NQS-P1060 | Shipping and customs clearance - Al Qassim | PRO.NQS.LOG | Procurement | NQS | MS4 | 20% |  |  | 0.15 |  | 101967 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 421 |  | 2028-02-29 | 2028-03-29 | 22
SH-SPR | Commissioning spares (per railway, allocated) | NQS-P1070 | Delivery to station and receiving inspection - Al Qassim | PRO.NQS.LOG | Procurement | NQS | MS4 | 20% |  |  | 0.05 |  | 33989 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 211 |  | 2028-03-30 | 2028-04-05 | 5
A6 | A6 Civil works | NQS-C1010 | Civil: platform trenches and duct banks - Al Qassim | CON.NQS.CIV | Construction | NQS | MS5 | 20% |  |  | 0.15505 |  | 105400 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 50% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 745,743) | 342 |  | 2027-12-26 | 2028-03-20 | 57
A6 | A6 Civil works | NQS-C1020 | Civil: camera and ALPR pole foundations and poles - Al Qassim | CON.NQS.CIV | Construction | NQS | MS5 | 20% |  |  | 0.12404 |  | 84320 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 40% (poles) | Annex 3 A6 Civil works (SAR 745,743) | 263 |  | 2028-02-15 | 2028-04-24 | 45
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NQS-C2010 | Install UPS, network switches and field cabinets - Al Qassim | CON.NQS.INS | Construction | NQS | MS5 | 20% |  |  | 0.13798 |  | 93797 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 20% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 158 |  | 2028-04-06 | 2028-04-24 | 13
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NQS-C2020 | Cabling and termination (power, fibre, data) - Al Qassim | CON.NQS.INS | Construction | NQS | MS5 | 20% |  |  | 0.20697 |  | 140695 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 30% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 316 |  | 2028-04-12 | 2028-05-18 | 22
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NQS-C2030 | Install and aim CCTV cameras - Al Qassim | CON.NQS.INS | Construction | NQS | MS5 | 20% |  |  | 0.17248 |  | 117246 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 25% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 263 |  | 2028-05-21 | 2028-06-13 | 18
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NQS-C2040 | Install video management, video wall and control-room equipment - Al Qassim | CON.NQS.INS | Construction | NQS | MS5 | 20% |  |  | 0.10349 |  | 70348 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 15% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 158 |  | 2028-04-25 | 2028-05-22 | 15
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NQS-C2050 | Install access control and intercom - Al Qassim | CON.NQS.INS | Construction | NQS | MS5 | 20% |  |  | 0.06899 |  | 46898 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 10% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 105 |  | 2028-05-08 | 2028-05-24 | 13
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | NQS-T1010 | Pre-commissioning and loop checks - Al Qassim | COM.NQS.TST | Commissioning and handover | NQS | MS6 | 10% |  |  | 0.4 |  | 135957 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.48% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 158 |  | 2028-06-14 | 2028-06-20 | 5
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | NQS-T1020 | Site acceptance test (SAT) and commissioning - Al Qassim | COM.NQS.TST | Commissioning and handover | NQS | MS6 | 10% |  |  | 0.6 |  | 203935 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.48% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 211 |  | 2028-06-21 | 2028-07-02 | 8
SH-TRN | Training (per railway, allocated) | NQS-T2010 | Operator and maintenance training - Al Qassim | COM.NQS.TRN | Commissioning and handover | NQS | MS7 | 10% |  |  | 0.15 |  | 50984 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 105 |  | 2028-07-03 | 2028-07-16 | 10
A1-A5 | A1 to A5 equipment sections: trial operation share | NQS-T2020 | Trial operation (maximum 45 days) - Al Qassim | COM.NQS.TOA | Commissioning and handover | NQS | MS7 | 10% |  |  | 0.35 |  | 118962 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 158 |  | 2028-07-03 | 2028-08-13 | 30
A1-A5 | A1 to A5 equipment sections: handover share | NQS-T3010 | Taking-over application, SAR review and handover - Al Qassim | COM.NQS.TOA | Commissioning and handover | NQS | MS7 | 10% |  |  | 0.3 |  | 101967 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 158 |  | 2028-08-14 | 2028-09-12 | 22
SH-DES | Design and engineering package (per railway, allocated to the station) | EHF-E1010 | Survey: submittal of site survey and as-found report - Hufuf | ENG.EHF.SRV.SUB | Engineering | EHF | MS2 | 10% |  |  | 0.069 |  | 19517 |  | MS2 Engineering submittal 10% x station price share 4.56% ¦ Design stage key 6.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 25 |  | 2027-08-04 | 2027-08-15 | 8
SH-DES | Design and engineering package (per railway, allocated to the station) | EHF-E1020 | Survey: SAR approval of survey report - Hufuf | ENG.EHF.SRV.APR | Engineering | EHF | MS3 | 10% |  |  | 0.05 |  | 14143 |  | MS3 SAR approval of engineering 10% x station price share 4.56% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 27 |  | 2027-08-16 | 2027-09-05 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | EHF-E1030 | Concept design: submittal - Hufuf | ENG.EHF.CNC.SUB | Engineering | EHF | MS2 | 10% |  |  | 0.098 |  | 27719 |  | MS2 Engineering submittal 10% x station price share 4.56% ¦ Design stage key 9.8% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 19 |  | 2027-08-16 | 2027-08-26 | 9
SH-DES | Design and engineering package (per railway, allocated to the station) | EHF-E1040 | Concept design: SAR review and approval - Hufuf | ENG.EHF.CNC.APR | Engineering | EHF | MS3 | 10% |  |  | 0.1 |  | 28285 |  | MS3 SAR approval of engineering 10% x station price share 4.56% ¦ Design stage key 10.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 32 |  | 2027-08-29 | 2027-09-16 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | EHF-E1050 | Preliminary design: submittal - Hufuf | ENG.EHF.PRE.SUB | Engineering | EHF | MS2 | 10% |  |  | 0.196 |  | 55439 |  | MS2 Engineering submittal 10% x station price share 4.56% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 48 |  | 2027-08-29 | 2027-09-19 | 16
SH-DES | Design and engineering package (per railway, allocated to the station) | EHF-E1060 | Preliminary design: SAR review and approval - Hufuf | ENG.EHF.PRE.APR | Engineering | EHF | MS3 | 10% |  |  | 0.2 |  | 56570 |  | MS3 SAR approval of engineering 10% x station price share 4.56% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 45 |  | 2027-09-20 | 2027-10-11 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | EHF-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Hufuf | ENG.EHF.DET.SUB | Engineering | EHF | MS2 | 10% |  |  | 0.392 |  | 110877 |  | MS2 Engineering submittal 10% x station price share 4.56% ¦ Design stage key 39.2% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 97 |  | 2027-09-20 | 2027-10-25 | 25
SH-DES | Design and engineering package (per railway, allocated to the station) | EHF-E1080 | Detailed design: SAR review and approval - Hufuf | ENG.EHF.DET.APR | Engineering | EHF | MS3 | 10% |  |  | 0.4 |  | 113140 |  | MS3 SAR approval of engineering 10% x station price share 4.56% ¦ Design stage key 40.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 58 |  | 2027-10-26 | 2027-11-15 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | EHF-E1090 | IFC and shop drawings: submittal - Hufuf | ENG.EHF.IFC.SUB | Engineering | EHF | MS2 | 10% |  |  | 0.196 |  | 55439 |  | MS2 Engineering submittal 10% x station price share 4.56% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 43 |  | 2027-10-26 | 2027-11-11 | 13
SH-DES | Design and engineering package (per railway, allocated to the station) | EHF-E1100 | IFC and shop drawings: SAR approval and release - Hufuf | ENG.EHF.IFC.APR | Engineering | EHF | MS3 | 10% |  |  | 0.2 |  | 56570 |  | MS3 SAR approval of engineering 10% x station price share 4.56% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 50 |  | 2027-11-14 | 2027-12-02 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | EHF-E1110 | HCIS Stage 3 and 4 documents: preparation - Hufuf | ENG.EHF.HCS.SUB | Engineering | EHF | MS2 | 10% |  |  | 0.049 |  | 13860 |  | MS2 Engineering submittal 10% x station price share 4.56% ¦ Design stage key 4.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 20 |  | 2027-10-04 | 2027-11-11 | 29
SH-DES | Design and engineering package (per railway, allocated to the station) | EHF-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Hufuf | ENG.EHF.HCS.APR | Engineering | EHF | MS3 | 10% |  |  | 0.05 |  | 14143 |  | MS3 SAR approval of engineering 10% x station price share 4.56% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 11 |  | 2027-11-14 | 2027-12-02 | 15
SH-DES, SH-TRN | Design and engineering package (per railway, allocated to the station) and Training (per railway, allocated): documentation and training share | EHF-E1130 | As-built and O&M documentation: submittal - Hufuf | ENG.EHF.ASB.SUB | Engineering | EHF | MS7 | 10% |  |  | 0.15 |  | 42428 |  | MS7 Final acceptance and handover 10% x station price share 4.56% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 33 |  | 2028-05-23 | 2028-06-28 | 27
SH-DES | Design and engineering package (per railway, allocated to the station): documentation share | EHF-E1140 | As-built and O&M documentation: SAR review and approval - Hufuf | ENG.EHF.ASB.APR | Engineering | EHF | MS7 | 10% |  |  | 0.05 |  | 14143 |  | MS7 Final acceptance and handover 10% x station price share 4.56% ¦ Fixed key 5% | Annex 3 documentation share | 18 |  | 2028-06-29 | 2028-07-19 | 15
- | No BOQ cost: administrative or review step with no payment milestone | EHF-X1010 | Enabling works: site preparation, setting out, temporary works and utilities clearance - Hufuf | CON.EHF.ENA | Construction | EHF | MS5 | 20% |  |  | 0.014631 |  | 8277 |  | MS5 Installation 20% x station price share 4.56% ¦ BOQ civil share 36.6% x 4% (enabling: site preparation) | Annex 3 A6 Civil works (SAR 659,866) | 44 |  | 2027-12-05 | 2027-12-09 | 5
- | No BOQ cost: administrative or review step with no payment milestone | EHF-X1020 | Enabling works: cable routes, duct-bank and cabinet plinth preparation - Hufuf | CON.EHF.ENA | Construction | EHF | MS5 | 20% |  |  | 0.021946 |  | 12415 |  | MS5 Installation 20% x station price share 4.56% ¦ BOQ civil share 36.6% x 6% (enabling: routes, ducts, plinths) | Annex 3 A6 Civil works (SAR 659,866) | 66 |  | 2027-12-12 | 2027-12-23 | 10
A1 | A1 CCTV system | EHF-P1010 | Manufacture CCTV cameras and analytics - Hufuf | PRO.EHF.CCT | Procurement | EHF | MS4 | 20% |  |  | 0.12596 |  | 71254 |  | MS4 Material delivery 20% x station price share 4.56% ¦ BOQ section share 16.8% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 192,155) | 177 |  | 2027-12-05 | 2028-01-30 | 41
A2 | A2 Video management and video wall | EHF-P1020 | Manufacture video management servers, storage and video wall - Hufuf | PRO.EHF.VMS | Procurement | EHF | MS4 | 20% |  |  | 0.22879 |  | 129428 |  | MS4 Material delivery 20% x station price share 4.56% ¦ BOQ section share 30.5% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 349,033) | 321 |  | 2027-12-05 | 2028-01-30 | 41
A3 | A3 Access control and intercom | EHF-P1030 | Manufacture access control and intercom equipment - Hufuf | PRO.EHF.ACC | Procurement | EHF | MS4 | 20% |  |  | 0.028898 |  | 16348 |  | MS4 Material delivery 20% x station price share 4.56% ¦ BOQ section share 3.9% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 40 |  | 2027-12-05 | 2028-01-30 | 41
A4, A5 | A4 UPS and A5 Poles, cabinets and network | EHF-P1040 | Manufacture UPS, network switches and field cabinets - Hufuf | PRO.EHF.UPN | Procurement | EHF | MS4 | 20% |  |  | 0.36635 |  | 207246 |  | MS4 Material delivery 20% x station price share 4.56% ¦ BOQ section share 48.8% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 558,888) | 513 |  | 2027-12-05 | 2028-01-30 | 41
SH-FAT | Factory acceptance test (per railway, allocated) | EHF-P1050 | Factory acceptance test at vendor premises - Hufuf | PRO.EHF.LOG | Procurement | EHF | MS4 | 20% |  |  | 0.05 |  | 28285 |  | MS4 Material delivery 20% x station price share 4.56% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 175 |  | 2028-01-31 | 2028-02-13 | 10
A1-A5 | A1 to A5 equipment sections: logistics (shipping, customs, delivery) share | EHF-P1060 | Shipping and customs clearance - Hufuf | PRO.EHF.LOG | Procurement | EHF | MS4 | 20% |  |  | 0.15 |  | 84855 |  | MS4 Material delivery 20% x station price share 4.56% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 350 |  | 2028-02-14 | 2028-03-19 | 20
SH-SPR | Commissioning spares (per railway, allocated) | EHF-P1070 | Delivery to station and receiving inspection - Hufuf | PRO.EHF.LOG | Procurement | EHF | MS4 | 20% |  |  | 0.05 |  | 28285 |  | MS4 Material delivery 20% x station price share 4.56% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 175 |  | 2028-03-20 | 2028-03-26 | 5
A6 | A6 Civil works | EHF-C1010 | Civil: platform trenches and duct banks - Hufuf | CON.EHF.CIV | Construction | EHF | MS5 | 20% |  |  | 0.18289 |  | 103459 |  | MS5 Installation 20% x station price share 4.56% ¦ BOQ civil share 36.6% x 50% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 659,866) | 285 |  | 2027-12-26 | 2028-03-14 | 53
A6 | A6 Civil works | EHF-C1020 | Civil: camera and ALPR pole foundations and poles - Hufuf | CON.EHF.CIV | Construction | EHF | MS5 | 20% |  |  | 0.14631 |  | 82767 |  | MS5 Installation 20% x station price share 4.56% ¦ BOQ civil share 36.6% x 40% (poles) | Annex 3 A6 Civil works (SAR 659,866) | 219 |  | 2028-02-10 | 2028-04-13 | 41
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | EHF-C2010 | Install UPS, network switches and field cabinets - Hufuf | CON.EHF.INS | Construction | EHF | MS5 | 20% |  |  | 0.12685 |  | 71756 |  | MS5 Installation 20% x station price share 4.56% ¦ Installation key 20% x (1 - civil share 36.6%) | Annex 3 equipment sections A1-A5 (installation share) | 131 |  | 2028-03-27 | 2028-04-10 | 11
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | EHF-C2020 | Cabling and termination (power, fibre, data) - Hufuf | CON.EHF.INS | Construction | EHF | MS5 | 20% |  |  | 0.19027 |  | 107635 |  | MS5 Installation 20% x station price share 4.56% ¦ Installation key 30% x (1 - civil share 36.6%) | Annex 3 equipment sections A1-A5 (installation share) | 263 |  | 2028-04-02 | 2028-04-25 | 18
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | EHF-C2030 | Install and aim CCTV cameras - Hufuf | CON.EHF.INS | Construction | EHF | MS5 | 20% |  |  | 0.15856 |  | 89695 |  | MS5 Installation 20% x station price share 4.56% ¦ Installation key 25% x (1 - civil share 36.6%) | Annex 3 equipment sections A1-A5 (installation share) | 219 |  | 2028-04-26 | 2028-05-22 | 14
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | EHF-C2040 | Install video management, video wall and control-room equipment - Hufuf | CON.EHF.INS | Construction | EHF | MS5 | 20% |  |  | 0.095134 |  | 53817 |  | MS5 Installation 20% x station price share 4.56% ¦ Installation key 15% x (1 - civil share 36.6%) | Annex 3 equipment sections A1-A5 (installation share) | 131 |  | 2028-04-11 | 2028-04-26 | 12
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | EHF-C2050 | Install access control and intercom - Hufuf | CON.EHF.INS | Construction | EHF | MS5 | 20% |  |  | 0.063423 |  | 35878 |  | MS5 Installation 20% x station price share 4.56% ¦ Installation key 10% x (1 - civil share 36.6%) | Annex 3 equipment sections A1-A5 (installation share) | 88 |  | 2028-04-17 | 2028-05-08 | 11
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | EHF-T1010 | Pre-commissioning and loop checks - Hufuf | COM.EHF.TST | Commissioning and handover | EHF | MS6 | 10% |  |  | 0.4 |  | 113140 |  | MS6 Testing and commissioning (SAT) 10% x station price share 4.56% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 131 |  | 2028-05-23 | 2028-05-29 | 5
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | EHF-T1020 | Site acceptance test (SAT) and commissioning - Hufuf | COM.EHF.TST | Commissioning and handover | EHF | MS6 | 10% |  |  | 0.6 |  | 169710 |  | MS6 Testing and commissioning (SAT) 10% x station price share 4.56% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 175 |  | 2028-05-30 | 2028-06-07 | 7
SH-TRN | Training (per railway, allocated) | EHF-T2010 | Operator and maintenance training - Hufuf | COM.EHF.TRN | Commissioning and handover | EHF | MS7 | 10% |  |  | 0.15 |  | 42428 |  | MS7 Final acceptance and handover 10% x station price share 4.56% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 88 |  | 2028-06-08 | 2028-06-21 | 10
A1-A5 | A1 to A5 equipment sections: trial operation share | EHF-T2020 | Trial operation (maximum 45 days) - Hufuf | COM.EHF.TOA | Commissioning and handover | EHF | MS7 | 10% |  |  | 0.35 |  | 98998 |  | MS7 Final acceptance and handover 10% x station price share 4.56% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 131 |  | 2028-06-08 | 2028-07-19 | 30
A1-A5 | A1 to A5 equipment sections: handover share | EHF-T3010 | Taking-over application, SAR review and handover - Hufuf | COM.EHF.TOA | Commissioning and handover | EHF | MS7 | 10% |  |  | 0.3 |  | 84855 |  | MS7 Final acceptance and handover 10% x station price share 4.56% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 131 |  | 2028-07-20 | 2028-08-20 | 22
SH-DES | Design and engineering package (per railway, allocated to the station) | NMJ-E1010 | Survey: submittal of site survey and as-found report - Al Majma'ah | ENG.NMJ.SRV.SUB | Engineering | NMJ | MS2 | 10% |  |  | 0.069 |  | 23453 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 6.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 30 |  | 2027-09-20 | 2027-09-30 | 8
SH-DES | Design and engineering package (per railway, allocated to the station) | NMJ-E1020 | Survey: SAR approval of survey report - Al Majma'ah | ENG.NMJ.SRV.APR | Engineering | NMJ | MS3 | 10% |  |  | 0.05 |  | 16995 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 32 |  | 2027-10-03 | 2027-10-21 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NMJ-E1030 | Concept design: submittal - Al Majma'ah | ENG.NMJ.CNC.SUB | Engineering | NMJ | MS2 | 10% |  |  | 0.098 |  | 33309 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 9.8% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 25 |  | 2027-10-03 | 2027-10-14 | 10
SH-DES | Design and engineering package (per railway, allocated to the station) | NMJ-E1040 | Concept design: SAR review and approval - Al Majma'ah | ENG.NMJ.CNC.APR | Engineering | NMJ | MS3 | 10% |  |  | 0.1 |  | 33989 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 10.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 37 |  | 2027-10-17 | 2027-11-04 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NMJ-E1050 | Preliminary design: submittal - Al Majma'ah | ENG.NMJ.PRE.SUB | Engineering | NMJ | MS2 | 10% |  |  | 0.196 |  | 66619 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 57 |  | 2027-10-17 | 2027-11-07 | 16
SH-DES | Design and engineering package (per railway, allocated to the station) | NMJ-E1060 | Preliminary design: SAR review and approval - Al Majma'ah | ENG.NMJ.PRE.APR | Engineering | NMJ | MS3 | 10% |  |  | 0.2 |  | 67978 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 54 |  | 2027-11-08 | 2027-11-28 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NMJ-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Al Majma'ah | ENG.NMJ.DET.SUB | Engineering | NMJ | MS2 | 10% |  |  | 0.392 |  | 133238 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 39.2% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 118 |  | 2027-11-08 | 2027-12-13 | 26
SH-DES | Design and engineering package (per railway, allocated to the station) | NMJ-E1080 | Detailed design: SAR review and approval - Al Majma'ah | ENG.NMJ.DET.APR | Engineering | NMJ | MS3 | 10% |  |  | 0.4 |  | 135957 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 40.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 68 |  | 2027-12-14 | 2028-01-03 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NMJ-E1090 | IFC and shop drawings: submittal - Al Majma'ah | ENG.NMJ.IFC.SUB | Engineering | NMJ | MS2 | 10% |  |  | 0.196 |  | 66619 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 50 |  | 2027-12-14 | 2027-12-29 | 12
SH-DES | Design and engineering package (per railway, allocated to the station) | NMJ-E1100 | IFC and shop drawings: SAR approval and release - Al Majma'ah | ENG.NMJ.IFC.APR | Engineering | NMJ | MS3 | 10% |  |  | 0.2 |  | 67978 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 62 |  | 2027-12-30 | 2028-01-19 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NMJ-E1110 | HCIS Stage 3 and 4 documents: preparation - Al Majma'ah | ENG.NMJ.HCS.SUB | Engineering | NMJ | MS2 | 10% |  |  | 0.049 |  | 16655 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 4.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 24 |  | 2027-11-22 | 2027-12-29 | 28
SH-DES | Design and engineering package (per railway, allocated to the station) | NMJ-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Al Majma'ah | ENG.NMJ.HCS.APR | Engineering | NMJ | MS3 | 10% |  |  | 0.05 |  | 16995 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 13 |  | 2027-12-30 | 2028-01-19 | 15
SH-DES, SH-TRN | Design and engineering package (per railway, allocated to the station) and Training (per railway, allocated): documentation and training share | NMJ-E1130 | As-built and O&M documentation: submittal - Al Majma'ah | ENG.NMJ.ASB.SUB | Engineering | NMJ | MS7 | 10% |  |  | 0.15 |  | 50984 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 40 |  | 2028-08-01 | 2028-09-07 | 28
SH-DES | Design and engineering package (per railway, allocated to the station): documentation share | NMJ-E1140 | As-built and O&M documentation: SAR review and approval - Al Majma'ah | ENG.NMJ.ASB.APR | Engineering | NMJ | MS7 | 10% |  |  | 0.05 |  | 16995 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 5% | Annex 3 documentation share | 22 |  | 2028-09-10 | 2028-09-28 | 15
- | No BOQ cost: administrative or review step with no payment milestone | NMJ-X1010 | Enabling works: site preparation, setting out, temporary works and utilities clearance - Al Majma'ah | CON.NMJ.ENA | Construction | NMJ | MS5 | 20% |  |  | 0.012404 |  | 8432 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 4% (enabling: site preparation) | Annex 3 A6 Civil works (SAR 745,743) | 53 |  | 2028-01-20 | 2028-01-26 | 5
- | No BOQ cost: administrative or review step with no payment milestone | NMJ-X1020 | Enabling works: cable routes, duct-bank and cabinet plinth preparation - Al Majma'ah | CON.NMJ.ENA | Construction | NMJ | MS5 | 20% |  |  | 0.018606 |  | 12648 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 6% (enabling: routes, ducts, plinths) | Annex 3 A6 Civil works (SAR 745,743) | 79 |  | 2028-01-27 | 2028-02-09 | 10
A1 | A1 CCTV system | NMJ-P1010 | Manufacture CCTV cameras and analytics - Al Majma'ah | PRO.NMJ.CCT | Procurement | NMJ | MS4 | 20% |  |  | 0.15324 |  | 104169 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 20.4% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 338,989) | 258 |  | 2028-01-20 | 2028-04-02 | 47
A2 | A2 Video management and video wall | NMJ-P1020 | Manufacture video management servers, storage and video wall - Al Majma'ah | PRO.NMJ.VMS | Procurement | NMJ | MS4 | 20% |  |  | 0.16238 |  | 110385 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 21.7% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 359,215) | 273 |  | 2028-01-20 | 2028-04-02 | 47
A3 | A3 Access control and intercom | NMJ-P1030 | Manufacture access control and intercom equipment - Al Majma'ah | PRO.NMJ.ACC | Procurement | NMJ | MS4 | 20% |  |  | 0.019928 |  | 13547 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 2.7% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 34 |  | 2028-01-20 | 2028-04-02 | 47
A4, A5 | A4 UPS and A5 Poles, cabinets and network | NMJ-P1040 | Manufacture UPS, network switches and field cabinets - Al Majma'ah | PRO.NMJ.UPN | Procurement | NMJ | MS4 | 20% |  |  | 0.41445 |  | 281736 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 55.3% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 916,830) | 698 |  | 2028-01-20 | 2028-04-02 | 47
SH-FAT | Factory acceptance test (per railway, allocated) | NMJ-P1050 | Factory acceptance test at vendor premises - Al Majma'ah | PRO.NMJ.LOG | Procurement | NMJ | MS4 | 20% |  |  | 0.05 |  | 33989 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 211 |  | 2028-04-03 | 2028-04-16 | 10
A1-A5 | A1 to A5 equipment sections: logistics (shipping, customs, delivery) share | NMJ-P1060 | Shipping and customs clearance - Al Majma'ah | PRO.NMJ.LOG | Procurement | NMJ | MS4 | 20% |  |  | 0.15 |  | 101967 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 421 |  | 2028-04-17 | 2028-05-23 | 22
SH-SPR | Commissioning spares (per railway, allocated) | NMJ-P1070 | Delivery to station and receiving inspection - Al Majma'ah | PRO.NMJ.LOG | Procurement | NMJ | MS4 | 20% |  |  | 0.05 |  | 33989 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 211 |  | 2028-05-24 | 2028-05-30 | 5
A6 | A6 Civil works | NMJ-C1010 | Civil: platform trenches and duct banks - Al Majma'ah | CON.NMJ.CIV | Construction | NMJ | MS5 | 20% |  |  | 0.15505 |  | 105400 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 50% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 745,743) | 342 |  | 2028-02-10 | 2028-05-14 | 57
A6 | A6 Civil works | NMJ-C1020 | Civil: camera and ALPR pole foundations and poles - Al Majma'ah | CON.NMJ.CIV | Construction | NMJ | MS5 | 20% |  |  | 0.12404 |  | 84320 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 40% (poles) | Annex 3 A6 Civil works (SAR 745,743) | 263 |  | 2028-04-10 | 2028-06-18 | 45
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NMJ-C2010 | Install UPS, network switches and field cabinets - Al Majma'ah | CON.NMJ.INS | Construction | NMJ | MS5 | 20% |  |  | 0.13798 |  | 93797 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 20% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 158 |  | 2028-05-31 | 2028-06-18 | 13
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NMJ-C2020 | Cabling and termination (power, fibre, data) - Al Majma'ah | CON.NMJ.INS | Construction | NMJ | MS5 | 20% |  |  | 0.20697 |  | 140695 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 30% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 316 |  | 2028-06-06 | 2028-07-05 | 22
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NMJ-C2030 | Install and aim CCTV cameras - Al Majma'ah | CON.NMJ.INS | Construction | NMJ | MS5 | 20% |  |  | 0.17248 |  | 117246 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 25% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 263 |  | 2028-07-06 | 2028-07-31 | 18
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NMJ-C2040 | Install video management, video wall and control-room equipment - Al Majma'ah | CON.NMJ.INS | Construction | NMJ | MS5 | 20% |  |  | 0.10349 |  | 70348 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 15% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 158 |  | 2028-06-19 | 2028-07-09 | 15
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NMJ-C2050 | Install access control and intercom - Al Majma'ah | CON.NMJ.INS | Construction | NMJ | MS5 | 20% |  |  | 0.06899 |  | 46898 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 10% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 105 |  | 2028-06-25 | 2028-07-11 | 13
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | NMJ-T1010 | Pre-commissioning and loop checks - Al Majma'ah | COM.NMJ.TST | Commissioning and handover | NMJ | MS6 | 10% |  |  | 0.4 |  | 135957 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.48% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 158 |  | 2028-08-01 | 2028-08-07 | 5
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | NMJ-T1020 | Site acceptance test (SAT) and commissioning - Al Majma'ah | COM.NMJ.TST | Commissioning and handover | NMJ | MS6 | 10% |  |  | 0.6 |  | 203935 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.48% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 211 |  | 2028-08-08 | 2028-08-17 | 8
SH-TRN | Training (per railway, allocated) | NMJ-T2010 | Operator and maintenance training - Al Majma'ah | COM.NMJ.TRN | Commissioning and handover | NMJ | MS7 | 10% |  |  | 0.15 |  | 50984 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 105 |  | 2028-08-20 | 2028-08-31 | 10
A1-A5 | A1 to A5 equipment sections: trial operation share | NMJ-T2020 | Trial operation (maximum 45 days) - Al Majma'ah | COM.NMJ.TOA | Commissioning and handover | NMJ | MS7 | 10% |  |  | 0.35 |  | 118962 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 158 |  | 2028-08-20 | 2028-09-28 | 30
A1-A5 | A1 to A5 equipment sections: handover share | NMJ-T3010 | Taking-over application, SAR review and handover - Al Majma'ah | COM.NMJ.TOA | Commissioning and handover | NMJ | MS7 | 10% |  |  | 0.3 |  | 101967 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 158 |  | 2028-10-01 | 2028-10-30 | 22
SH-DES | Design and engineering package (per railway, allocated to the station) | HKA-E1010 | Survey: submittal of site survey and as-found report - KAEC | ENG.HKA.SRV.SUB | Engineering | HKA | MS2 | 10% |  |  | 0.069 |  | 38394 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 6.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 61 |  | 2028-01-16 | 2028-02-03 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HKA-E1020 | Survey: SAR approval of survey report - KAEC | ENG.HKA.SRV.APR | Engineering | HKA | MS3 | 10% |  |  | 0.05 |  | 27822 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 41 |  | 2028-02-06 | 2028-03-02 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HKA-E1030 | Concept design: submittal - KAEC | ENG.HKA.CNC.SUB | Engineering | HKA | MS2 | 10% |  |  | 0.098 |  | 54531 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 9.8% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 32 |  | 2028-02-06 | 2028-02-14 | 7
SH-DES | Design and engineering package (per railway, allocated to the station) | HKA-E1040 | Concept design: SAR review and approval - KAEC | ENG.HKA.CNC.APR | Engineering | HKA | MS3 | 10% |  |  | 0.1 |  | 55644 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 10.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 69 |  | 2028-02-15 | 2028-03-13 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HKA-E1050 | Preliminary design: submittal - KAEC | ENG.HKA.PRE.SUB | Engineering | HKA | MS2 | 10% |  |  | 0.196 |  | 109062 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 81 |  | 2028-02-15 | 2028-03-08 | 12
SH-DES | Design and engineering package (per railway, allocated to the station) | HKA-E1060 | Preliminary design: SAR review and approval - KAEC | ENG.HKA.PRE.APR | Engineering | HKA | MS3 | 10% |  |  | 0.2 |  | 111288 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 101 |  | 2028-03-09 | 2028-03-29 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HKA-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - KAEC | ENG.HKA.DET.SUB | Engineering | HKA | MS2 | 10% |  |  | 0.392 |  | 218124 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 39.2% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 170 |  | 2028-03-09 | 2028-04-04 | 19
SH-DES | Design and engineering package (per railway, allocated to the station) | HKA-E1080 | Detailed design: SAR review and approval - KAEC | ENG.HKA.DET.APR | Engineering | HKA | MS3 | 10% |  |  | 0.4 |  | 222575 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 40.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 134 |  | 2028-04-05 | 2028-04-25 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HKA-E1090 | IFC and shop drawings: submittal - KAEC | ENG.HKA.IFC.SUB | Engineering | HKA | MS2 | 10% |  |  | 0.196 |  | 109062 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 68 |  | 2028-04-05 | 2028-04-17 | 9
SH-DES | Design and engineering package (per railway, allocated to the station) | HKA-E1100 | IFC and shop drawings: SAR approval and release - KAEC | ENG.HKA.IFC.APR | Engineering | HKA | MS3 | 10% |  |  | 0.2 |  | 111288 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 114 |  | 2028-04-18 | 2028-05-15 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HKA-E1110 | HCIS Stage 3 and 4 documents: preparation - KAEC | ENG.HKA.HCS.SUB | Engineering | HKA | MS2 | 10% |  |  | 0.049 |  | 27265 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 4.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 35 |  | 2028-03-20 | 2028-04-17 | 21
SH-DES | Design and engineering package (per railway, allocated to the station) | HKA-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - KAEC | ENG.HKA.HCS.APR | Engineering | HKA | MS3 | 10% |  |  | 0.05 |  | 27822 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 25 |  | 2028-04-18 | 2028-05-15 | 15
SH-DES, SH-TRN | Design and engineering package (per railway, allocated to the station) and Training (per railway, allocated): documentation and training share | HKA-E1130 | As-built and O&M documentation: submittal - KAEC | ENG.HKA.ASB.SUB | Engineering | HKA | MS7 | 10% |  |  | 0.15 |  | 83466 |  | MS7 Final acceptance and handover 10% x station price share 8.97% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 71 |  | 2029-01-09 | 2029-03-06 | 35
SH-DES | Design and engineering package (per railway, allocated to the station): documentation share | HKA-E1140 | As-built and O&M documentation: SAR review and approval - KAEC | ENG.HKA.ASB.APR | Engineering | HKA | MS7 | 10% |  |  | 0.05 |  | 27822 |  | MS7 Final acceptance and handover 10% x station price share 8.97% ¦ Fixed key 5% | Annex 3 documentation share | 30 |  | 2029-03-07 | 2029-03-27 | 15
- | No BOQ cost: administrative or review step with no payment milestone | HKA-X1010 | Enabling works: site preparation, setting out, temporary works and utilities clearance - KAEC | CON.HKA.ENA | Construction | HKA | MS5 | 20% |  |  | 0.0023131 |  | 2574 |  | MS5 Installation 20% x station price share 8.97% ¦ BOQ civil share 5.8% x 4% (enabling: site preparation) | Annex 3 A6 Civil works (SAR 187,054) | 86 |  | 2028-05-16 | 2028-05-22 | 5
- | No BOQ cost: administrative or review step with no payment milestone | HKA-X1020 | Enabling works: cable routes, duct-bank and cabinet plinth preparation - KAEC | CON.HKA.ENA | Construction | HKA | MS5 | 20% |  |  | 0.0034697 |  | 3861 |  | MS5 Installation 20% x station price share 8.97% ¦ BOQ civil share 5.8% x 6% (enabling: routes, ducts, plinths) | Annex 3 A6 Civil works (SAR 187,054) | 129 |  | 2028-05-23 | 2028-06-05 | 10
A1 | A1 CCTV system | HKA-P1010 | Manufacture CCTV cameras and analytics - KAEC | PRO.HKA.CCT | Procurement | HKA | MS4 | 20% |  |  | 0.23675 |  | 263474 |  | MS4 Material delivery 20% x station price share 8.97% ¦ BOQ section share 31.6% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 962,039) | 653 |  | 2028-05-16 | 2028-08-07 | 60
A2 | A2 Video management and video wall | HKA-P1020 | Manufacture video management servers, storage and video wall - KAEC | PRO.HKA.VMS | Procurement | HKA | MS4 | 20% |  |  | 0.1 |  | 111291 |  | MS4 Material delivery 20% x station price share 8.97% ¦ BOQ section share 13.3% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 406,364) | 276 |  | 2028-05-16 | 2028-08-07 | 60
A3 | A3 Access control and intercom | HKA-P1030 | Manufacture access control and intercom equipment - KAEC | PRO.HKA.ACC | Procurement | HKA | MS4 | 20% |  |  | 0.010849 |  | 12074 |  | MS4 Material delivery 20% x station price share 8.97% ¦ BOQ section share 1.4% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 30 |  | 2028-05-16 | 2028-08-07 | 60
A4, A5 | A4 UPS and A5 Poles, cabinets and network | HKA-P1040 | Manufacture UPS, network switches and field cabinets - KAEC | PRO.HKA.UPN | Procurement | HKA | MS4 | 20% |  |  | 0.4024 |  | 447818 |  | MS4 Material delivery 20% x station price share 8.97% ¦ BOQ section share 53.7% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 1,635,145) | 1110 |  | 2028-05-16 | 2028-08-07 | 60
SH-FAT | Factory acceptance test (per railway, allocated) | HKA-P1050 | Factory acceptance test at vendor premises - KAEC | PRO.HKA.LOG | Procurement | HKA | MS4 | 20% |  |  | 0.05 |  | 55644 |  | MS4 Material delivery 20% x station price share 8.97% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 345 |  | 2028-08-08 | 2028-08-21 | 10
A1-A5 | A1 to A5 equipment sections: logistics (shipping, customs, delivery) share | HKA-P1060 | Shipping and customs clearance - KAEC | PRO.HKA.LOG | Procurement | HKA | MS4 | 20% |  |  | 0.15 |  | 166931 |  | MS4 Material delivery 20% x station price share 8.97% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 689 |  | 2028-08-22 | 2028-09-27 | 27
SH-SPR | Commissioning spares (per railway, allocated) | HKA-P1070 | Delivery to station and receiving inspection - KAEC | PRO.HKA.LOG | Procurement | HKA | MS4 | 20% |  |  | 0.05 |  | 55644 |  | MS4 Material delivery 20% x station price share 8.97% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 345 |  | 2028-09-28 | 2028-10-04 | 5
A6 | A6 Civil works | HKA-C1010 | Civil: platform trenches and duct banks - KAEC | CON.HKA.CIV | Construction | HKA | MS5 | 20% |  |  | 0.028914 |  | 32177 |  | MS5 Installation 20% x station price share 8.97% ¦ BOQ civil share 5.8% x 50% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 187,054) | 560 |  | 2028-06-06 | 2028-07-10 | 25
A6 | A6 Civil works | HKA-C1020 | Civil: camera and ALPR pole foundations and poles - KAEC | CON.HKA.CIV | Construction | HKA | MS5 | 20% |  |  | 0.023131 |  | 25742 |  | MS5 Installation 20% x station price share 8.97% ¦ BOQ civil share 5.8% x 40% (poles) | Annex 3 A6 Civil works (SAR 187,054) | 431 |  | 2028-06-28 | 2028-07-25 | 20
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | HKA-C2010 | Install UPS, network switches and field cabinets - KAEC | CON.HKA.INS | Construction | HKA | MS5 | 20% |  |  | 0.18843 |  | 209704 |  | MS5 Installation 20% x station price share 8.97% ¦ Installation key 20% x (1 - civil share 5.8%) | Annex 3 equipment sections A1-A5 (installation share) | 258 |  | 2028-10-05 | 2028-11-01 | 20
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | HKA-C2020 | Cabling and termination (power, fibre, data) - KAEC | CON.HKA.INS | Construction | HKA | MS5 | 20% |  |  | 0.28265 |  | 314556 |  | MS5 Installation 20% x station price share 8.97% ¦ Installation key 30% x (1 - civil share 5.8%) | Annex 3 equipment sections A1-A5 (installation share) | 517 |  | 2028-10-16 | 2028-11-30 | 34
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | HKA-C2030 | Install and aim CCTV cameras - KAEC | CON.HKA.INS | Construction | HKA | MS5 | 20% |  |  | 0.23554 |  | 262130 |  | MS5 Installation 20% x station price share 8.97% ¦ Installation key 25% x (1 - civil share 5.8%) | Annex 3 equipment sections A1-A5 (installation share) | 431 |  | 2028-12-03 | 2029-01-08 | 27
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | HKA-C2040 | Install video management, video wall and control-room equipment - KAEC | CON.HKA.INS | Construction | HKA | MS5 | 20% |  |  | 0.14133 |  | 157278 |  | MS5 Installation 20% x station price share 8.97% ¦ Installation key 15% x (1 - civil share 5.8%) | Annex 3 equipment sections A1-A5 (installation share) | 258 |  | 2028-11-02 | 2028-12-04 | 23
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | HKA-C2050 | Install access control and intercom - KAEC | CON.HKA.INS | Construction | HKA | MS5 | 20% |  |  | 0.094217 |  | 104852 |  | MS5 Installation 20% x station price share 8.97% ¦ Installation key 10% x (1 - civil share 5.8%) | Annex 3 equipment sections A1-A5 (installation share) | 172 |  | 2028-11-13 | 2028-12-10 | 20
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | HKA-T1010 | Pre-commissioning and loop checks - KAEC | COM.HKA.TST | Commissioning and handover | HKA | MS6 | 10% |  |  | 0.4 |  | 222575 |  | MS6 Testing and commissioning (SAT) 10% x station price share 8.97% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 258 |  | 2029-01-09 | 2029-01-18 | 8
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | HKA-T1020 | Site acceptance test (SAT) and commissioning - KAEC | COM.HKA.TST | Commissioning and handover | HKA | MS6 | 10% |  |  | 0.6 |  | 333863 |  | MS6 Testing and commissioning (SAT) 10% x station price share 8.97% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 345 |  | 2029-01-21 | 2029-02-05 | 12
SH-TRN | Training (per railway, allocated) | HKA-T2010 | Operator and maintenance training - KAEC | COM.HKA.TRN | Commissioning and handover | HKA | MS7 | 10% |  |  | 0.15 |  | 83466 |  | MS7 Final acceptance and handover 10% x station price share 8.97% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 172 |  | 2029-02-06 | 2029-02-27 | 10
A1-A5 | A1 to A5 equipment sections: trial operation share | HKA-T2020 | Trial operation (maximum 45 days) - KAEC | COM.HKA.TOA | Commissioning and handover | HKA | MS7 | 10% |  |  | 0.35 |  | 194753 |  | MS7 Final acceptance and handover 10% x station price share 8.97% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 258 |  | 2029-02-06 | 2029-03-27 | 30
A1-A5 | A1 to A5 equipment sections: handover share | HKA-T3010 | Taking-over application, SAR review and handover - KAEC | COM.HKA.TOA | Commissioning and handover | HKA | MS7 | 10% |  |  | 0.3 |  | 166931 |  | MS7 Final acceptance and handover 10% x station price share 8.97% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 258 |  | 2029-03-28 | 2029-05-03 | 22
SH-DES | Design and engineering package (per railway, allocated to the station) | HMD-E1010 | Survey: submittal of site survey and as-found report - Madinah | ENG.HMD.SRV.SUB | Engineering | HMD | MS2 | 10% |  |  | 0.069 |  | 38379 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 6.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 62 |  | 2028-01-16 | 2028-02-06 | 16
SH-DES | Design and engineering package (per railway, allocated to the station) | HMD-E1020 | Survey: SAR approval of survey report - Madinah | ENG.HMD.SRV.APR | Engineering | HMD | MS3 | 10% |  |  | 0.05 |  | 27811 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 39 |  | 2028-02-07 | 2028-03-05 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HMD-E1030 | Concept design: submittal - Madinah | ENG.HMD.CNC.SUB | Engineering | HMD | MS2 | 10% |  |  | 0.098 |  | 54509 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 9.8% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 32 |  | 2028-02-07 | 2028-02-15 | 7
SH-DES | Design and engineering package (per railway, allocated to the station) | HMD-E1040 | Concept design: SAR review and approval - Madinah | ENG.HMD.CNC.APR | Engineering | HMD | MS3 | 10% |  |  | 0.1 |  | 55621 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 10.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 69 |  | 2028-02-16 | 2028-03-14 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HMD-E1050 | Preliminary design: submittal - Madinah | ENG.HMD.PRE.SUB | Engineering | HMD | MS2 | 10% |  |  | 0.196 |  | 109018 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 81 |  | 2028-02-16 | 2028-03-09 | 12
SH-DES | Design and engineering package (per railway, allocated to the station) | HMD-E1060 | Preliminary design: SAR review and approval - Madinah | ENG.HMD.PRE.APR | Engineering | HMD | MS3 | 10% |  |  | 0.2 |  | 111243 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 101 |  | 2028-03-12 | 2028-03-30 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HMD-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Madinah | ENG.HMD.DET.SUB | Engineering | HMD | MS2 | 10% |  |  | 0.392 |  | 218036 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 39.2% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 166 |  | 2028-03-12 | 2028-04-04 | 18
SH-DES | Design and engineering package (per railway, allocated to the station) | HMD-E1080 | Detailed design: SAR review and approval - Madinah | ENG.HMD.DET.APR | Engineering | HMD | MS3 | 10% |  |  | 0.4 |  | 222485 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 40.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 138 |  | 2028-04-05 | 2028-04-25 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HMD-E1090 | IFC and shop drawings: submittal - Madinah | ENG.HMD.IFC.SUB | Engineering | HMD | MS2 | 10% |  |  | 0.196 |  | 109018 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 68 |  | 2028-04-05 | 2028-04-17 | 9
SH-DES | Design and engineering package (per railway, allocated to the station) | HMD-E1100 | IFC and shop drawings: SAR approval and release - Madinah | ENG.HMD.IFC.APR | Engineering | HMD | MS3 | 10% |  |  | 0.2 |  | 111243 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 114 |  | 2028-04-18 | 2028-05-15 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | HMD-E1110 | HCIS Stage 3 and 4 documents: preparation - Madinah | ENG.HMD.HCS.SUB | Engineering | HMD | MS2 | 10% |  |  | 0.049 |  | 27254 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 4.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 35 |  | 2028-03-21 | 2028-04-17 | 20
SH-DES | Design and engineering package (per railway, allocated to the station) | HMD-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Madinah | ENG.HMD.HCS.APR | Engineering | HMD | MS3 | 10% |  |  | 0.05 |  | 27811 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 26 |  | 2028-04-18 | 2028-05-15 | 15
SH-DES, SH-TRN | Design and engineering package (per railway, allocated to the station) and Training (per railway, allocated): documentation and training share | HMD-E1130 | As-built and O&M documentation: submittal - Madinah | ENG.HMD.ASB.SUB | Engineering | HMD | MS7 | 10% |  |  | 0.15 |  | 83432 |  | MS7 Final acceptance and handover 10% x station price share 8.97% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 71 |  | 2029-01-14 | 2029-03-12 | 36
SH-DES | Design and engineering package (per railway, allocated to the station): documentation share | HMD-E1140 | As-built and O&M documentation: SAR review and approval - Madinah | ENG.HMD.ASB.APR | Engineering | HMD | MS7 | 10% |  |  | 0.05 |  | 27811 |  | MS7 Final acceptance and handover 10% x station price share 8.97% ¦ Fixed key 5% | Annex 3 documentation share | 30 |  | 2029-03-13 | 2029-04-02 | 15
- | No BOQ cost: administrative or review step with no payment milestone | HMD-X1010 | Enabling works: site preparation, setting out, temporary works and utilities clearance - Madinah | CON.HMD.ENA | Construction | HMD | MS5 | 20% |  |  | 0.0036004 |  | 4005 |  | MS5 Installation 20% x station price share 8.97% ¦ BOQ civil share 9.0% x 4% (enabling: site preparation) | Annex 3 A6 Civil works (SAR 291,036) | 86 |  | 2028-05-16 | 2028-05-22 | 5
- | No BOQ cost: administrative or review step with no payment milestone | HMD-X1020 | Enabling works: cable routes, duct-bank and cabinet plinth preparation - Madinah | CON.HMD.ENA | Construction | HMD | MS5 | 20% |  |  | 0.0054006 |  | 6008 |  | MS5 Installation 20% x station price share 8.97% ¦ BOQ civil share 9.0% x 6% (enabling: routes, ducts, plinths) | Annex 3 A6 Civil works (SAR 291,036) | 129 |  | 2028-05-23 | 2028-06-05 | 10
A1 | A1 CCTV system | HMD-P1010 | Manufacture CCTV cameras and analytics - Madinah | PRO.HMD.CCT | Procurement | HMD | MS4 | 20% |  |  | 0.23816 |  | 264932 |  | MS4 Material delivery 20% x station price share 8.97% ¦ BOQ section share 31.8% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 934,319) | 656 |  | 2028-05-16 | 2028-08-06 | 59
A2 | A2 Video management and video wall | HMD-P1020 | Manufacture video management servers, storage and video wall - Madinah | PRO.HMD.VMS | Procurement | HMD | MS4 | 20% |  |  | 0.1043 |  | 116027 |  | MS4 Material delivery 20% x station price share 8.97% ¦ BOQ section share 13.9% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 409,184) | 287 |  | 2028-05-16 | 2028-08-06 | 59
A3 | A3 Access control and intercom | HMD-P1030 | Manufacture access control and intercom equipment - Madinah | PRO.HMD.ACC | Procurement | HMD | MS4 | 20% |  |  | 0.011237 |  | 12501 |  | MS4 Material delivery 20% x station price share 8.97% ¦ BOQ section share 1.5% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 31 |  | 2028-05-16 | 2028-08-06 | 59
A4, A5 | A4 UPS and A5 Poles, cabinets and network | HMD-P1040 | Manufacture UPS, network switches and field cabinets - Madinah | PRO.HMD.UPN | Procurement | HMD | MS4 | 20% |  |  | 0.39631 |  | 440861 |  | MS4 Material delivery 20% x station price share 8.97% ¦ BOQ section share 52.8% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 1,554,756) | 1092 |  | 2028-05-16 | 2028-08-06 | 59
SH-FAT | Factory acceptance test (per railway, allocated) | HMD-P1050 | Factory acceptance test at vendor premises - Madinah | PRO.HMD.LOG | Procurement | HMD | MS4 | 20% |  |  | 0.05 |  | 55621 |  | MS4 Material delivery 20% x station price share 8.97% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 344 |  | 2028-08-07 | 2028-08-20 | 10
A1-A5 | A1 to A5 equipment sections: logistics (shipping, customs, delivery) share | HMD-P1060 | Shipping and customs clearance - Madinah | PRO.HMD.LOG | Procurement | HMD | MS4 | 20% |  |  | 0.15 |  | 166864 |  | MS4 Material delivery 20% x station price share 8.97% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 689 |  | 2028-08-21 | 2028-09-26 | 27
SH-SPR | Commissioning spares (per railway, allocated) | HMD-P1070 | Delivery to station and receiving inspection - Madinah | PRO.HMD.LOG | Procurement | HMD | MS4 | 20% |  |  | 0.05 |  | 55621 |  | MS4 Material delivery 20% x station price share 8.97% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 344 |  | 2028-09-27 | 2028-10-03 | 5
A6 | A6 Civil works | HMD-C1010 | Civil: platform trenches and duct banks - Madinah | CON.HMD.CIV | Construction | HMD | MS5 | 20% |  |  | 0.045005 |  | 50065 |  | MS5 Installation 20% x station price share 8.97% ¦ BOQ civil share 9.0% x 50% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 291,036) | 560 |  | 2028-06-06 | 2028-07-18 | 31
A6 | A6 Civil works | HMD-C1020 | Civil: camera and ALPR pole foundations and poles - Madinah | CON.HMD.CIV | Construction | HMD | MS5 | 20% |  |  | 0.036004 |  | 40052 |  | MS5 Installation 20% x station price share 8.97% ¦ BOQ civil share 9.0% x 40% (poles) | Annex 3 A6 Civil works (SAR 291,036) | 431 |  | 2028-07-04 | 2028-08-06 | 24
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | HMD-C2010 | Install UPS, network switches and field cabinets - Madinah | CON.HMD.INS | Construction | HMD | MS5 | 20% |  |  | 0.182 |  | 202459 |  | MS5 Installation 20% x station price share 8.97% ¦ Installation key 20% x (1 - civil share 9.0%) | Annex 3 equipment sections A1-A5 (installation share) | 258 |  | 2028-10-04 | 2028-11-02 | 22
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | HMD-C2020 | Cabling and termination (power, fibre, data) - Madinah | CON.HMD.INS | Construction | HMD | MS5 | 20% |  |  | 0.273 |  | 303689 |  | MS5 Installation 20% x station price share 8.97% ¦ Installation key 30% x (1 - civil share 9.0%) | Annex 3 equipment sections A1-A5 (installation share) | 517 |  | 2028-10-15 | 2028-12-03 | 36
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | HMD-C2030 | Install and aim CCTV cameras - Madinah | CON.HMD.INS | Construction | HMD | MS5 | 20% |  |  | 0.2275 |  | 253074 |  | MS5 Installation 20% x station price share 8.97% ¦ Installation key 25% x (1 - civil share 9.0%) | Annex 3 equipment sections A1-A5 (installation share) | 431 |  | 2028-12-04 | 2029-01-11 | 29
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | HMD-C2040 | Install video management, video wall and control-room equipment - Madinah | CON.HMD.INS | Construction | HMD | MS5 | 20% |  |  | 0.1365 |  | 151845 |  | MS5 Installation 20% x station price share 8.97% ¦ Installation key 15% x (1 - civil share 9.0%) | Annex 3 equipment sections A1-A5 (installation share) | 258 |  | 2028-11-05 | 2028-12-07 | 25
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | HMD-C2050 | Install access control and intercom - Madinah | CON.HMD.INS | Construction | HMD | MS5 | 20% |  |  | 0.090999 |  | 101230 |  | MS5 Installation 20% x station price share 8.97% ¦ Installation key 10% x (1 - civil share 9.0%) | Annex 3 equipment sections A1-A5 (installation share) | 172 |  | 2028-11-14 | 2028-12-13 | 22
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | HMD-T1010 | Pre-commissioning and loop checks - Madinah | COM.HMD.TST | Commissioning and handover | HMD | MS6 | 10% |  |  | 0.4 |  | 222485 |  | MS6 Testing and commissioning (SAT) 10% x station price share 8.97% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 258 |  | 2029-01-14 | 2029-01-23 | 8
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | HMD-T1020 | Site acceptance test (SAT) and commissioning - Madinah | COM.HMD.TST | Commissioning and handover | HMD | MS6 | 10% |  |  | 0.6 |  | 333728 |  | MS6 Testing and commissioning (SAT) 10% x station price share 8.97% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 344 |  | 2029-01-24 | 2029-02-18 | 13
SH-TRN | Training (per railway, allocated) | HMD-T2010 | Operator and maintenance training - Madinah | COM.HMD.TRN | Commissioning and handover | HMD | MS7 | 10% |  |  | 0.15 |  | 83432 |  | MS7 Final acceptance and handover 10% x station price share 8.97% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 172 |  | 2029-02-19 | 2029-03-05 | 10
A1-A5 | A1 to A5 equipment sections: trial operation share | HMD-T2020 | Trial operation (maximum 45 days) - Madinah | COM.HMD.TOA | Commissioning and handover | HMD | MS7 | 10% |  |  | 0.35 |  | 194675 |  | MS7 Final acceptance and handover 10% x station price share 8.97% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 258 |  | 2029-02-19 | 2029-04-02 | 30
A1-A5 | A1 to A5 equipment sections: handover share | HMD-T3010 | Taking-over application, SAR review and handover - Madinah | COM.HMD.TOA | Commissioning and handover | HMD | MS7 | 10% |  |  | 0.3 |  | 166864 |  | MS7 Final acceptance and handover 10% x station price share 8.97% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 258 |  | 2029-04-03 | 2029-05-09 | 22
SH-DES | Design and engineering package (per railway, allocated to the station) | EAB-E1010 | Survey: submittal of site survey and as-found report - Abqaiq | ENG.EAB.SRV.SUB | Engineering | EAB | MS2 | 10% |  |  | 0.069 |  | 13839 |  | MS2 Engineering submittal 10% x station price share 3.23% ¦ Design stage key 6.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 18 |  | 2028-03-08 | 2028-03-19 | 8
SH-DES | Design and engineering package (per railway, allocated to the station) | EAB-E1020 | Survey: SAR approval of survey report - Abqaiq | ENG.EAB.SRV.APR | Engineering | EAB | MS3 | 10% |  |  | 0.05 |  | 10028 |  | MS3 SAR approval of engineering 10% x station price share 3.23% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 19 |  | 2028-03-20 | 2028-04-09 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | EAB-E1030 | Concept design: submittal - Abqaiq | ENG.EAB.CNC.SUB | Engineering | EAB | MS2 | 10% |  |  | 0.098 |  | 19656 |  | MS2 Engineering submittal 10% x station price share 3.23% ¦ Design stage key 9.8% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 14 |  | 2028-03-20 | 2028-03-30 | 9
SH-DES | Design and engineering package (per railway, allocated to the station) | EAB-E1040 | Concept design: SAR review and approval - Abqaiq | ENG.EAB.CNC.APR | Engineering | EAB | MS3 | 10% |  |  | 0.1 |  | 20057 |  | MS3 SAR approval of engineering 10% x station price share 3.23% ¦ Design stage key 10.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 23 |  | 2028-04-02 | 2028-04-20 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | EAB-E1050 | Preliminary design: submittal - Abqaiq | ENG.EAB.PRE.SUB | Engineering | EAB | MS2 | 10% |  |  | 0.196 |  | 39311 |  | MS2 Engineering submittal 10% x station price share 3.23% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 33 |  | 2028-04-02 | 2028-04-20 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | EAB-E1060 | Preliminary design: SAR review and approval - Abqaiq | ENG.EAB.PRE.APR | Engineering | EAB | MS3 | 10% |  |  | 0.2 |  | 40114 |  | MS3 SAR approval of engineering 10% x station price share 3.23% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 33 |  | 2028-04-23 | 2028-05-18 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | EAB-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Abqaiq | ENG.EAB.DET.SUB | Engineering | EAB | MS2 | 10% |  |  | 0.392 |  | 78623 |  | MS2 Engineering submittal 10% x station price share 3.23% ¦ Design stage key 39.2% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 67 |  | 2028-04-23 | 2028-05-31 | 24
SH-DES | Design and engineering package (per railway, allocated to the station) | EAB-E1080 | Detailed design: SAR review and approval - Abqaiq | ENG.EAB.DET.APR | Engineering | EAB | MS3 | 10% |  |  | 0.4 |  | 80227 |  | MS3 SAR approval of engineering 10% x station price share 3.23% ¦ Design stage key 40.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 42 |  | 2028-06-01 | 2028-06-21 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | EAB-E1090 | IFC and shop drawings: submittal - Abqaiq | ENG.EAB.IFC.SUB | Engineering | EAB | MS2 | 10% |  |  | 0.196 |  | 39311 |  | MS2 Engineering submittal 10% x station price share 3.23% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 28 |  | 2028-06-01 | 2028-06-15 | 11
SH-DES | Design and engineering package (per railway, allocated to the station) | EAB-E1100 | IFC and shop drawings: SAR approval and release - Abqaiq | ENG.EAB.IFC.APR | Engineering | EAB | MS3 | 10% |  |  | 0.2 |  | 40114 |  | MS3 SAR approval of engineering 10% x station price share 3.23% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 38 |  | 2028-06-18 | 2028-07-06 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | EAB-E1110 | HCIS Stage 3 and 4 documents: preparation - Abqaiq | ENG.EAB.HCS.SUB | Engineering | EAB | MS2 | 10% |  |  | 0.049 |  | 9828 |  | MS2 Engineering submittal 10% x station price share 3.23% ¦ Design stage key 4.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 14 |  | 2028-05-11 | 2028-06-15 | 26
SH-DES | Design and engineering package (per railway, allocated to the station) | EAB-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Abqaiq | ENG.EAB.HCS.APR | Engineering | EAB | MS3 | 10% |  |  | 0.05 |  | 10028 |  | MS3 SAR approval of engineering 10% x station price share 3.23% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 8 |  | 2028-06-18 | 2028-07-06 | 15
SH-DES, SH-TRN | Design and engineering package (per railway, allocated to the station) and Training (per railway, allocated): documentation and training share | EAB-E1130 | As-built and O&M documentation: submittal - Abqaiq | ENG.EAB.ASB.SUB | Engineering | EAB | MS7 | 10% |  |  | 0.15 |  | 30085 |  | MS7 Final acceptance and handover 10% x station price share 3.23% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 23 |  | 2028-11-23 | 2028-12-28 | 26
SH-DES | Design and engineering package (per railway, allocated to the station): documentation share | EAB-E1140 | As-built and O&M documentation: SAR review and approval - Abqaiq | ENG.EAB.ASB.APR | Engineering | EAB | MS7 | 10% |  |  | 0.05 |  | 10028 |  | MS7 Final acceptance and handover 10% x station price share 3.23% ¦ Fixed key 5% | Annex 3 documentation share | 13 |  | 2028-12-31 | 2029-01-18 | 15
- | No BOQ cost: administrative or review step with no payment milestone | EAB-X1010 | Enabling works: site preparation, setting out, temporary works and utilities clearance - Abqaiq | CON.EAB.ENA | Construction | EAB | MS5 | 20% |  |  | 0.011755 |  | 4715 |  | MS5 Installation 20% x station price share 3.23% ¦ BOQ civil share 29.4% x 4% (enabling: site preparation) | Annex 3 A6 Civil works (SAR 375,936) | 31 |  | 2028-07-09 | 2028-07-13 | 5
- | No BOQ cost: administrative or review step with no payment milestone | EAB-X1020 | Enabling works: cable routes, duct-bank and cabinet plinth preparation - Abqaiq | CON.EAB.ENA | Construction | EAB | MS5 | 20% |  |  | 0.017633 |  | 7073 |  | MS5 Installation 20% x station price share 3.23% ¦ BOQ civil share 29.4% x 6% (enabling: routes, ducts, plinths) | Annex 3 A6 Civil works (SAR 375,936) | 47 |  | 2028-07-16 | 2028-07-27 | 10
A1 | A1 CCTV system | EAB-P1010 | Manufacture CCTV cameras and analytics - Abqaiq | PRO.EAB.CCT | Procurement | EAB | MS4 | 20% |  |  | 0.092232 |  | 36997 |  | MS4 Material delivery 20% x station price share 3.23% ¦ BOQ section share 12.3% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 111,083) | 92 |  | 2028-07-09 | 2028-08-30 | 39
A2 | A2 Video management and video wall | EAB-P1020 | Manufacture video management servers, storage and video wall - Abqaiq | PRO.EAB.VMS | Procurement | EAB | MS4 | 20% |  |  | 0.23749 |  | 95266 |  | MS4 Material delivery 20% x station price share 3.23% ¦ BOQ section share 31.7% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 286,032) | 236 |  | 2028-07-09 | 2028-08-30 | 39
A3 | A3 Access control and intercom | EAB-P1030 | Manufacture access control and intercom equipment - Abqaiq | PRO.EAB.ACC | Procurement | EAB | MS4 | 20% |  |  | 0.036604 |  | 14683 |  | MS4 Material delivery 20% x station price share 3.23% ¦ BOQ section share 4.9% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 36 |  | 2028-07-09 | 2028-08-30 | 39
A4, A5 | A4 UPS and A5 Poles, cabinets and network | EAB-P1040 | Manufacture UPS, network switches and field cabinets - Abqaiq | PRO.EAB.UPN | Procurement | EAB | MS4 | 20% |  |  | 0.38367 |  | 153905 |  | MS4 Material delivery 20% x station price share 3.23% ¦ BOQ section share 51.2% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 462,093) | 381 |  | 2028-07-09 | 2028-08-30 | 39
SH-FAT | Factory acceptance test (per railway, allocated) | EAB-P1050 | Factory acceptance test at vendor premises - Abqaiq | PRO.EAB.LOG | Procurement | EAB | MS4 | 20% |  |  | 0.05 |  | 20057 |  | MS4 Material delivery 20% x station price share 3.23% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 124 |  | 2028-08-31 | 2028-09-13 | 10
A1-A5 | A1 to A5 equipment sections: logistics (shipping, customs, delivery) share | EAB-P1060 | Shipping and customs clearance - Abqaiq | PRO.EAB.LOG | Procurement | EAB | MS4 | 20% |  |  | 0.15 |  | 60170 |  | MS4 Material delivery 20% x station price share 3.23% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 248 |  | 2028-09-14 | 2028-10-10 | 19
SH-SPR | Commissioning spares (per railway, allocated) | EAB-P1070 | Delivery to station and receiving inspection - Abqaiq | PRO.EAB.LOG | Procurement | EAB | MS4 | 20% |  |  | 0.05 |  | 20057 |  | MS4 Material delivery 20% x station price share 3.23% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 124 |  | 2028-10-11 | 2028-10-17 | 5
A6 | A6 Civil works | EAB-C1010 | Civil: platform trenches and duct banks - Abqaiq | CON.EAB.CIV | Construction | EAB | MS5 | 20% |  |  | 0.14694 |  | 58942 |  | MS5 Installation 20% x station price share 3.23% ¦ BOQ civil share 29.4% x 50% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 375,936) | 202 |  | 2028-07-30 | 2028-09-17 | 36
A6 | A6 Civil works | EAB-C1020 | Civil: camera and ALPR pole foundations and poles - Abqaiq | CON.EAB.CIV | Construction | EAB | MS5 | 20% |  |  | 0.11755 |  | 47154 |  | MS5 Installation 20% x station price share 3.23% ¦ BOQ civil share 29.4% x 40% (poles) | Annex 3 A6 Civil works (SAR 375,936) | 155 |  | 2028-08-30 | 2028-10-08 | 28
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | EAB-C2010 | Install UPS, network switches and field cabinets - Abqaiq | CON.EAB.INS | Construction | EAB | MS5 | 20% |  |  | 0.14122 |  | 56650 |  | MS5 Installation 20% x station price share 3.23% ¦ Installation key 20% x (1 - civil share 29.4%) | Annex 3 equipment sections A1-A5 (installation share) | 93 |  | 2028-10-18 | 2028-10-29 | 8
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | EAB-C2020 | Cabling and termination (power, fibre, data) - Abqaiq | CON.EAB.INS | Construction | EAB | MS5 | 20% |  |  | 0.21184 |  | 84975 |  | MS5 Installation 20% x station price share 3.23% ¦ Installation key 30% x (1 - civil share 29.4%) | Annex 3 equipment sections A1-A5 (installation share) | 186 |  | 2028-10-23 | 2028-11-08 | 13
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | EAB-C2030 | Install and aim CCTV cameras - Abqaiq | CON.EAB.INS | Construction | EAB | MS5 | 20% |  |  | 0.17653 |  | 70813 |  | MS5 Installation 20% x station price share 3.23% ¦ Installation key 25% x (1 - civil share 29.4%) | Annex 3 equipment sections A1-A5 (installation share) | 155 |  | 2028-11-09 | 2028-11-22 | 10
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | EAB-C2040 | Install video management, video wall and control-room equipment - Abqaiq | CON.EAB.INS | Construction | EAB | MS5 | 20% |  |  | 0.10592 |  | 42488 |  | MS5 Installation 20% x station price share 3.23% ¦ Installation key 15% x (1 - civil share 29.4%) | Annex 3 equipment sections A1-A5 (installation share) | 93 |  | 2028-10-30 | 2028-11-09 | 9
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | EAB-C2050 | Install access control and intercom - Abqaiq | CON.EAB.INS | Construction | EAB | MS5 | 20% |  |  | 0.070612 |  | 28325 |  | MS5 Installation 20% x station price share 3.23% ¦ Installation key 10% x (1 - civil share 29.4%) | Annex 3 equipment sections A1-A5 (installation share) | 62 |  | 2028-11-02 | 2028-11-13 | 8
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | EAB-T1010 | Pre-commissioning and loop checks - Abqaiq | COM.EAB.TST | Commissioning and handover | EAB | MS6 | 10% |  |  | 0.4 |  | 80227 |  | MS6 Testing and commissioning (SAT) 10% x station price share 3.23% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 93 |  | 2028-11-23 | 2028-11-28 | 4
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | EAB-T1020 | Site acceptance test (SAT) and commissioning - Abqaiq | COM.EAB.TST | Commissioning and handover | EAB | MS6 | 10% |  |  | 0.6 |  | 120341 |  | MS6 Testing and commissioning (SAT) 10% x station price share 3.23% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 124 |  | 2028-11-29 | 2028-12-07 | 7
SH-TRN | Training (per railway, allocated) | EAB-T2010 | Operator and maintenance training - Abqaiq | COM.EAB.TRN | Commissioning and handover | EAB | MS7 | 10% |  |  | 0.15 |  | 30085 |  | MS7 Final acceptance and handover 10% x station price share 3.23% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 62 |  | 2028-12-10 | 2028-12-21 | 10
A1-A5 | A1 to A5 equipment sections: trial operation share | EAB-T2020 | Trial operation (maximum 45 days) - Abqaiq | COM.EAB.TOA | Commissioning and handover | EAB | MS7 | 10% |  |  | 0.35 |  | 70199 |  | MS7 Final acceptance and handover 10% x station price share 3.23% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 93 |  | 2028-12-10 | 2029-01-18 | 30
A1-A5 | A1 to A5 equipment sections: handover share | EAB-T3010 | Taking-over application, SAR review and handover - Abqaiq | COM.EAB.TOA | Commissioning and handover | EAB | MS7 | 10% |  |  | 0.3 |  | 60170 |  | MS7 Final acceptance and handover 10% x station price share 3.23% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 93 |  | 2029-01-21 | 2029-02-27 | 22
SH-DES | Design and engineering package (per railway, allocated to the station) | NHL-E1010 | Survey: submittal of site survey and as-found report - Hail | ENG.NHL.SRV.SUB | Engineering | NHL | MS2 | 10% |  |  | 0.069 |  | 23453 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 6.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 30 |  | 2028-04-02 | 2028-04-11 | 8
SH-DES | Design and engineering package (per railway, allocated to the station) | NHL-E1020 | Survey: SAR approval of survey report - Hail | ENG.NHL.SRV.APR | Engineering | NHL | MS3 | 10% |  |  | 0.05 |  | 16995 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 32 |  | 2028-04-12 | 2028-05-09 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NHL-E1030 | Concept design: submittal - Hail | ENG.NHL.CNC.SUB | Engineering | NHL | MS2 | 10% |  |  | 0.098 |  | 33309 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 9.8% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 23 |  | 2028-04-12 | 2028-04-24 | 9
SH-DES | Design and engineering package (per railway, allocated to the station) | NHL-E1040 | Concept design: SAR review and approval - Hail | ENG.NHL.CNC.APR | Engineering | NHL | MS3 | 10% |  |  | 0.1 |  | 33989 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 10.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 39 |  | 2028-04-25 | 2028-05-22 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NHL-E1050 | Preliminary design: submittal - Hail | ENG.NHL.PRE.SUB | Engineering | NHL | MS2 | 10% |  |  | 0.196 |  | 66619 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 56 |  | 2028-04-25 | 2028-05-22 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NHL-E1060 | Preliminary design: SAR review and approval - Hail | ENG.NHL.PRE.APR | Engineering | NHL | MS3 | 10% |  |  | 0.2 |  | 67978 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 56 |  | 2028-05-23 | 2028-06-12 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NHL-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Hail | ENG.NHL.DET.SUB | Engineering | NHL | MS2 | 10% |  |  | 0.392 |  | 133238 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 39.2% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 114 |  | 2028-05-23 | 2028-06-25 | 24
SH-DES | Design and engineering package (per railway, allocated to the station) | NHL-E1080 | Detailed design: SAR review and approval - Hail | ENG.NHL.DET.APR | Engineering | NHL | MS3 | 10% |  |  | 0.4 |  | 135957 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 40.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 71 |  | 2028-06-26 | 2028-07-16 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NHL-E1090 | IFC and shop drawings: submittal - Hail | ENG.NHL.IFC.SUB | Engineering | NHL | MS2 | 10% |  |  | 0.196 |  | 66619 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 50 |  | 2028-06-26 | 2028-07-11 | 12
SH-DES | Design and engineering package (per railway, allocated to the station) | NHL-E1100 | IFC and shop drawings: SAR approval and release - Hail | ENG.NHL.IFC.APR | Engineering | NHL | MS3 | 10% |  |  | 0.2 |  | 67978 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 62 |  | 2028-07-12 | 2028-08-01 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NHL-E1110 | HCIS Stage 3 and 4 documents: preparation - Hail | ENG.NHL.HCS.SUB | Engineering | NHL | MS2 | 10% |  |  | 0.049 |  | 16655 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 4.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 24 |  | 2028-06-05 | 2028-07-11 | 27
SH-DES | Design and engineering package (per railway, allocated to the station) | NHL-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Hail | ENG.NHL.HCS.APR | Engineering | NHL | MS3 | 10% |  |  | 0.05 |  | 16995 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 13 |  | 2028-07-12 | 2028-08-01 | 15
SH-DES, SH-TRN | Design and engineering package (per railway, allocated to the station) and Training (per railway, allocated): documentation and training share | NHL-E1130 | As-built and O&M documentation: submittal - Hail | ENG.NHL.ASB.SUB | Engineering | NHL | MS7 | 10% |  |  | 0.15 |  | 50984 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 40 |  | 2029-01-29 | 2029-03-15 | 28
SH-DES | Design and engineering package (per railway, allocated to the station): documentation share | NHL-E1140 | As-built and O&M documentation: SAR review and approval - Hail | ENG.NHL.ASB.APR | Engineering | NHL | MS7 | 10% |  |  | 0.05 |  | 16995 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 5% | Annex 3 documentation share | 22 |  | 2029-03-18 | 2029-04-05 | 15
- | No BOQ cost: administrative or review step with no payment milestone | NHL-X1010 | Enabling works: site preparation, setting out, temporary works and utilities clearance - Hail | CON.NHL.ENA | Construction | NHL | MS5 | 20% |  |  | 0.012404 |  | 8432 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 4% (enabling: site preparation) | Annex 3 A6 Civil works (SAR 745,743) | 53 |  | 2028-08-02 | 2028-08-08 | 5
- | No BOQ cost: administrative or review step with no payment milestone | NHL-X1020 | Enabling works: cable routes, duct-bank and cabinet plinth preparation - Hail | CON.NHL.ENA | Construction | NHL | MS5 | 20% |  |  | 0.018606 |  | 12648 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 6% (enabling: routes, ducts, plinths) | Annex 3 A6 Civil works (SAR 745,743) | 79 |  | 2028-08-09 | 2028-08-22 | 10
A1 | A1 CCTV system | NHL-P1010 | Manufacture CCTV cameras and analytics - Hail | PRO.NHL.CCT | Procurement | NHL | MS4 | 20% |  |  | 0.15324 |  | 104169 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 20.4% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 338,989) | 258 |  | 2028-08-02 | 2028-10-05 | 47
A2 | A2 Video management and video wall | NHL-P1020 | Manufacture video management servers, storage and video wall - Hail | PRO.NHL.VMS | Procurement | NHL | MS4 | 20% |  |  | 0.16238 |  | 110385 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 21.7% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 359,215) | 273 |  | 2028-08-02 | 2028-10-05 | 47
A3 | A3 Access control and intercom | NHL-P1030 | Manufacture access control and intercom equipment - Hail | PRO.NHL.ACC | Procurement | NHL | MS4 | 20% |  |  | 0.019928 |  | 13547 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 2.7% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 34 |  | 2028-08-02 | 2028-10-05 | 47
A4, A5 | A4 UPS and A5 Poles, cabinets and network | NHL-P1040 | Manufacture UPS, network switches and field cabinets - Hail | PRO.NHL.UPN | Procurement | NHL | MS4 | 20% |  |  | 0.41445 |  | 281736 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 55.3% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 916,830) | 698 |  | 2028-08-02 | 2028-10-05 | 47
SH-FAT | Factory acceptance test (per railway, allocated) | NHL-P1050 | Factory acceptance test at vendor premises - Hail | PRO.NHL.LOG | Procurement | NHL | MS4 | 20% |  |  | 0.05 |  | 33989 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 211 |  | 2028-10-08 | 2028-10-19 | 10
A1-A5 | A1 to A5 equipment sections: logistics (shipping, customs, delivery) share | NHL-P1060 | Shipping and customs clearance - Hail | PRO.NHL.LOG | Procurement | NHL | MS4 | 20% |  |  | 0.15 |  | 101967 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 421 |  | 2028-10-22 | 2028-11-20 | 22
SH-SPR | Commissioning spares (per railway, allocated) | NHL-P1070 | Delivery to station and receiving inspection - Hail | PRO.NHL.LOG | Procurement | NHL | MS4 | 20% |  |  | 0.05 |  | 33989 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 211 |  | 2028-11-21 | 2028-11-27 | 5
A6 | A6 Civil works | NHL-C1010 | Civil: platform trenches and duct banks - Hail | CON.NHL.CIV | Construction | NHL | MS5 | 20% |  |  | 0.15505 |  | 105400 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 50% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 745,743) | 342 |  | 2028-08-23 | 2028-11-09 | 57
A6 | A6 Civil works | NHL-C1020 | Civil: camera and ALPR pole foundations and poles - Hail | CON.NHL.CIV | Construction | NHL | MS5 | 20% |  |  | 0.12404 |  | 84320 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 40% (poles) | Annex 3 A6 Civil works (SAR 745,743) | 263 |  | 2028-10-15 | 2028-12-14 | 45
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NHL-C2010 | Install UPS, network switches and field cabinets - Hail | CON.NHL.INS | Construction | NHL | MS5 | 20% |  |  | 0.13798 |  | 93797 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 20% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 158 |  | 2028-11-28 | 2028-12-14 | 13
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NHL-C2020 | Cabling and termination (power, fibre, data) - Hail | CON.NHL.INS | Construction | NHL | MS5 | 20% |  |  | 0.20697 |  | 140695 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 30% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 316 |  | 2028-12-04 | 2029-01-02 | 22
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NHL-C2030 | Install and aim CCTV cameras - Hail | CON.NHL.INS | Construction | NHL | MS5 | 20% |  |  | 0.17248 |  | 117246 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 25% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 263 |  | 2029-01-03 | 2029-01-28 | 18
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NHL-C2040 | Install video management, video wall and control-room equipment - Hail | CON.NHL.INS | Construction | NHL | MS5 | 20% |  |  | 0.10349 |  | 70348 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 15% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 158 |  | 2028-12-17 | 2029-01-04 | 15
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NHL-C2050 | Install access control and intercom - Hail | CON.NHL.INS | Construction | NHL | MS5 | 20% |  |  | 0.06899 |  | 46898 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 10% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 105 |  | 2028-12-21 | 2029-01-08 | 13
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | NHL-T1010 | Pre-commissioning and loop checks - Hail | COM.NHL.TST | Commissioning and handover | NHL | MS6 | 10% |  |  | 0.4 |  | 135957 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.48% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 158 |  | 2029-01-29 | 2029-02-04 | 5
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | NHL-T1020 | Site acceptance test (SAT) and commissioning - Hail | COM.NHL.TST | Commissioning and handover | NHL | MS6 | 10% |  |  | 0.6 |  | 203935 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.48% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 211 |  | 2029-02-05 | 2029-02-21 | 8
SH-TRN | Training (per railway, allocated) | NHL-T2010 | Operator and maintenance training - Hail | COM.NHL.TRN | Commissioning and handover | NHL | MS7 | 10% |  |  | 0.15 |  | 50984 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 105 |  | 2029-02-25 | 2029-03-08 | 10
A1-A5 | A1 to A5 equipment sections: trial operation share | NHL-T2020 | Trial operation (maximum 45 days) - Hail | COM.NHL.TOA | Commissioning and handover | NHL | MS7 | 10% |  |  | 0.35 |  | 118962 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 158 |  | 2029-02-25 | 2029-04-05 | 30
A1-A5 | A1 to A5 equipment sections: handover share | NHL-T3010 | Taking-over application, SAR review and handover - Hail | COM.NHL.TOA | Commissioning and handover | NHL | MS7 | 10% |  |  | 0.3 |  | 101967 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 158 |  | 2029-04-08 | 2029-05-14 | 22
SH-DES | Design and engineering package (per railway, allocated to the station) | NJF-E1010 | Survey: submittal of site survey and as-found report - Al Jouf | ENG.NJF.SRV.SUB | Engineering | NJF | MS2 | 10% |  |  | 0.069 |  | 23618 |  | MS2 Engineering submittal 10% x station price share 5.52% ¦ Design stage key 6.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 30 |  | 2028-06-18 | 2028-06-27 | 8
SH-DES | Design and engineering package (per railway, allocated to the station) | NJF-E1020 | Survey: SAR approval of survey report - Al Jouf | ENG.NJF.SRV.APR | Engineering | NJF | MS3 | 10% |  |  | 0.05 |  | 17114 |  | MS3 SAR approval of engineering 10% x station price share 5.52% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 33 |  | 2028-06-28 | 2028-07-18 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NJF-E1030 | Concept design: submittal - Al Jouf | ENG.NJF.CNC.SUB | Engineering | NJF | MS2 | 10% |  |  | 0.098 |  | 33544 |  | MS2 Engineering submittal 10% x station price share 5.52% ¦ Design stage key 9.8% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 25 |  | 2028-06-28 | 2028-07-11 | 10
SH-DES | Design and engineering package (per railway, allocated to the station) | NJF-E1040 | Concept design: SAR review and approval - Al Jouf | ENG.NJF.CNC.APR | Engineering | NJF | MS3 | 10% |  |  | 0.1 |  | 34228 |  | MS3 SAR approval of engineering 10% x station price share 5.52% ¦ Design stage key 10.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 37 |  | 2028-07-12 | 2028-08-01 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NJF-E1050 | Preliminary design: submittal - Al Jouf | ENG.NJF.PRE.SUB | Engineering | NJF | MS2 | 10% |  |  | 0.196 |  | 67088 |  | MS2 Engineering submittal 10% x station price share 5.52% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 58 |  | 2028-07-12 | 2028-08-02 | 16
SH-DES | Design and engineering package (per railway, allocated to the station) | NJF-E1060 | Preliminary design: SAR review and approval - Al Jouf | ENG.NJF.PRE.APR | Engineering | NJF | MS3 | 10% |  |  | 0.2 |  | 68457 |  | MS3 SAR approval of engineering 10% x station price share 5.52% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 54 |  | 2028-08-03 | 2028-08-23 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NJF-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Al Jouf | ENG.NJF.DET.SUB | Engineering | NJF | MS2 | 10% |  |  | 0.392 |  | 134176 |  | MS2 Engineering submittal 10% x station price share 5.52% ¦ Design stage key 39.2% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 119 |  | 2028-08-03 | 2028-09-07 | 26
SH-DES | Design and engineering package (per railway, allocated to the station) | NJF-E1080 | Detailed design: SAR review and approval - Al Jouf | ENG.NJF.DET.APR | Engineering | NJF | MS3 | 10% |  |  | 0.4 |  | 136914 |  | MS3 SAR approval of engineering 10% x station price share 5.52% ¦ Design stage key 40.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 68 |  | 2028-09-10 | 2028-09-28 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NJF-E1090 | IFC and shop drawings: submittal - Al Jouf | ENG.NJF.IFC.SUB | Engineering | NJF | MS2 | 10% |  |  | 0.196 |  | 67088 |  | MS2 Engineering submittal 10% x station price share 5.52% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 52 |  | 2028-09-10 | 2028-09-26 | 13
SH-DES | Design and engineering package (per railway, allocated to the station) | NJF-E1100 | IFC and shop drawings: SAR approval and release - Al Jouf | ENG.NJF.IFC.APR | Engineering | NJF | MS3 | 10% |  |  | 0.2 |  | 68457 |  | MS3 SAR approval of engineering 10% x station price share 5.52% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 60 |  | 2028-09-27 | 2028-10-17 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NJF-E1110 | HCIS Stage 3 and 4 documents: preparation - Al Jouf | ENG.NJF.HCS.SUB | Engineering | NJF | MS2 | 10% |  |  | 0.049 |  | 16772 |  | MS2 Engineering submittal 10% x station price share 5.52% ¦ Design stage key 4.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 25 |  | 2028-08-17 | 2028-09-26 | 29
SH-DES | Design and engineering package (per railway, allocated to the station) | NJF-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Al Jouf | ENG.NJF.HCS.APR | Engineering | NJF | MS3 | 10% |  |  | 0.05 |  | 17114 |  | MS3 SAR approval of engineering 10% x station price share 5.52% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 13 |  | 2028-09-27 | 2028-10-17 | 15
SH-DES, SH-TRN | Design and engineering package (per railway, allocated to the station) and Training (per railway, allocated): documentation and training share | NJF-E1130 | As-built and O&M documentation: submittal - Al Jouf | ENG.NJF.ASB.SUB | Engineering | NJF | MS7 | 10% |  |  | 0.15 |  | 51343 |  | MS7 Final acceptance and handover 10% x station price share 5.52% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 41 |  | 2029-05-01 | 2029-06-07 | 28
SH-DES | Design and engineering package (per railway, allocated to the station): documentation share | NJF-E1140 | As-built and O&M documentation: SAR review and approval - Al Jouf | ENG.NJF.ASB.APR | Engineering | NJF | MS7 | 10% |  |  | 0.05 |  | 17114 |  | MS7 Final acceptance and handover 10% x station price share 5.52% ¦ Fixed key 5% | Annex 3 documentation share | 22 |  | 2029-06-10 | 2029-06-28 | 15
- | No BOQ cost: administrative or review step with no payment milestone | NJF-X1010 | Enabling works: site preparation, setting out, temporary works and utilities clearance - Al Jouf | CON.NJF.ENA | Construction | NJF | MS5 | 20% |  |  | 0.012317 |  | 8432 |  | MS5 Installation 20% x station price share 5.52% ¦ BOQ civil share 30.8% x 4% (enabling: site preparation) | Annex 3 A6 Civil works (SAR 745,743) | 53 |  | 2028-10-18 | 2028-10-24 | 5
- | No BOQ cost: administrative or review step with no payment milestone | NJF-X1020 | Enabling works: cable routes, duct-bank and cabinet plinth preparation - Al Jouf | CON.NJF.ENA | Construction | NJF | MS5 | 20% |  |  | 0.018476 |  | 12648 |  | MS5 Installation 20% x station price share 5.52% ¦ BOQ civil share 30.8% x 6% (enabling: routes, ducts, plinths) | Annex 3 A6 Civil works (SAR 745,743) | 79 |  | 2028-10-25 | 2028-11-07 | 10
A1 | A1 CCTV system | NJF-P1010 | Manufacture CCTV cameras and analytics - Al Jouf | PRO.NJF.CCT | Procurement | NJF | MS4 | 20% |  |  | 0.15169 |  | 103843 |  | MS4 Material delivery 20% x station price share 5.52% ¦ BOQ section share 20.2% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 338,989) | 257 |  | 2028-10-18 | 2028-12-21 | 47
A2 | A2 Video management and video wall | NJF-P1020 | Manufacture video management servers, storage and video wall - Al Jouf | PRO.NJF.VMS | Procurement | NJF | MS4 | 20% |  |  | 0.16074 |  | 110039 |  | MS4 Material delivery 20% x station price share 5.52% ¦ BOQ section share 21.4% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 359,215) | 273 |  | 2028-10-18 | 2028-12-21 | 47
A3 | A3 Access control and intercom | NJF-P1030 | Manufacture access control and intercom equipment - Al Jouf | PRO.NJF.ACC | Procurement | NJF | MS4 | 20% |  |  | 0.019727 |  | 13505 |  | MS4 Material delivery 20% x station price share 5.52% ¦ BOQ section share 2.6% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 33 |  | 2028-10-18 | 2028-12-21 | 47
A4, A5 | A4 UPS and A5 Poles, cabinets and network | NJF-P1040 | Manufacture UPS, network switches and field cabinets - Al Jouf | PRO.NJF.UPN | Procurement | NJF | MS4 | 20% |  |  | 0.41784 |  | 286040 |  | MS4 Material delivery 20% x station price share 5.52% ¦ BOQ section share 55.7% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 933,761) | 709 |  | 2028-10-18 | 2028-12-21 | 47
SH-FAT | Factory acceptance test (per railway, allocated) | NJF-P1050 | Factory acceptance test at vendor premises - Al Jouf | PRO.NJF.LOG | Procurement | NJF | MS4 | 20% |  |  | 0.05 |  | 34228 |  | MS4 Material delivery 20% x station price share 5.52% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 212 |  | 2028-12-24 | 2029-01-04 | 10
A1-A5 | A1 to A5 equipment sections: logistics (shipping, customs, delivery) share | NJF-P1060 | Shipping and customs clearance - Al Jouf | PRO.NJF.LOG | Procurement | NJF | MS4 | 20% |  |  | 0.15 |  | 102685 |  | MS4 Material delivery 20% x station price share 5.52% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 424 |  | 2029-01-07 | 2029-02-05 | 22
SH-SPR | Commissioning spares (per railway, allocated) | NJF-P1070 | Delivery to station and receiving inspection - Al Jouf | PRO.NJF.LOG | Procurement | NJF | MS4 | 20% |  |  | 0.05 |  | 34228 |  | MS4 Material delivery 20% x station price share 5.52% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 212 |  | 2029-02-06 | 2029-02-19 | 5
A6 | A6 Civil works | NJF-C1010 | Civil: platform trenches and duct banks - Al Jouf | CON.NJF.CIV | Construction | NJF | MS5 | 20% |  |  | 0.15397 |  | 105400 |  | MS5 Installation 20% x station price share 5.52% ¦ BOQ civil share 30.8% x 50% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 745,743) | 344 |  | 2028-11-08 | 2029-01-25 | 57
A6 | A6 Civil works | NJF-C1020 | Civil: camera and ALPR pole foundations and poles - Al Jouf | CON.NJF.CIV | Construction | NJF | MS5 | 20% |  |  | 0.12317 |  | 84320 |  | MS5 Installation 20% x station price share 5.52% ¦ BOQ civil share 30.8% x 40% (poles) | Annex 3 A6 Civil works (SAR 745,743) | 265 |  | 2028-12-31 | 2029-03-11 | 45
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NJF-C2010 | Install UPS, network switches and field cabinets - Al Jouf | CON.NJF.INS | Construction | NJF | MS5 | 20% |  |  | 0.13841 |  | 94754 |  | MS5 Installation 20% x station price share 5.52% ¦ Installation key 20% x (1 - civil share 30.8%) | Annex 3 equipment sections A1-A5 (installation share) | 159 |  | 2029-02-20 | 2029-03-11 | 13
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NJF-C2020 | Cabling and termination (power, fibre, data) - Al Jouf | CON.NJF.INS | Construction | NJF | MS5 | 20% |  |  | 0.20762 |  | 142131 |  | MS5 Installation 20% x station price share 5.52% ¦ Installation key 30% x (1 - civil share 30.8%) | Annex 3 equipment sections A1-A5 (installation share) | 318 |  | 2029-02-27 | 2029-03-28 | 22
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NJF-C2030 | Install and aim CCTV cameras - Al Jouf | CON.NJF.INS | Construction | NJF | MS5 | 20% |  |  | 0.17302 |  | 118442 |  | MS5 Installation 20% x station price share 5.52% ¦ Installation key 25% x (1 - civil share 30.8%) | Annex 3 equipment sections A1-A5 (installation share) | 265 |  | 2029-03-29 | 2029-04-30 | 18
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NJF-C2040 | Install video management, video wall and control-room equipment - Al Jouf | CON.NJF.INS | Construction | NJF | MS5 | 20% |  |  | 0.10381 |  | 71065 |  | MS5 Installation 20% x station price share 5.52% ¦ Installation key 15% x (1 - civil share 30.8%) | Annex 3 equipment sections A1-A5 (installation share) | 159 |  | 2029-03-12 | 2029-04-01 | 15
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NJF-C2050 | Install access control and intercom - Al Jouf | CON.NJF.INS | Construction | NJF | MS5 | 20% |  |  | 0.069207 |  | 47377 |  | MS5 Installation 20% x station price share 5.52% ¦ Installation key 10% x (1 - civil share 30.8%) | Annex 3 equipment sections A1-A5 (installation share) | 106 |  | 2029-03-18 | 2029-04-03 | 13
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | NJF-T1010 | Pre-commissioning and loop checks - Al Jouf | COM.NJF.TST | Commissioning and handover | NJF | MS6 | 10% |  |  | 0.4 |  | 136914 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.52% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 159 |  | 2029-05-01 | 2029-05-07 | 5
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | NJF-T1020 | Site acceptance test (SAT) and commissioning - Al Jouf | COM.NJF.TST | Commissioning and handover | NJF | MS6 | 10% |  |  | 0.6 |  | 205371 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.52% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 212 |  | 2029-05-08 | 2029-05-17 | 8
SH-TRN | Training (per railway, allocated) | NJF-T2010 | Operator and maintenance training - Al Jouf | COM.NJF.TRN | Commissioning and handover | NJF | MS7 | 10% |  |  | 0.15 |  | 51343 |  | MS7 Final acceptance and handover 10% x station price share 5.52% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 106 |  | 2029-05-20 | 2029-05-31 | 10
A1-A5 | A1 to A5 equipment sections: trial operation share | NJF-T2020 | Trial operation (maximum 45 days) - Al Jouf | COM.NJF.TOA | Commissioning and handover | NJF | MS7 | 10% |  |  | 0.35 |  | 119800 |  | MS7 Final acceptance and handover 10% x station price share 5.52% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 159 |  | 2029-05-20 | 2029-06-28 | 30
A1-A5 | A1 to A5 equipment sections: handover share | NJF-T3010 | Taking-over application, SAR review and handover - Al Jouf | COM.NJF.TOA | Commissioning and handover | NJF | MS7 | 10% |  |  | 0.3 |  | 102685 |  | MS7 Final acceptance and handover 10% x station price share 5.52% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 159 |  | 2029-07-01 | 2029-07-30 | 22
SH-DES | Design and engineering package (per railway, allocated to the station) | NQR-E1010 | Survey: submittal of site survey and as-found report - Al Qurayyat | ENG.NQR.SRV.SUB | Engineering | NQR | MS2 | 10% |  |  | 0.069 |  | 23453 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 6.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 30 |  | 2028-08-02 | 2028-08-13 | 8
SH-DES | Design and engineering package (per railway, allocated to the station) | NQR-E1020 | Survey: SAR approval of survey report - Al Qurayyat | ENG.NQR.SRV.APR | Engineering | NQR | MS3 | 10% |  |  | 0.05 |  | 16995 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 32 |  | 2028-08-14 | 2028-09-03 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NQR-E1030 | Concept design: submittal - Al Qurayyat | ENG.NQR.CNC.SUB | Engineering | NQR | MS2 | 10% |  |  | 0.098 |  | 33309 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 9.8% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 25 |  | 2028-08-14 | 2028-08-27 | 10
SH-DES | Design and engineering package (per railway, allocated to the station) | NQR-E1040 | Concept design: SAR review and approval - Al Qurayyat | ENG.NQR.CNC.APR | Engineering | NQR | MS3 | 10% |  |  | 0.1 |  | 33989 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 10.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 37 |  | 2028-08-28 | 2028-09-17 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NQR-E1050 | Preliminary design: submittal - Al Qurayyat | ENG.NQR.PRE.SUB | Engineering | NQR | MS2 | 10% |  |  | 0.196 |  | 66619 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 57 |  | 2028-08-28 | 2028-09-18 | 16
SH-DES | Design and engineering package (per railway, allocated to the station) | NQR-E1060 | Preliminary design: SAR review and approval - Al Qurayyat | ENG.NQR.PRE.APR | Engineering | NQR | MS3 | 10% |  |  | 0.2 |  | 67978 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 54 |  | 2028-09-19 | 2028-10-09 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NQR-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Al Qurayyat | ENG.NQR.DET.SUB | Engineering | NQR | MS2 | 10% |  |  | 0.392 |  | 133238 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 39.2% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 118 |  | 2028-09-19 | 2028-10-24 | 26
SH-DES | Design and engineering package (per railway, allocated to the station) | NQR-E1080 | Detailed design: SAR review and approval - Al Qurayyat | ENG.NQR.DET.APR | Engineering | NQR | MS3 | 10% |  |  | 0.4 |  | 135957 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 40.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 68 |  | 2028-10-25 | 2028-11-14 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NQR-E1090 | IFC and shop drawings: submittal - Al Qurayyat | ENG.NQR.IFC.SUB | Engineering | NQR | MS2 | 10% |  |  | 0.196 |  | 66619 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 19.6% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 50 |  | 2028-10-25 | 2028-11-09 | 12
SH-DES | Design and engineering package (per railway, allocated to the station) | NQR-E1100 | IFC and shop drawings: SAR approval and release - Al Qurayyat | ENG.NQR.IFC.APR | Engineering | NQR | MS3 | 10% |  |  | 0.2 |  | 67978 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 20.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 62 |  | 2028-11-12 | 2028-11-30 | 15
SH-DES | Design and engineering package (per railway, allocated to the station) | NQR-E1110 | HCIS Stage 3 and 4 documents: preparation - Al Qurayyat | ENG.NQR.HCS.SUB | Engineering | NQR | MS2 | 10% |  |  | 0.049 |  | 16655 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 4.9% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 24 |  | 2028-10-03 | 2028-11-09 | 28
SH-DES | Design and engineering package (per railway, allocated to the station) | NQR-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Al Qurayyat | ENG.NQR.HCS.APR | Engineering | NQR | MS3 | 10% |  |  | 0.05 |  | 16995 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 5.0% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 13 |  | 2028-11-12 | 2028-11-30 | 15
SH-DES, SH-TRN | Design and engineering package (per railway, allocated to the station) and Training (per railway, allocated): documentation and training share | NQR-E1130 | As-built and O&M documentation: submittal - Al Qurayyat | ENG.NQR.ASB.SUB | Engineering | NQR | MS7 | 10% |  |  | 0.15 |  | 50984 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 40 |  | 2029-06-14 | 2029-07-23 | 28
SH-DES | Design and engineering package (per railway, allocated to the station): documentation share | NQR-E1140 | As-built and O&M documentation: SAR review and approval - Al Qurayyat | ENG.NQR.ASB.APR | Engineering | NQR | MS7 | 10% |  |  | 0.05 |  | 16995 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 5% | Annex 3 documentation share | 22 |  | 2029-07-24 | 2029-08-13 | 15
- | No BOQ cost: administrative or review step with no payment milestone | NQR-X1010 | Enabling works: site preparation, setting out, temporary works and utilities clearance - Al Qurayyat | CON.NQR.ENA | Construction | NQR | MS5 | 20% |  |  | 0.012404 |  | 8432 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 4% (enabling: site preparation) | Annex 3 A6 Civil works (SAR 745,743) | 53 |  | 2028-12-03 | 2028-12-07 | 5
- | No BOQ cost: administrative or review step with no payment milestone | NQR-X1020 | Enabling works: cable routes, duct-bank and cabinet plinth preparation - Al Qurayyat | CON.NQR.ENA | Construction | NQR | MS5 | 20% |  |  | 0.018606 |  | 12648 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 6% (enabling: routes, ducts, plinths) | Annex 3 A6 Civil works (SAR 745,743) | 79 |  | 2028-12-10 | 2028-12-21 | 10
A1 | A1 CCTV system | NQR-P1010 | Manufacture CCTV cameras and analytics - Al Qurayyat | PRO.NQR.CCT | Procurement | NQR | MS4 | 20% |  |  | 0.15324 |  | 104169 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 20.4% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 338,989) | 258 |  | 2028-12-03 | 2029-02-05 | 47
A2 | A2 Video management and video wall | NQR-P1020 | Manufacture video management servers, storage and video wall - Al Qurayyat | PRO.NQR.VMS | Procurement | NQR | MS4 | 20% |  |  | 0.16238 |  | 110385 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 21.7% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 359,215) | 273 |  | 2028-12-03 | 2029-02-05 | 47
A3 | A3 Access control and intercom | NQR-P1030 | Manufacture access control and intercom equipment - Al Qurayyat | PRO.NQR.ACC | Procurement | NQR | MS4 | 20% |  |  | 0.019928 |  | 13547 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 2.7% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 34 |  | 2028-12-03 | 2029-02-05 | 47
A4, A5 | A4 UPS and A5 Poles, cabinets and network | NQR-P1040 | Manufacture UPS, network switches and field cabinets - Al Qurayyat | PRO.NQR.UPN | Procurement | NQR | MS4 | 20% |  |  | 0.41445 |  | 281736 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 55.3% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 916,830) | 698 |  | 2028-12-03 | 2029-02-05 | 47
SH-FAT | Factory acceptance test (per railway, allocated) | NQR-P1050 | Factory acceptance test at vendor premises - Al Qurayyat | PRO.NQR.LOG | Procurement | NQR | MS4 | 20% |  |  | 0.05 |  | 33989 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 211 |  | 2029-02-06 | 2029-02-27 | 10
A1-A5 | A1 to A5 equipment sections: logistics (shipping, customs, delivery) share | NQR-P1060 | Shipping and customs clearance - Al Qurayyat | PRO.NQR.LOG | Procurement | NQR | MS4 | 20% |  |  | 0.15 |  | 101967 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 421 |  | 2029-02-28 | 2029-03-29 | 22
SH-SPR | Commissioning spares (per railway, allocated) | NQR-P1070 | Delivery to station and receiving inspection - Al Qurayyat | PRO.NQR.LOG | Procurement | NQR | MS4 | 20% |  |  | 0.05 |  | 33989 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 211 |  | 2029-04-01 | 2029-04-05 | 5
A6 | A6 Civil works | NQR-C1010 | Civil: platform trenches and duct banks - Al Qurayyat | CON.NQR.CIV | Construction | NQR | MS5 | 20% |  |  | 0.15505 |  | 105400 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 50% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 745,743) | 342 |  | 2028-12-24 | 2029-03-20 | 57
A6 | A6 Civil works | NQR-C1020 | Civil: camera and ALPR pole foundations and poles - Al Qurayyat | CON.NQR.CIV | Construction | NQR | MS5 | 20% |  |  | 0.12404 |  | 84320 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 40% (poles) | Annex 3 A6 Civil works (SAR 745,743) | 263 |  | 2029-02-20 | 2029-05-01 | 45
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NQR-C2010 | Install UPS, network switches and field cabinets - Al Qurayyat | CON.NQR.INS | Construction | NQR | MS5 | 20% |  |  | 0.13798 |  | 93797 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 20% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 158 |  | 2029-04-08 | 2029-05-01 | 13
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NQR-C2020 | Cabling and termination (power, fibre, data) - Al Qurayyat | CON.NQR.INS | Construction | NQR | MS5 | 20% |  |  | 0.20697 |  | 140695 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 30% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 316 |  | 2029-04-12 | 2029-05-20 | 22
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NQR-C2030 | Install and aim CCTV cameras - Al Qurayyat | CON.NQR.INS | Construction | NQR | MS5 | 20% |  |  | 0.17248 |  | 117246 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 25% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 263 |  | 2029-05-21 | 2029-06-13 | 18
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NQR-C2040 | Install video management, video wall and control-room equipment - Al Qurayyat | CON.NQR.INS | Construction | NQR | MS5 | 20% |  |  | 0.10349 |  | 70348 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 15% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 158 |  | 2029-05-02 | 2029-05-22 | 15
A1-A5 | A1 to A5 equipment sections: installation share (works included in unit prices) | NQR-C2050 | Install access control and intercom - Al Qurayyat | CON.NQR.INS | Construction | NQR | MS5 | 20% |  |  | 0.06899 |  | 46898 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 10% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 105 |  | 2029-05-08 | 2029-05-24 | 13
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | NQR-T1010 | Pre-commissioning and loop checks - Al Qurayyat | COM.NQR.TST | Commissioning and handover | NQR | MS6 | 10% |  |  | 0.4 |  | 135957 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.48% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 158 |  | 2029-06-14 | 2029-06-20 | 5
A1-A5 | A1 to A5 equipment sections: testing and commissioning share | NQR-T1020 | Site acceptance test (SAT) and commissioning - Al Qurayyat | COM.NQR.TST | Commissioning and handover | NQR | MS6 | 10% |  |  | 0.6 |  | 203935 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.48% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 211 |  | 2029-06-21 | 2029-07-02 | 8
SH-TRN | Training (per railway, allocated) | NQR-T2010 | Operator and maintenance training - Al Qurayyat | COM.NQR.TRN | Commissioning and handover | NQR | MS7 | 10% |  |  | 0.15 |  | 50984 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 105 |  | 2029-07-03 | 2029-07-16 | 10
A1-A5 | A1 to A5 equipment sections: trial operation share | NQR-T2020 | Trial operation (maximum 45 days) - Al Qurayyat | COM.NQR.TOA | Commissioning and handover | NQR | MS7 | 10% |  |  | 0.35 |  | 118962 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 158 |  | 2029-07-03 | 2029-08-13 | 30
A1-A5 | A1 to A5 equipment sections: handover share | NQR-T3010 | Taking-over application, SAR review and handover - Al Qurayyat | COM.NQR.TOA | Commissioning and handover | NQR | MS7 | 10% |  |  | 0.3 |  | 101967 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 158 |  | 2029-08-14 | 2029-09-12 | 22
Total

## Distribution_Keys
Distribution keys (cost within each payment milestone, and progress weights)
Milestone | Activity template | Key | Basis
MS2 | Survey, concept, preliminary, detailed, IFC, HCIS submittals | 5 / 10 / 20 / 40 / 20 / 5 % of 98% | Survey (including the permit follow-up) carries 7% of the MS2 bucket; design effort split by stage; the railway design and engineering package sits inside the station price
MS3 | Approval activities of the same six stages | 5 / 10 / 20 / 40 / 20 / 5 % | Mirror of the submittal key. Every SAR review is 21 days (15 working days)
MS4 | Manufacture CCTV, VMS, access control, UPS and network | 75% split by BOQ section share | A1, A2, A3 and A4+A5 shares of the station equipment value
MS4 | FAT / shipping and customs / delivery and receiving | 5 / 15 / 5 % | Fixed keys; spares and logistics sit inside delivery
MS5 | Enabling works / civil trenches and duct banks / poles and foundations | 4 + 6 / 50 / 40 % of the A6 share | A6 civil works share of station hardware; enabling works carved from the civil line
MS5 | Install cabinets / cabling / CCTV / VMS / access control | 20 / 30 / 25 / 15 / 10 % of (1 - A6 share) | Installation is included in the unit prices (Annex 3 works included)
MS6 | Pre-commissioning / SAT | 40 / 60 % | Fixed keys. Riyadh (Thumamah): 97% of the keys, 3% to the mock-up approval (no separate Annex 3 item)
MS7 | As-built submittal / approval / training / trial operation / handover | 15 / 5 / 15 / 35 / 30 % | Fixed keys
MS1 | Performance security / initial baseline / site establishment / mobilization submittals | 15 / 10 / 45 / 30 % | Project level, 20% of the total price
EPC phase | Component | Weight (% of station progress) | Basis
Engineering | Survey 8, concept 10, preliminary 18, detailed 30, IFC 18, HCIS 6, as-built 10 (of 12%); each stage split submittal / approval by duration | 12 | Typical EPC effort weighting for design
Procurement | Manufacture 24 (split by BOQ package share), FAT 4, shipping 8, delivery 4 | 40 | Procurement carries the largest share of a supply-led security contract
Construction | Enabling works 2.5, trenches 6.5, poles 5, cabinets 3, cabling 6, CCTV 5, VMS 3, access 2 | 33 | Site works
Commissioning and handover | Pre-commissioning 3, SAT 4, training 2, trial operation 3, handover 3 | 15 | Testing, trial and acceptance
Total stations |  |  | Station weights sum to 100%
Project level | Mobilization and baseline 2.7% and closeout pack 1.3% of the whole project | 4 | Stations carry 96% of the project, each station weighted by its BOQ price share

## S_Curve
S-curve: cost (contract payment conditions) against progress (fair EPC distribution), spread linearly over each activity
Month | Cost in month (SAR) | Cumulative cost (SAR) | Cumulative cost % | Progress in month % | Cumulative progress %
2026-11-01 | 10056396.47 |  |  | 1.835%
2026-12-01 | 2343599.53 |  |  | 0.3651%
2027-01-01 | 262431.1381 |  |  | 0.701%
2027-02-01 | 728474.6632 |  |  | 0.7463%
2027-03-01 | 1149268.961 |  |  | 0.9865%
2027-04-01 | 1744434.8544 |  |  | 1.375%
2027-05-01 | 1442176.5541 |  |  | 2.705%
2027-06-01 | 1684819.1217 |  |  | 3.651%
2027-07-01 | 1309023.6995 |  |  | 4.2%
2027-08-01 | 1682555.4871 |  |  | 5.262%
2027-09-01 | 1807538.6881 |  |  | 4.574%
2027-10-01 | 1709704.9992 |  |  | 3.86%
2027-11-01 | 2195829.2076 |  |  | 3.89%
2027-12-01 | 2036383.8284 |  |  | 4.598%
2028-01-01 | 2321339.0341 |  |  | 4.739%
2028-02-01 | 1753077.8532 |  |  | 3.563%
2028-03-01 | 2801838.1781 |  |  | 4.777%
2028-04-01 | 3549570.8646 |  |  | 4.825%
2028-05-01 | 2433062.0511 |  |  | 4.451%
2028-06-01 | 2658079.1043 |  |  | 4.994%
2028-07-01 | 2078816.2587 |  |  | 4.808%
2028-08-01 | 1769603.582 |  |  | 3.932%
2028-09-01 | 1167986.9509 |  |  | 2.733%
2028-10-01 | 1551041.2554 |  |  | 3.272%
2028-11-01 | 1780674.5649 |  |  | 3.439%
2028-12-01 | 1461766.1223 |  |  | 3.099%
2029-01-01 | 1856103.6544 |  |  | 3.257%
2029-02-01 | 1182733.6612 |  |  | 2.071%
2029-03-01 | 990317.0319 |  |  | 1.972%
2029-04-01 | 671679.4717 |  |  | 1.373%
2029-05-01 | 872432.0994 |  |  | 1.366%
2029-06-01 | 473709.7381 |  |  | 0.5988%
2029-07-01 | 325678.7214 |  |  | 0.4604%
2029-08-01 | 106138.8273 |  |  | 0.154%
2029-09-01 | 41713.7727 |  |  | 1.366%

## Resources
Resource ID | Name | Type | Unit | Price per unit | Meaning | How P6 uses it
COST-SAR | Contract cost (BOQ x payment milestones) | Material | SAR | 0 | Contract cost of the activity in SAR from the payment conditions applied to the BOQ station value (column N of BOQ_Mapping) | Quantity carrier. Price 0, so it adds no budget cost. Set the price to 1 (and PROG-WT to 0) to see the contract-condition cost curve instead.
PROG-WT | Progress weight (fair EPC distribution, SAR value) | Material | SAR | 1 | Progress share x SAR 62,000,000 (100,000 points x SAR 620). Fair EPC distribution (see Distribution_Keys) | Price 1, so budgeted cost = progress value in SAR. Activity % complete type is Physical, so earned value = physical % x this budget, and the cost and schedule performance indexes are measured in SAR on the progress distribution.

## Activity_Codes
Code type | Code value | Description | Activities
Area | EWR | EWR | 164
Area | HHR | HHR | 164
Area | NSR | NSR | 248
Area | PRJ | Project level | 15
Discipline | ACC | Access control and intercom | 28
Discipline | CCTV | CCTV system | 42
Discipline | CIVIL | Civil works | 56
Discipline | DOCS | Design documentation | 224
Discipline | PM | Project management and logistics | 85
Discipline | TC | Testing, commissioning and handover | 100
Discipline | UPSNET | UPS, network and cabinets | 28
Discipline | VMS | Video management and wall | 28
EPC phase | COM | Commissioning and handover | 71
EPC phase | CON | Construction | 126
EPC phase | ENG | Engineering | 196
EPC phase | MOB | Mobilization | 6
EPC phase | MS | Milestone | 91
EPC phase | PMG | Project management | 3
EPC phase | PRO | Procurement | 98
Payment milestone | - | Not a payment milestone | 10
Payment milestone | MS1 | MS1 Mobilization | 6
Payment milestone | MS2 | MS2 Engineering submittal | 98
Payment milestone | MS3 | MS3 SAR approval of engineering | 98
Payment milestone | MS4 | MS4 Material delivery | 112
Payment milestone | MS5 | MS5 Installation | 140
Payment milestone | MS6 | MS6 Testing and commissioning (SAT) | 43
Payment milestone | MS7 | MS7 Final acceptance and handover | 84
Programme phase | COM | Testing, commissioning and handover | 99
Programme phase | CON | Construction and installation | 98
Programme phase | DES | Design including survey (months 3-6) | 168
Programme phase | ENA | Enabling works | 28
Programme phase | MOB | Mobilization and survey permit (months 1-2) | 6
Programme phase | MS | Milestones | 91
Programme phase | PMG | Project management and closeout | 3
Programme phase | PRO | Procurement and supply | 98
Priority | Priority 1 | Priority 1 - Makkah and Riyadh (Thumamah) | 84
Priority | Priority 2 | Priority 2 - Riyadh (Malaz) | 41
Priority | Standard | Standard | 466
Railway | ALL | All railways | 15
Railway | EWR | EWR | 164
Railway | HHR | HHR | 164
Railway | NSR | NSR | 248
Responsibility | ETECHS | ETECHS | 343
Responsibility | SAR | SAR | 164
Responsibility | SAR/HCIS | SAR and HCIS | 14
Responsibility | Vendor | Vendor | 70
Design stage | - | Not a design stage | 395
Design stage | As-built | As-built and O&M | 28
Design stage | Concept | Concept design | 28
Design stage | Detailed | Detailed design | 28
Design stage | HCIS | HCIS documentation | 28
Design stage | IFC | IFC and shop drawings | 28
Design stage | Preliminary | Preliminary design | 28
Design stage | Survey | Site survey | 28
Station | EAB | Abqaiq (EWR) | 41
Station | EDM | Dammam (EWR) | 41
Station | EHF | Hufuf (EWR) | 41
Station | ERY | Riyadh (Malaz) (EWR) | 41
Station | HJD | Jeddah (HHR) | 41
Station | HKA | KAEC (HHR) | 41
Station | HMD | Madinah (HHR) | 41
Station | HMK | Makkah (HHR) | 41
Station | NHL | Hail (NSR) | 41
Station | NJF | Al Jouf (NSR) | 41
Station | NMJ | Al Majma'ah (NSR) | 41
Station | NQR | Al Qurayyat (NSR) | 41
Station | NQS | Al Qassim (NSR) | 41
Station | NRY | Riyadh (Thumamah) (NSR) | 43
Station | PRJ | Project level | 15
Submittal or approval | - | Not applicable | 388
Submittal or approval | Approval | Approval | 102
Submittal or approval | Submittal | Submittal | 101

## WBS
WBS code | Name | Level | Parent
0580 | 0580-Security Technology Salutation after eliminating Passenger Checking Roles | 1
PM | Project Management and Mobilization | 2 | 0580
ENG | Engineering | 2 | 0580
PRO | Procurement | 2 | 0580
CON | Construction | 2 | 0580
COM | Commissioning and Handover | 2 | 0580
PM.MOB | Mobilization and baseline programme | 3 | PM
PM.MST | Contract milestones | 3 | PM
PM.CLO | Closeout | 3 | PM
ENG.NRY | Riyadh (Thumamah) (NSR) | 3 | ENG
PRO.NRY | Riyadh (Thumamah) (NSR) | 3 | PRO
CON.NRY | Riyadh (Thumamah) (NSR) | 3 | CON
COM.NRY | Riyadh (Thumamah) (NSR) | 3 | COM
ENG.NRY.SRV | Site survey and as-found verification | 4 | ENG.NRY
ENG.NRY.SRV.SUB | Submittal | 5 | ENG.NRY.SRV
ENG.NRY.SRV.APR | Approval | 5 | ENG.NRY.SRV
ENG.NRY.CNC | Concept design | 4 | ENG.NRY
ENG.NRY.CNC.SUB | Submittal | 5 | ENG.NRY.CNC
ENG.NRY.CNC.APR | Approval | 5 | ENG.NRY.CNC
ENG.NRY.PRE | Preliminary (schematic) design | 4 | ENG.NRY
ENG.NRY.PRE.SUB | Submittal | 5 | ENG.NRY.PRE
ENG.NRY.PRE.APR | Approval | 5 | ENG.NRY.PRE
ENG.NRY.DET | Detailed design | 4 | ENG.NRY
ENG.NRY.DET.SUB | Submittal | 5 | ENG.NRY.DET
ENG.NRY.DET.APR | Approval | 5 | ENG.NRY.DET
ENG.NRY.IFC | IFC and shop drawings | 4 | ENG.NRY
ENG.NRY.IFC.SUB | Submittal | 5 | ENG.NRY.IFC
ENG.NRY.IFC.APR | Approval | 5 | ENG.NRY.IFC
ENG.NRY.HCS | HCIS documentation (Stage 3 and 4) | 4 | ENG.NRY
ENG.NRY.HCS.SUB | Submittal | 5 | ENG.NRY.HCS
ENG.NRY.HCS.APR | Approval | 5 | ENG.NRY.HCS
ENG.NRY.ASB | As-built and O&M documentation | 4 | ENG.NRY
ENG.NRY.ASB.SUB | Submittal | 5 | ENG.NRY.ASB
ENG.NRY.ASB.APR | Approval | 5 | ENG.NRY.ASB
PRO.NRY.CCT | CCTV system | 4 | PRO.NRY
PRO.NRY.VMS | Video management and video wall | 4 | PRO.NRY
PRO.NRY.ACC | Access control and intercom | 4 | PRO.NRY
PRO.NRY.UPN | UPS, network and cabinets | 4 | PRO.NRY
PRO.NRY.LOG | FAT and logistics | 4 | PRO.NRY
CON.NRY.ENA | Enabling works | 4 | CON.NRY
CON.NRY.CIV | Civil works | 4 | CON.NRY
CON.NRY.INS | Installation | 4 | CON.NRY
COM.NRY.TST | Testing and commissioning | 4 | COM.NRY
COM.NRY.TRN | Training | 4 | COM.NRY
COM.NRY.TOA | Trial operation and acceptance | 4 | COM.NRY
COM.NRY.MOK | Mock-up approval | 4 | COM.NRY
ENG.HMK | Makkah (HHR) | 3 | ENG
PRO.HMK | Makkah (HHR) | 3 | PRO
CON.HMK | Makkah (HHR) | 3 | CON
COM.HMK | Makkah (HHR) | 3 | COM
ENG.HMK.SRV | Site survey and as-found verification | 4 | ENG.HMK
ENG.HMK.SRV.SUB | Submittal | 5 | ENG.HMK.SRV
ENG.HMK.SRV.APR | Approval | 5 | ENG.HMK.SRV
ENG.HMK.CNC | Concept design | 4 | ENG.HMK
ENG.HMK.CNC.SUB | Submittal | 5 | ENG.HMK.CNC
ENG.HMK.CNC.APR | Approval | 5 | ENG.HMK.CNC
ENG.HMK.PRE | Preliminary (schematic) design | 4 | ENG.HMK
ENG.HMK.PRE.SUB | Submittal | 5 | ENG.HMK.PRE
ENG.HMK.PRE.APR | Approval | 5 | ENG.HMK.PRE
ENG.HMK.DET | Detailed design | 4 | ENG.HMK
ENG.HMK.DET.SUB | Submittal | 5 | ENG.HMK.DET
ENG.HMK.DET.APR | Approval | 5 | ENG.HMK.DET
ENG.HMK.IFC | IFC and shop drawings | 4 | ENG.HMK
ENG.HMK.IFC.SUB | Submittal | 5 | ENG.HMK.IFC
ENG.HMK.IFC.APR | Approval | 5 | ENG.HMK.IFC
ENG.HMK.HCS | HCIS documentation (Stage 3 and 4) | 4 | ENG.HMK
ENG.HMK.HCS.SUB | Submittal | 5 | ENG.HMK.HCS
ENG.HMK.HCS.APR | Approval | 5 | ENG.HMK.HCS
ENG.HMK.ASB | As-built and O&M documentation | 4 | ENG.HMK
ENG.HMK.ASB.SUB | Submittal | 5 | ENG.HMK.ASB
ENG.HMK.ASB.APR | Approval | 5 | ENG.HMK.ASB
PRO.HMK.CCT | CCTV system | 4 | PRO.HMK
PRO.HMK.VMS | Video management and video wall | 4 | PRO.HMK
PRO.HMK.ACC | Access control and intercom | 4 | PRO.HMK
PRO.HMK.UPN | UPS, network and cabinets | 4 | PRO.HMK
PRO.HMK.LOG | FAT and logistics | 4 | PRO.HMK
CON.HMK.ENA | Enabling works | 4 | CON.HMK
CON.HMK.CIV | Civil works | 4 | CON.HMK
CON.HMK.INS | Installation | 4 | CON.HMK
COM.HMK.TST | Testing and commissioning | 4 | COM.HMK
COM.HMK.TRN | Training | 4 | COM.HMK
COM.HMK.TOA | Trial operation and acceptance | 4 | COM.HMK
ENG.ERY | Riyadh (Malaz) (EWR) | 3 | ENG
PRO.ERY | Riyadh (Malaz) (EWR) | 3 | PRO
CON.ERY | Riyadh (Malaz) (EWR) | 3 | CON
COM.ERY | Riyadh (Malaz) (EWR) | 3 | COM
ENG.ERY.SRV | Site survey and as-found verification | 4 | ENG.ERY
ENG.ERY.SRV.SUB | Submittal | 5 | ENG.ERY.SRV
ENG.ERY.SRV.APR | Approval | 5 | ENG.ERY.SRV
ENG.ERY.CNC | Concept design | 4 | ENG.ERY
ENG.ERY.CNC.SUB | Submittal | 5 | ENG.ERY.CNC
ENG.ERY.CNC.APR | Approval | 5 | ENG.ERY.CNC
ENG.ERY.PRE | Preliminary (schematic) design | 4 | ENG.ERY
ENG.ERY.PRE.SUB | Submittal | 5 | ENG.ERY.PRE
ENG.ERY.PRE.APR | Approval | 5 | ENG.ERY.PRE
ENG.ERY.DET | Detailed design | 4 | ENG.ERY
ENG.ERY.DET.SUB | Submittal | 5 | ENG.ERY.DET
ENG.ERY.DET.APR | Approval | 5 | ENG.ERY.DET
ENG.ERY.IFC | IFC and shop drawings | 4 | ENG.ERY
ENG.ERY.IFC.SUB | Submittal | 5 | ENG.ERY.IFC
ENG.ERY.IFC.APR | Approval | 5 | ENG.ERY.IFC
ENG.ERY.HCS | HCIS documentation (Stage 3 and 4) | 4 | ENG.ERY
ENG.ERY.HCS.SUB | Submittal | 5 | ENG.ERY.HCS
ENG.ERY.HCS.APR | Approval | 5 | ENG.ERY.HCS
ENG.ERY.ASB | As-built and O&M documentation | 4 | ENG.ERY
ENG.ERY.ASB.SUB | Submittal | 5 | ENG.ERY.ASB
ENG.ERY.ASB.APR | Approval | 5 | ENG.ERY.ASB
PRO.ERY.CCT | CCTV system | 4 | PRO.ERY
PRO.ERY.VMS | Video management and video wall | 4 | PRO.ERY
PRO.ERY.ACC | Access control and intercom | 4 | PRO.ERY
PRO.ERY.UPN | UPS, network and cabinets | 4 | PRO.ERY
PRO.ERY.LOG | FAT and logistics | 4 | PRO.ERY
CON.ERY.ENA | Enabling works | 4 | CON.ERY
CON.ERY.CIV | Civil works | 4 | CON.ERY
CON.ERY.INS | Installation | 4 | CON.ERY
COM.ERY.TST | Testing and commissioning | 4 | COM.ERY
COM.ERY.TRN | Training | 4 | COM.ERY
COM.ERY.TOA | Trial operation and acceptance | 4 | COM.ERY
ENG.HJD | Jeddah (HHR) | 3 | ENG
PRO.HJD | Jeddah (HHR) | 3 | PRO
CON.HJD | Jeddah (HHR) | 3 | CON
COM.HJD | Jeddah (HHR) | 3 | COM
ENG.HJD.SRV | Site survey and as-found verification | 4 | ENG.HJD
ENG.HJD.SRV.SUB | Submittal | 5 | ENG.HJD.SRV
ENG.HJD.SRV.APR | Approval | 5 | ENG.HJD.SRV
ENG.HJD.CNC | Concept design | 4 | ENG.HJD
ENG.HJD.CNC.SUB | Submittal | 5 | ENG.HJD.CNC
ENG.HJD.CNC.APR | Approval | 5 | ENG.HJD.CNC
ENG.HJD.PRE | Preliminary (schematic) design | 4 | ENG.HJD
ENG.HJD.PRE.SUB | Submittal | 5 | ENG.HJD.PRE
ENG.HJD.PRE.APR | Approval | 5 | ENG.HJD.PRE
ENG.HJD.DET | Detailed design | 4 | ENG.HJD
ENG.HJD.DET.SUB | Submittal | 5 | ENG.HJD.DET
ENG.HJD.DET.APR | Approval | 5 | ENG.HJD.DET
ENG.HJD.IFC | IFC and shop drawings | 4 | ENG.HJD
ENG.HJD.IFC.SUB | Submittal | 5 | ENG.HJD.IFC
ENG.HJD.IFC.APR | Approval | 5 | ENG.HJD.IFC
ENG.HJD.HCS | HCIS documentation (Stage 3 and 4) | 4 | ENG.HJD
ENG.HJD.HCS.SUB | Submittal | 5 | ENG.HJD.HCS
ENG.HJD.HCS.APR | Approval | 5 | ENG.HJD.HCS
ENG.HJD.ASB | As-built and O&M documentation | 4 | ENG.HJD
ENG.HJD.ASB.SUB | Submittal | 5 | ENG.HJD.ASB
ENG.HJD.ASB.APR | Approval | 5 | ENG.HJD.ASB
PRO.HJD.CCT | CCTV system | 4 | PRO.HJD
PRO.HJD.VMS | Video management and video wall | 4 | PRO.HJD
PRO.HJD.ACC | Access control and intercom | 4 | PRO.HJD
PRO.HJD.UPN | UPS, network and cabinets | 4 | PRO.HJD
PRO.HJD.LOG | FAT and logistics | 4 | PRO.HJD
CON.HJD.ENA | Enabling works | 4 | CON.HJD
CON.HJD.CIV | Civil works | 4 | CON.HJD
CON.HJD.INS | Installation | 4 | CON.HJD
COM.HJD.TST | Testing and commissioning | 4 | COM.HJD
COM.HJD.TRN | Training | 4 | COM.HJD
COM.HJD.TOA | Trial operation and acceptance | 4 | COM.HJD
ENG.EDM | Dammam (EWR) | 3 | ENG
PRO.EDM | Dammam (EWR) | 3 | PRO
CON.EDM | Dammam (EWR) | 3 | CON
COM.EDM | Dammam (EWR) | 3 | COM
ENG.EDM.SRV | Site survey and as-found verification | 4 | ENG.EDM
ENG.EDM.SRV.SUB | Submittal | 5 | ENG.EDM.SRV
ENG.EDM.SRV.APR | Approval | 5 | ENG.EDM.SRV
ENG.EDM.CNC | Concept design | 4 | ENG.EDM
ENG.EDM.CNC.SUB | Submittal | 5 | ENG.EDM.CNC
ENG.EDM.CNC.APR | Approval | 5 | ENG.EDM.CNC
ENG.EDM.PRE | Preliminary (schematic) design | 4 | ENG.EDM
ENG.EDM.PRE.SUB | Submittal | 5 | ENG.EDM.PRE
ENG.EDM.PRE.APR | Approval | 5 | ENG.EDM.PRE
ENG.EDM.DET | Detailed design | 4 | ENG.EDM
ENG.EDM.DET.SUB | Submittal | 5 | ENG.EDM.DET
ENG.EDM.DET.APR | Approval | 5 | ENG.EDM.DET
ENG.EDM.IFC | IFC and shop drawings | 4 | ENG.EDM
ENG.EDM.IFC.SUB | Submittal | 5 | ENG.EDM.IFC
ENG.EDM.IFC.APR | Approval | 5 | ENG.EDM.IFC
ENG.EDM.HCS | HCIS documentation (Stage 3 and 4) | 4 | ENG.EDM
ENG.EDM.HCS.SUB | Submittal | 5 | ENG.EDM.HCS
ENG.EDM.HCS.APR | Approval | 5 | ENG.EDM.HCS
ENG.EDM.ASB | As-built and O&M documentation | 4 | ENG.EDM
ENG.EDM.ASB.SUB | Submittal | 5 | ENG.EDM.ASB
ENG.EDM.ASB.APR | Approval | 5 | ENG.EDM.ASB
PRO.EDM.CCT | CCTV system | 4 | PRO.EDM
PRO.EDM.VMS | Video management and video wall | 4 | PRO.EDM
PRO.EDM.ACC | Access control and intercom | 4 | PRO.EDM
PRO.EDM.UPN | UPS, network and cabinets | 4 | PRO.EDM
PRO.EDM.LOG | FAT and logistics | 4 | PRO.EDM
CON.EDM.ENA | Enabling works | 4 | CON.EDM
CON.EDM.CIV | Civil works | 4 | CON.EDM
CON.EDM.INS | Installation | 4 | CON.EDM
COM.EDM.TST | Testing and commissioning | 4 | COM.EDM
COM.EDM.TRN | Training | 4 | COM.EDM
COM.EDM.TOA | Trial operation and acceptance | 4 | COM.EDM
ENG.NQS | Al Qassim (NSR) | 3 | ENG
PRO.NQS | Al Qassim (NSR) | 3 | PRO
CON.NQS | Al Qassim (NSR) | 3 | CON
COM.NQS | Al Qassim (NSR) | 3 | COM
ENG.NQS.SRV | Site survey and as-found verification | 4 | ENG.NQS
ENG.NQS.SRV.SUB | Submittal | 5 | ENG.NQS.SRV
ENG.NQS.SRV.APR | Approval | 5 | ENG.NQS.SRV
ENG.NQS.CNC | Concept design | 4 | ENG.NQS
ENG.NQS.CNC.SUB | Submittal | 5 | ENG.NQS.CNC
ENG.NQS.CNC.APR | Approval | 5 | ENG.NQS.CNC
ENG.NQS.PRE | Preliminary (schematic) design | 4 | ENG.NQS
ENG.NQS.PRE.SUB | Submittal | 5 | ENG.NQS.PRE
ENG.NQS.PRE.APR | Approval | 5 | ENG.NQS.PRE
ENG.NQS.DET | Detailed design | 4 | ENG.NQS
ENG.NQS.DET.SUB | Submittal | 5 | ENG.NQS.DET
ENG.NQS.DET.APR | Approval | 5 | ENG.NQS.DET
ENG.NQS.IFC | IFC and shop drawings | 4 | ENG.NQS
ENG.NQS.IFC.SUB | Submittal | 5 | ENG.NQS.IFC
ENG.NQS.IFC.APR | Approval | 5 | ENG.NQS.IFC
ENG.NQS.HCS | HCIS documentation (Stage 3 and 4) | 4 | ENG.NQS
ENG.NQS.HCS.SUB | Submittal | 5 | ENG.NQS.HCS
ENG.NQS.HCS.APR | Approval | 5 | ENG.NQS.HCS
ENG.NQS.ASB | As-built and O&M documentation | 4 | ENG.NQS
ENG.NQS.ASB.SUB | Submittal | 5 | ENG.NQS.ASB
ENG.NQS.ASB.APR | Approval | 5 | ENG.NQS.ASB
PRO.NQS.CCT | CCTV system | 4 | PRO.NQS
PRO.NQS.VMS | Video management and video wall | 4 | PRO.NQS
PRO.NQS.ACC | Access control and intercom | 4 | PRO.NQS
PRO.NQS.UPN | UPS, network and cabinets | 4 | PRO.NQS
PRO.NQS.LOG | FAT and logistics | 4 | PRO.NQS
CON.NQS.ENA | Enabling works | 4 | CON.NQS
CON.NQS.CIV | Civil works | 4 | CON.NQS
CON.NQS.INS | Installation | 4 | CON.NQS
COM.NQS.TST | Testing and commissioning | 4 | COM.NQS
COM.NQS.TRN | Training | 4 | COM.NQS
COM.NQS.TOA | Trial operation and acceptance | 4 | COM.NQS
ENG.EHF | Hufuf (EWR) | 3 | ENG
PRO.EHF | Hufuf (EWR) | 3 | PRO
CON.EHF | Hufuf (EWR) | 3 | CON
COM.EHF | Hufuf (EWR) | 3 | COM
ENG.EHF.SRV | Site survey and as-found verification | 4 | ENG.EHF
ENG.EHF.SRV.SUB | Submittal | 5 | ENG.EHF.SRV
ENG.EHF.SRV.APR | Approval | 5 | ENG.EHF.SRV
ENG.EHF.CNC | Concept design | 4 | ENG.EHF
ENG.EHF.CNC.SUB | Submittal | 5 | ENG.EHF.CNC
ENG.EHF.CNC.APR | Approval | 5 | ENG.EHF.CNC
ENG.EHF.PRE | Preliminary (schematic) design | 4 | ENG.EHF
ENG.EHF.PRE.SUB | Submittal | 5 | ENG.EHF.PRE
ENG.EHF.PRE.APR | Approval | 5 | ENG.EHF.PRE
ENG.EHF.DET | Detailed design | 4 | ENG.EHF
ENG.EHF.DET.SUB | Submittal | 5 | ENG.EHF.DET
ENG.EHF.DET.APR | Approval | 5 | ENG.EHF.DET
ENG.EHF.IFC | IFC and shop drawings | 4 | ENG.EHF
ENG.EHF.IFC.SUB | Submittal | 5 | ENG.EHF.IFC
ENG.EHF.IFC.APR | Approval | 5 | ENG.EHF.IFC
ENG.EHF.HCS | HCIS documentation (Stage 3 and 4) | 4 | ENG.EHF
ENG.EHF.HCS.SUB | Submittal | 5 | ENG.EHF.HCS
ENG.EHF.HCS.APR | Approval | 5 | ENG.EHF.HCS
ENG.EHF.ASB | As-built and O&M documentation | 4 | ENG.EHF
ENG.EHF.ASB.SUB | Submittal | 5 | ENG.EHF.ASB
ENG.EHF.ASB.APR | Approval | 5 | ENG.EHF.ASB
PRO.EHF.CCT | CCTV system | 4 | PRO.EHF
PRO.EHF.VMS | Video management and video wall | 4 | PRO.EHF
PRO.EHF.ACC | Access control and intercom | 4 | PRO.EHF
PRO.EHF.UPN | UPS, network and cabinets | 4 | PRO.EHF
PRO.EHF.LOG | FAT and logistics | 4 | PRO.EHF
CON.EHF.ENA | Enabling works | 4 | CON.EHF
CON.EHF.CIV | Civil works | 4 | CON.EHF
CON.EHF.INS | Installation | 4 | CON.EHF
COM.EHF.TST | Testing and commissioning | 4 | COM.EHF
COM.EHF.TRN | Training | 4 | COM.EHF
COM.EHF.TOA | Trial operation and acceptance | 4 | COM.EHF
ENG.NMJ | Al Majma'ah (NSR) | 3 | ENG
PRO.NMJ | Al Majma'ah (NSR) | 3 | PRO
CON.NMJ | Al Majma'ah (NSR) | 3 | CON
COM.NMJ | Al Majma'ah (NSR) | 3 | COM
ENG.NMJ.SRV | Site survey and as-found verification | 4 | ENG.NMJ
ENG.NMJ.SRV.SUB | Submittal | 5 | ENG.NMJ.SRV
ENG.NMJ.SRV.APR | Approval | 5 | ENG.NMJ.SRV
ENG.NMJ.CNC | Concept design | 4 | ENG.NMJ
ENG.NMJ.CNC.SUB | Submittal | 5 | ENG.NMJ.CNC
ENG.NMJ.CNC.APR | Approval | 5 | ENG.NMJ.CNC
ENG.NMJ.PRE | Preliminary (schematic) design | 4 | ENG.NMJ
ENG.NMJ.PRE.SUB | Submittal | 5 | ENG.NMJ.PRE
ENG.NMJ.PRE.APR | Approval | 5 | ENG.NMJ.PRE
ENG.NMJ.DET | Detailed design | 4 | ENG.NMJ
ENG.NMJ.DET.SUB | Submittal | 5 | ENG.NMJ.DET
ENG.NMJ.DET.APR | Approval | 5 | ENG.NMJ.DET
ENG.NMJ.IFC | IFC and shop drawings | 4 | ENG.NMJ
ENG.NMJ.IFC.SUB | Submittal | 5 | ENG.NMJ.IFC
ENG.NMJ.IFC.APR | Approval | 5 | ENG.NMJ.IFC
ENG.NMJ.HCS | HCIS documentation (Stage 3 and 4) | 4 | ENG.NMJ
ENG.NMJ.HCS.SUB | Submittal | 5 | ENG.NMJ.HCS
ENG.NMJ.HCS.APR | Approval | 5 | ENG.NMJ.HCS
ENG.NMJ.ASB | As-built and O&M documentation | 4 | ENG.NMJ
ENG.NMJ.ASB.SUB | Submittal | 5 | ENG.NMJ.ASB
ENG.NMJ.ASB.APR | Approval | 5 | ENG.NMJ.ASB
PRO.NMJ.CCT | CCTV system | 4 | PRO.NMJ
PRO.NMJ.VMS | Video management and video wall | 4 | PRO.NMJ
PRO.NMJ.ACC | Access control and intercom | 4 | PRO.NMJ
PRO.NMJ.UPN | UPS, network and cabinets | 4 | PRO.NMJ
PRO.NMJ.LOG | FAT and logistics | 4 | PRO.NMJ
CON.NMJ.ENA | Enabling works | 4 | CON.NMJ
CON.NMJ.CIV | Civil works | 4 | CON.NMJ
CON.NMJ.INS | Installation | 4 | CON.NMJ
COM.NMJ.TST | Testing and commissioning | 4 | COM.NMJ
COM.NMJ.TRN | Training | 4 | COM.NMJ
COM.NMJ.TOA | Trial operation and acceptance | 4 | COM.NMJ
ENG.HKA | KAEC (HHR) | 3 | ENG
PRO.HKA | KAEC (HHR) | 3 | PRO
CON.HKA | KAEC (HHR) | 3 | CON
COM.HKA | KAEC (HHR) | 3 | COM
ENG.HKA.SRV | Site survey and as-found verification | 4 | ENG.HKA
ENG.HKA.SRV.SUB | Submittal | 5 | ENG.HKA.SRV
ENG.HKA.SRV.APR | Approval | 5 | ENG.HKA.SRV
ENG.HKA.CNC | Concept design | 4 | ENG.HKA
ENG.HKA.CNC.SUB | Submittal | 5 | ENG.HKA.CNC
ENG.HKA.CNC.APR | Approval | 5 | ENG.HKA.CNC
ENG.HKA.PRE | Preliminary (schematic) design | 4 | ENG.HKA
ENG.HKA.PRE.SUB | Submittal | 5 | ENG.HKA.PRE
ENG.HKA.PRE.APR | Approval | 5 | ENG.HKA.PRE
ENG.HKA.DET | Detailed design | 4 | ENG.HKA
ENG.HKA.DET.SUB | Submittal | 5 | ENG.HKA.DET
ENG.HKA.DET.APR | Approval | 5 | ENG.HKA.DET
ENG.HKA.IFC | IFC and shop drawings | 4 | ENG.HKA
ENG.HKA.IFC.SUB | Submittal | 5 | ENG.HKA.IFC
ENG.HKA.IFC.APR | Approval | 5 | ENG.HKA.IFC
ENG.HKA.HCS | HCIS documentation (Stage 3 and 4) | 4 | ENG.HKA
ENG.HKA.HCS.SUB | Submittal | 5 | ENG.HKA.HCS
ENG.HKA.HCS.APR | Approval | 5 | ENG.HKA.HCS
ENG.HKA.ASB | As-built and O&M documentation | 4 | ENG.HKA
ENG.HKA.ASB.SUB | Submittal | 5 | ENG.HKA.ASB
ENG.HKA.ASB.APR | Approval | 5 | ENG.HKA.ASB
PRO.HKA.CCT | CCTV system | 4 | PRO.HKA
PRO.HKA.VMS | Video management and video wall | 4 | PRO.HKA
PRO.HKA.ACC | Access control and intercom | 4 | PRO.HKA
PRO.HKA.UPN | UPS, network and cabinets | 4 | PRO.HKA
PRO.HKA.LOG | FAT and logistics | 4 | PRO.HKA
CON.HKA.ENA | Enabling works | 4 | CON.HKA
CON.HKA.CIV | Civil works | 4 | CON.HKA
CON.HKA.INS | Installation | 4 | CON.HKA
COM.HKA.TST | Testing and commissioning | 4 | COM.HKA
COM.HKA.TRN | Training | 4 | COM.HKA
COM.HKA.TOA | Trial operation and acceptance | 4 | COM.HKA
ENG.HMD | Madinah (HHR) | 3 | ENG
PRO.HMD | Madinah (HHR) | 3 | PRO
CON.HMD | Madinah (HHR) | 3 | CON
COM.HMD | Madinah (HHR) | 3 | COM
ENG.HMD.SRV | Site survey and as-found verification | 4 | ENG.HMD
ENG.HMD.SRV.SUB | Submittal | 5 | ENG.HMD.SRV
ENG.HMD.SRV.APR | Approval | 5 | ENG.HMD.SRV
ENG.HMD.CNC | Concept design | 4 | ENG.HMD
ENG.HMD.CNC.SUB | Submittal | 5 | ENG.HMD.CNC
ENG.HMD.CNC.APR | Approval | 5 | ENG.HMD.CNC
ENG.HMD.PRE | Preliminary (schematic) design | 4 | ENG.HMD
ENG.HMD.PRE.SUB | Submittal | 5 | ENG.HMD.PRE
ENG.HMD.PRE.APR | Approval | 5 | ENG.HMD.PRE
ENG.HMD.DET | Detailed design | 4 | ENG.HMD
ENG.HMD.DET.SUB | Submittal | 5 | ENG.HMD.DET
ENG.HMD.DET.APR | Approval | 5 | ENG.HMD.DET
ENG.HMD.IFC | IFC and shop drawings | 4 | ENG.HMD
ENG.HMD.IFC.SUB | Submittal | 5 | ENG.HMD.IFC
ENG.HMD.IFC.APR | Approval | 5 | ENG.HMD.IFC
ENG.HMD.HCS | HCIS documentation (Stage 3 and 4) | 4 | ENG.HMD
ENG.HMD.HCS.SUB | Submittal | 5 | ENG.HMD.HCS
ENG.HMD.HCS.APR | Approval | 5 | ENG.HMD.HCS
ENG.HMD.ASB | As-built and O&M documentation | 4 | ENG.HMD
ENG.HMD.ASB.SUB | Submittal | 5 | ENG.HMD.ASB
ENG.HMD.ASB.APR | Approval | 5 | ENG.HMD.ASB
PRO.HMD.CCT | CCTV system | 4 | PRO.HMD
PRO.HMD.VMS | Video management and video wall | 4 | PRO.HMD
PRO.HMD.ACC | Access control and intercom | 4 | PRO.HMD
PRO.HMD.UPN | UPS, network and cabinets | 4 | PRO.HMD
PRO.HMD.LOG | FAT and logistics | 4 | PRO.HMD
CON.HMD.ENA | Enabling works | 4 | CON.HMD
CON.HMD.CIV | Civil works | 4 | CON.HMD
CON.HMD.INS | Installation | 4 | CON.HMD
COM.HMD.TST | Testing and commissioning | 4 | COM.HMD
COM.HMD.TRN | Training | 4 | COM.HMD
COM.HMD.TOA | Trial operation and acceptance | 4 | COM.HMD
ENG.EAB | Abqaiq (EWR) | 3 | ENG
PRO.EAB | Abqaiq (EWR) | 3 | PRO
CON.EAB | Abqaiq (EWR) | 3 | CON
COM.EAB | Abqaiq (EWR) | 3 | COM
ENG.EAB.SRV | Site survey and as-found verification | 4 | ENG.EAB
ENG.EAB.SRV.SUB | Submittal | 5 | ENG.EAB.SRV
ENG.EAB.SRV.APR | Approval | 5 | ENG.EAB.SRV
ENG.EAB.CNC | Concept design | 4 | ENG.EAB
ENG.EAB.CNC.SUB | Submittal | 5 | ENG.EAB.CNC
ENG.EAB.CNC.APR | Approval | 5 | ENG.EAB.CNC
ENG.EAB.PRE | Preliminary (schematic) design | 4 | ENG.EAB
ENG.EAB.PRE.SUB | Submittal | 5 | ENG.EAB.PRE
ENG.EAB.PRE.APR | Approval | 5 | ENG.EAB.PRE
ENG.EAB.DET | Detailed design | 4 | ENG.EAB
ENG.EAB.DET.SUB | Submittal | 5 | ENG.EAB.DET
ENG.EAB.DET.APR | Approval | 5 | ENG.EAB.DET
ENG.EAB.IFC | IFC and shop drawings | 4 | ENG.EAB
ENG.EAB.IFC.SUB | Submittal | 5 | ENG.EAB.IFC
ENG.EAB.IFC.APR | Approval | 5 | ENG.EAB.IFC
ENG.EAB.HCS | HCIS documentation (Stage 3 and 4) | 4 | ENG.EAB
ENG.EAB.HCS.SUB | Submittal | 5 | ENG.EAB.HCS
ENG.EAB.HCS.APR | Approval | 5 | ENG.EAB.HCS
ENG.EAB.ASB | As-built and O&M documentation | 4 | ENG.EAB
ENG.EAB.ASB.SUB | Submittal | 5 | ENG.EAB.ASB
ENG.EAB.ASB.APR | Approval | 5 | ENG.EAB.ASB
PRO.EAB.CCT | CCTV system | 4 | PRO.EAB
PRO.EAB.VMS | Video management and video wall | 4 | PRO.EAB
PRO.EAB.ACC | Access control and intercom | 4 | PRO.EAB
PRO.EAB.UPN | UPS, network and cabinets | 4 | PRO.EAB
PRO.EAB.LOG | FAT and logistics | 4 | PRO.EAB
CON.EAB.ENA | Enabling works | 4 | CON.EAB
CON.EAB.CIV | Civil works | 4 | CON.EAB
CON.EAB.INS | Installation | 4 | CON.EAB
COM.EAB.TST | Testing and commissioning | 4 | COM.EAB
COM.EAB.TRN | Training | 4 | COM.EAB
COM.EAB.TOA | Trial operation and acceptance | 4 | COM.EAB
ENG.NHL | Hail (NSR) | 3 | ENG
PRO.NHL | Hail (NSR) | 3 | PRO
CON.NHL | Hail (NSR) | 3 | CON
COM.NHL | Hail (NSR) | 3 | COM
ENG.NHL.SRV | Site survey and as-found verification | 4 | ENG.NHL
ENG.NHL.SRV.SUB | Submittal | 5 | ENG.NHL.SRV
ENG.NHL.SRV.APR | Approval | 5 | ENG.NHL.SRV
ENG.NHL.CNC | Concept design | 4 | ENG.NHL
ENG.NHL.CNC.SUB | Submittal | 5 | ENG.NHL.CNC
ENG.NHL.CNC.APR | Approval | 5 | ENG.NHL.CNC
ENG.NHL.PRE | Preliminary (schematic) design | 4 | ENG.NHL
ENG.NHL.PRE.SUB | Submittal | 5 | ENG.NHL.PRE
ENG.NHL.PRE.APR | Approval | 5 | ENG.NHL.PRE
ENG.NHL.DET | Detailed design | 4 | ENG.NHL
ENG.NHL.DET.SUB | Submittal | 5 | ENG.NHL.DET
ENG.NHL.DET.APR | Approval | 5 | ENG.NHL.DET
ENG.NHL.IFC | IFC and shop drawings | 4 | ENG.NHL
ENG.NHL.IFC.SUB | Submittal | 5 | ENG.NHL.IFC
ENG.NHL.IFC.APR | Approval | 5 | ENG.NHL.IFC
ENG.NHL.HCS | HCIS documentation (Stage 3 and 4) | 4 | ENG.NHL
ENG.NHL.HCS.SUB | Submittal | 5 | ENG.NHL.HCS
ENG.NHL.HCS.APR | Approval | 5 | ENG.NHL.HCS
ENG.NHL.ASB | As-built and O&M documentation | 4 | ENG.NHL
ENG.NHL.ASB.SUB | Submittal | 5 | ENG.NHL.ASB
ENG.NHL.ASB.APR | Approval | 5 | ENG.NHL.ASB
PRO.NHL.CCT | CCTV system | 4 | PRO.NHL
PRO.NHL.VMS | Video management and video wall | 4 | PRO.NHL
PRO.NHL.ACC | Access control and intercom | 4 | PRO.NHL
PRO.NHL.UPN | UPS, network and cabinets | 4 | PRO.NHL
PRO.NHL.LOG | FAT and logistics | 4 | PRO.NHL
CON.NHL.ENA | Enabling works | 4 | CON.NHL
CON.NHL.CIV | Civil works | 4 | CON.NHL
CON.NHL.INS | Installation | 4 | CON.NHL
COM.NHL.TST | Testing and commissioning | 4 | COM.NHL
COM.NHL.TRN | Training | 4 | COM.NHL
COM.NHL.TOA | Trial operation and acceptance | 4 | COM.NHL
ENG.NJF | Al Jouf (NSR) | 3 | ENG
PRO.NJF | Al Jouf (NSR) | 3 | PRO
CON.NJF | Al Jouf (NSR) | 3 | CON
COM.NJF | Al Jouf (NSR) | 3 | COM
ENG.NJF.SRV | Site survey and as-found verification | 4 | ENG.NJF
ENG.NJF.SRV.SUB | Submittal | 5 | ENG.NJF.SRV
ENG.NJF.SRV.APR | Approval | 5 | ENG.NJF.SRV
ENG.NJF.CNC | Concept design | 4 | ENG.NJF
ENG.NJF.CNC.SUB | Submittal | 5 | ENG.NJF.CNC
ENG.NJF.CNC.APR | Approval | 5 | ENG.NJF.CNC
ENG.NJF.PRE | Preliminary (schematic) design | 4 | ENG.NJF
ENG.NJF.PRE.SUB | Submittal | 5 | ENG.NJF.PRE
ENG.NJF.PRE.APR | Approval | 5 | ENG.NJF.PRE
ENG.NJF.DET | Detailed design | 4 | ENG.NJF
ENG.NJF.DET.SUB | Submittal | 5 | ENG.NJF.DET
ENG.NJF.DET.APR | Approval | 5 | ENG.NJF.DET
ENG.NJF.IFC | IFC and shop drawings | 4 | ENG.NJF
ENG.NJF.IFC.SUB | Submittal | 5 | ENG.NJF.IFC
ENG.NJF.IFC.APR | Approval | 5 | ENG.NJF.IFC
ENG.NJF.HCS | HCIS documentation (Stage 3 and 4) | 4 | ENG.NJF
ENG.NJF.HCS.SUB | Submittal | 5 | ENG.NJF.HCS
ENG.NJF.HCS.APR | Approval | 5 | ENG.NJF.HCS
ENG.NJF.ASB | As-built and O&M documentation | 4 | ENG.NJF
ENG.NJF.ASB.SUB | Submittal | 5 | ENG.NJF.ASB
ENG.NJF.ASB.APR | Approval | 5 | ENG.NJF.ASB
PRO.NJF.CCT | CCTV system | 4 | PRO.NJF
PRO.NJF.VMS | Video management and video wall | 4 | PRO.NJF
PRO.NJF.ACC | Access control and intercom | 4 | PRO.NJF
PRO.NJF.UPN | UPS, network and cabinets | 4 | PRO.NJF
PRO.NJF.LOG | FAT and logistics | 4 | PRO.NJF
CON.NJF.ENA | Enabling works | 4 | CON.NJF
CON.NJF.CIV | Civil works | 4 | CON.NJF
CON.NJF.INS | Installation | 4 | CON.NJF
COM.NJF.TST | Testing and commissioning | 4 | COM.NJF
COM.NJF.TRN | Training | 4 | COM.NJF
COM.NJF.TOA | Trial operation and acceptance | 4 | COM.NJF
ENG.NQR | Al Qurayyat (NSR) | 3 | ENG
PRO.NQR | Al Qurayyat (NSR) | 3 | PRO
CON.NQR | Al Qurayyat (NSR) | 3 | CON
COM.NQR | Al Qurayyat (NSR) | 3 | COM
ENG.NQR.SRV | Site survey and as-found verification | 4 | ENG.NQR
ENG.NQR.SRV.SUB | Submittal | 5 | ENG.NQR.SRV
ENG.NQR.SRV.APR | Approval | 5 | ENG.NQR.SRV
ENG.NQR.CNC | Concept design | 4 | ENG.NQR
ENG.NQR.CNC.SUB | Submittal | 5 | ENG.NQR.CNC
ENG.NQR.CNC.APR | Approval | 5 | ENG.NQR.CNC
ENG.NQR.PRE | Preliminary (schematic) design | 4 | ENG.NQR
ENG.NQR.PRE.SUB | Submittal | 5 | ENG.NQR.PRE
ENG.NQR.PRE.APR | Approval | 5 | ENG.NQR.PRE
ENG.NQR.DET | Detailed design | 4 | ENG.NQR
ENG.NQR.DET.SUB | Submittal | 5 | ENG.NQR.DET
ENG.NQR.DET.APR | Approval | 5 | ENG.NQR.DET
ENG.NQR.IFC | IFC and shop drawings | 4 | ENG.NQR
ENG.NQR.IFC.SUB | Submittal | 5 | ENG.NQR.IFC
ENG.NQR.IFC.APR | Approval | 5 | ENG.NQR.IFC
ENG.NQR.HCS | HCIS documentation (Stage 3 and 4) | 4 | ENG.NQR
ENG.NQR.HCS.SUB | Submittal | 5 | ENG.NQR.HCS
ENG.NQR.HCS.APR | Approval | 5 | ENG.NQR.HCS
ENG.NQR.ASB | As-built and O&M documentation | 4 | ENG.NQR
ENG.NQR.ASB.SUB | Submittal | 5 | ENG.NQR.ASB
ENG.NQR.ASB.APR | Approval | 5 | ENG.NQR.ASB
PRO.NQR.CCT | CCTV system | 4 | PRO.NQR
PRO.NQR.VMS | Video management and video wall | 4 | PRO.NQR
PRO.NQR.ACC | Access control and intercom | 4 | PRO.NQR
PRO.NQR.UPN | UPS, network and cabinets | 4 | PRO.NQR
PRO.NQR.LOG | FAT and logistics | 4 | PRO.NQR
CON.NQR.ENA | Enabling works | 4 | CON.NQR
CON.NQR.CIV | Civil works | 4 | CON.NQR
CON.NQR.INS | Installation | 4 | CON.NQR
COM.NQR.TST | Testing and commissioning | 4 | COM.NQR
COM.NQR.TRN | Training | 4 | COM.NQR
COM.NQR.TOA | Trial operation and acceptance | 4 | COM.NQR

## Relationships
Predecessor | Successor | Type | Lag (work days)
PRJ-M0000 | PRJ-A1010 | FS | 0
PRJ-M0000 | PRJ-A1020 | FS | 0
PRJ-A1020 | PRJ-A1030 | FS | 0
PRJ-M0000 | PRJ-A1040 | FS | 5
PRJ-M0000 | PRJ-A1050 | FS | 5
PRJ-M0000 | PRJ-A1060 | FS | 0
PRJ-A1010 | PRJ-M1100 | FS | 0
PRJ-A1030 | PRJ-M1100 | FS | 0
PRJ-A1040 | PRJ-M1100 | FS | 0
PRJ-A1050 | PRJ-M1100 | FS | 0
PRJ-M1100 | PRJ-M1150 | FS | 0
PRJ-M0000 | PRJ-M1150 | FS | 45
PRJ-A1060 | PRJ-M1150 | FS | 0
PRJ-M1150 | PRJ-A2010 | FS | 0
PRJ-A2010 | PRJ-A2020 | FS | 0
PRJ-A2020 | PRJ-M2100 | FS | 0
PRJ-A1060 | NRY-E1010 | FS | 0
PRJ-M1150 | NRY-E1010 | FS | 0
NRY-E1010 | NRY-E1030 | FS | 0
NRY-E1030 | NRY-E1050 | FS | 0
NRY-E1050 | NRY-E1070 | FS | 0
NRY-E1070 | NRY-E1090 | FS | 0
NRY-E1090 | NRY-E1100 | FS | 0
NRY-E1050 | NRY-E1110 | FS | 8
NRY-E1090 | NRY-E1110 | FF | 0
NRY-E1110 | NRY-E1120 | FS | 0
PRJ-A1060 | HMK-E1010 | FS | 0
PRJ-M1150 | HMK-E1010 | FS | 0
HMK-E1010 | HMK-E1030 | FS | 0
HMK-E1030 | HMK-E1050 | FS | 0
HMK-E1050 | HMK-E1070 | FS | 0
HMK-E1070 | HMK-E1090 | FS | 0
HMK-E1090 | HMK-E1100 | FS | 0
HMK-E1050 | HMK-E1110 | FS | 6
HMK-E1090 | HMK-E1110 | FF | 0
HMK-E1110 | HMK-E1120 | FS | 0
PRJ-A1060 | ERY-E1010 | FS | 0
PRJ-M1150 | ERY-E1010 | FS | 0
ERY-E1010 | ERY-E1030 | FS | 0
ERY-E1030 | ERY-E1050 | FS | 0
ERY-E1050 | ERY-E1070 | FS | 0
ERY-E1070 | ERY-E1090 | FS | 0
ERY-E1090 | ERY-E1100 | FS | 0
ERY-E1050 | ERY-E1110 | FS | 8
ERY-E1090 | ERY-E1110 | FF | 0
ERY-E1110 | ERY-E1120 | FS | 0
NRY-E1100 | PRJ-M1250 | FS | 0
NRY-E1120 | PRJ-M1250 | FS | 0
HMK-E1100 | PRJ-M1250 | FS | 0
HMK-E1120 | PRJ-M1250 | FS | 0
ERY-E1100 | PRJ-M1250 | FS | 0
ERY-E1120 | PRJ-M1250 | FS | 0
NRY-E1010 | NRY-E1020 | FS | 0
NRY-E1030 | NRY-E1040 | FS | 0
NRY-E1050 | NRY-E1060 | FS | 0
NRY-E1070 | NRY-E1080 | FS | 0
NRY-E1090 | NRY-E1200 | FS | 0
NRY-E1110 | NRY-E1200 | FS | 0
NRY-E1020 | NRY-E1210 | FS | 0
NRY-E1040 | NRY-E1210 | FS | 0
NRY-E1060 | NRY-E1210 | FS | 0
NRY-E1080 | NRY-E1210 | FS | 0
NRY-E1100 | NRY-E1210 | FS | 0
NRY-E1120 | NRY-E1210 | FS | 0
NRY-E1200 | NRY-E1210 | FS | 0
NRY-E1210 | NRY-P1010 | FS | 0
NRY-E1210 | NRY-P1020 | FS | 0
NRY-E1210 | NRY-P1030 | FS | 0
NRY-E1210 | NRY-P1040 | FS | 0
NRY-P1010 | NRY-P1050 | FS | 0
NRY-P1020 | NRY-P1050 | FS | 0
NRY-P1030 | NRY-P1050 | FS | 0
NRY-P1040 | NRY-P1050 | FS | 0
NRY-P1050 | NRY-P1060 | FS | 0
NRY-P1060 | NRY-P1070 | FS | 0
NRY-P1070 | NRY-P1100 | FS | 0
NRY-P1100 | NRY-C2010 | FS | 0
NRY-E1120 | NRY-X1010 | FS | 0
NRY-X1010 | NRY-X1020 | FS | 0
NRY-X1020 | NRY-C1010 | FS | 0
NRY-C2010 | NRY-C2020 | SS | 4
NRY-C1010 | NRY-C2020 | SS | 41
NRY-C1010 | NRY-C1020 | SS | 37
NRY-C2020 | NRY-C2030 | FS | 0
NRY-C1020 | NRY-C2030 | FS | 0
NRY-C2010 | NRY-C2040 | FS | 0
NRY-C2010 | NRY-C2050 | FS | 4
NRY-C2020 | NRY-C2100 | FS | 0
NRY-C2030 | NRY-C2100 | FS | 0
NRY-C2040 | NRY-C2100 | FS | 0
NRY-C2050 | NRY-C2100 | FS | 0
NRY-C1020 | NRY-C2100 | FS | 0
NRY-C2100 | NRY-T1010 | FS | 0
NRY-T1010 | NRY-T1020 | FS | 0
NRY-C2100 | NRY-T1030 | FS | 0
NRY-T1030 | NRY-T1130 | FS | 0
NRY-T1020 | NRY-T1100 | FS | 0
NRY-T1130 | NRY-T1100 | FS | 0
NRY-T1020 | NRY-T2010 | FS | 0
NRY-T1020 | NRY-T2020 | FS | 0
NRY-C2100 | NRY-E1130 | FS | 0
NRY-E1130 | NRY-E1140 | FS | 0
NRY-T1100 | NRY-T3010 | FS | 0
NRY-T2010 | NRY-T3010 | FS | 0
NRY-T2020 | NRY-T3010 | FS | 0
NRY-E1140 | NRY-T3010 | FS | 0
NRY-T1130 | NRY-T3010 | FS | 0
NRY-T3010 | NRY-T3100 | FS | 0
HMK-E1010 | HMK-E1020 | FS | 0
HMK-E1030 | HMK-E1040 | FS | 0
HMK-E1050 | HMK-E1060 | FS | 0
HMK-E1070 | HMK-E1080 | FS | 0
HMK-E1090 | HMK-E1200 | FS | 0
HMK-E1110 | HMK-E1200 | FS | 0
HMK-E1020 | HMK-E1210 | FS | 0
HMK-E1040 | HMK-E1210 | FS | 0
HMK-E1060 | HMK-E1210 | FS | 0
HMK-E1080 | HMK-E1210 | FS | 0
HMK-E1100 | HMK-E1210 | FS | 0
HMK-E1120 | HMK-E1210 | FS | 0
HMK-E1200 | HMK-E1210 | FS | 0
HMK-E1210 | HMK-P1010 | FS | 0
HMK-E1210 | HMK-P1020 | FS | 0
HMK-E1210 | HMK-P1030 | FS | 0
HMK-E1210 | HMK-P1040 | FS | 0
HMK-P1010 | HMK-P1050 | FS | 0
HMK-P1020 | HMK-P1050 | FS | 0
HMK-P1030 | HMK-P1050 | FS | 0
HMK-P1040 | HMK-P1050 | FS | 0
HMK-P1050 | HMK-P1060 | FS | 0
HMK-P1060 | HMK-P1070 | FS | 0
HMK-P1070 | HMK-P1100 | FS | 0
HMK-P1100 | HMK-C2010 | FS | 0
HMK-E1120 | HMK-X1010 | FS | 0
HMK-X1010 | HMK-X1020 | FS | 0
HMK-X1020 | HMK-C1010 | FS | 0
HMK-C2010 | HMK-C2020 | SS | 8
HMK-C1010 | HMK-C2020 | SS | 34
HMK-C1010 | HMK-C1020 | SS | 31
HMK-C2020 | HMK-C2030 | FS | 0
HMK-C1020 | HMK-C2030 | FS | 0
HMK-C2010 | HMK-C2040 | FS | 0
HMK-C2010 | HMK-C2050 | FS | 8
HMK-C2020 | HMK-C2100 | FS | 0
HMK-C2030 | HMK-C2100 | FS | 0
HMK-C2040 | HMK-C2100 | FS | 0
HMK-C2050 | HMK-C2100 | FS | 0
HMK-C1020 | HMK-C2100 | FS | 0
HMK-C2100 | HMK-T1010 | FS | 0
HMK-T1010 | HMK-T1020 | FS | 0
HMK-T1020 | HMK-T1100 | FS | 0
HMK-T1020 | HMK-T2010 | FS | 0
HMK-T1020 | HMK-T2020 | FS | 0
HMK-C2100 | HMK-E1130 | FS | 0
HMK-E1130 | HMK-E1140 | FS | 0
HMK-T1100 | HMK-T3010 | FS | 0
HMK-T2010 | HMK-T3010 | FS | 0
HMK-T2020 | HMK-T3010 | FS | 0
HMK-E1140 | HMK-T3010 | FS | 0
HMK-T3010 | HMK-T3100 | FS | 0
ERY-E1010 | ERY-E1020 | FS | 0
ERY-E1030 | ERY-E1040 | FS | 0
ERY-E1050 | ERY-E1060 | FS | 0
ERY-E1070 | ERY-E1080 | FS | 0
ERY-E1090 | ERY-E1200 | FS | 0
ERY-E1110 | ERY-E1200 | FS | 0
ERY-E1020 | ERY-E1210 | FS | 0
ERY-E1040 | ERY-E1210 | FS | 0
ERY-E1060 | ERY-E1210 | FS | 0
ERY-E1080 | ERY-E1210 | FS | 0
ERY-E1100 | ERY-E1210 | FS | 0
ERY-E1120 | ERY-E1210 | FS | 0
ERY-E1200 | ERY-E1210 | FS | 0
ERY-E1210 | ERY-P1010 | FS | 0
ERY-E1210 | ERY-P1020 | FS | 0
ERY-E1210 | ERY-P1030 | FS | 0
ERY-E1210 | ERY-P1040 | FS | 0
ERY-P1010 | ERY-P1050 | FS | 0
ERY-P1020 | ERY-P1050 | FS | 0
ERY-P1030 | ERY-P1050 | FS | 0
ERY-P1040 | ERY-P1050 | FS | 0
ERY-P1050 | ERY-P1060 | FS | 0
ERY-P1060 | ERY-P1070 | FS | 0
ERY-P1070 | ERY-P1100 | FS | 0
ERY-P1100 | ERY-C2010 | FS | 0
ERY-E1120 | ERY-X1010 | FS | 0
ERY-X1010 | ERY-X1020 | FS | 0
ERY-X1020 | ERY-C1010 | FS | 0
ERY-C2010 | ERY-C2020 | SS | 4
ERY-C1010 | ERY-C2020 | SS | 39
ERY-C1010 | ERY-C1020 | SS | 35
ERY-C2020 | ERY-C2030 | FS | 0
ERY-C1020 | ERY-C2030 | FS | 0
ERY-C2010 | ERY-C2040 | FS | 0
ERY-C2010 | ERY-C2050 | FS | 4
ERY-C2020 | ERY-C2100 | FS | 0
ERY-C2030 | ERY-C2100 | FS | 0
ERY-C2040 | ERY-C2100 | FS | 0
ERY-C2050 | ERY-C2100 | FS | 0
ERY-C1020 | ERY-C2100 | FS | 0
ERY-C2100 | ERY-T1010 | FS | 0
ERY-T1010 | ERY-T1020 | FS | 0
ERY-T1020 | ERY-T1100 | FS | 0
ERY-T1020 | ERY-T2010 | FS | 0
ERY-T1020 | ERY-T2020 | FS | 0
ERY-C2100 | ERY-E1130 | FS | 0
ERY-E1130 | ERY-E1140 | FS | 0
ERY-T1100 | ERY-T3010 | FS | 0
ERY-T2010 | ERY-T3010 | FS | 0
ERY-T2020 | ERY-T3010 | FS | 0
ERY-E1140 | ERY-T3010 | FS | 0
ERY-T3010 | ERY-T3100 | FS | 0
PRJ-A1060 | HJD-E1010 | FS | 0
PRJ-M1150 | HJD-E1010 | FS | 38
HJD-E1010 | HJD-E1020 | FS | 0
HJD-E1010 | HJD-E1030 | FS | 0
HJD-E1030 | HJD-E1040 | FS | 0
HJD-E1030 | HJD-E1050 | FS | 0
HJD-E1050 | HJD-E1060 | FS | 0
HJD-E1050 | HJD-E1070 | FS | 0
HJD-E1070 | HJD-E1080 | FS | 0
HJD-E1070 | HJD-E1090 | FS | 0
HJD-E1090 | HJD-E1100 | FS | 0
HJD-E1050 | HJD-E1110 | FS | 6
HJD-E1090 | HJD-E1110 | FF | 0
HJD-E1110 | HJD-E1120 | FS | 0
HJD-E1090 | HJD-E1200 | FS | 0
HJD-E1110 | HJD-E1200 | FS | 0
HJD-E1020 | HJD-E1210 | FS | 0
HJD-E1040 | HJD-E1210 | FS | 0
HJD-E1060 | HJD-E1210 | FS | 0
HJD-E1080 | HJD-E1210 | FS | 0
HJD-E1100 | HJD-E1210 | FS | 0
HJD-E1120 | HJD-E1210 | FS | 0
HJD-E1200 | HJD-E1210 | FS | 0
HJD-E1210 | HJD-P1010 | FS | 0
HJD-E1210 | HJD-P1020 | FS | 0
HJD-E1210 | HJD-P1030 | FS | 0
HJD-E1210 | HJD-P1040 | FS | 0
HJD-P1010 | HJD-P1050 | FS | 0
HJD-P1020 | HJD-P1050 | FS | 0
HJD-P1030 | HJD-P1050 | FS | 0
HJD-P1040 | HJD-P1050 | FS | 0
HJD-P1050 | HJD-P1060 | FS | 0
HJD-P1060 | HJD-P1070 | FS | 0
HJD-P1070 | HJD-P1100 | FS | 0
HJD-P1100 | HJD-C2010 | FS | 0
HJD-E1120 | HJD-X1010 | FS | 0
HJD-X1010 | HJD-X1020 | FS | 0
HJD-X1020 | HJD-C1010 | FS | 0
HJD-C2010 | HJD-C2020 | SS | 7
HJD-C1010 | HJD-C2020 | SS | 32
HJD-C1010 | HJD-C1020 | SS | 28
HJD-C2020 | HJD-C2030 | FS | 0
HJD-C1020 | HJD-C2030 | FS | 0
HJD-C2010 | HJD-C2040 | FS | 0
HJD-C2010 | HJD-C2050 | FS | 7
HJD-C2020 | HJD-C2100 | FS | 0
HJD-C2030 | HJD-C2100 | FS | 0
HJD-C2040 | HJD-C2100 | FS | 0
HJD-C2050 | HJD-C2100 | FS | 0
HJD-C1020 | HJD-C2100 | FS | 0
HJD-C2100 | HJD-T1010 | FS | 0
HJD-T1010 | HJD-T1020 | FS | 0
HJD-T1020 | HJD-T1100 | FS | 0
HJD-T1020 | HJD-T2010 | FS | 0
HJD-T1020 | HJD-T2020 | FS | 0
HJD-C2100 | HJD-E1130 | FS | 0
HJD-E1130 | HJD-E1140 | FS | 0
HJD-T1100 | HJD-T3010 | FS | 0
HJD-T2010 | HJD-T3010 | FS | 0
HJD-T2020 | HJD-T3010 | FS | 0
HJD-E1140 | HJD-T3010 | FS | 0
HJD-T3010 | HJD-T3100 | FS | 0
PRJ-A1060 | EDM-E1010 | FS | 0
PRJ-M1150 | EDM-E1010 | FS | 104
EDM-E1010 | EDM-E1020 | FS | 0
EDM-E1010 | EDM-E1030 | FS | 0
EDM-E1030 | EDM-E1040 | FS | 0
EDM-E1030 | EDM-E1050 | FS | 0
EDM-E1050 | EDM-E1060 | FS | 0
EDM-E1050 | EDM-E1070 | FS | 0
EDM-E1070 | EDM-E1080 | FS | 0
EDM-E1070 | EDM-E1090 | FS | 0
EDM-E1090 | EDM-E1100 | FS | 0
EDM-E1050 | EDM-E1110 | FS | 10
EDM-E1090 | EDM-E1110 | FF | 0
EDM-E1110 | EDM-E1120 | FS | 0
EDM-E1090 | EDM-E1200 | FS | 0
EDM-E1110 | EDM-E1200 | FS | 0
EDM-E1020 | EDM-E1210 | FS | 0
EDM-E1040 | EDM-E1210 | FS | 0
EDM-E1060 | EDM-E1210 | FS | 0
EDM-E1080 | EDM-E1210 | FS | 0
EDM-E1100 | EDM-E1210 | FS | 0
EDM-E1120 | EDM-E1210 | FS | 0
EDM-E1200 | EDM-E1210 | FS | 0
EDM-E1210 | EDM-P1010 | FS | 0
EDM-E1210 | EDM-P1020 | FS | 0
EDM-E1210 | EDM-P1030 | FS | 0
EDM-E1210 | EDM-P1040 | FS | 0
EDM-P1010 | EDM-P1050 | FS | 0
EDM-P1020 | EDM-P1050 | FS | 0
EDM-P1030 | EDM-P1050 | FS | 0
EDM-P1040 | EDM-P1050 | FS | 0
EDM-P1050 | EDM-P1060 | FS | 0
EDM-P1060 | EDM-P1070 | FS | 0
EDM-P1070 | EDM-P1100 | FS | 0
EDM-P1100 | EDM-C2010 | FS | 0
EDM-E1120 | EDM-X1010 | FS | 0
EDM-X1010 | EDM-X1020 | FS | 0
EDM-X1020 | EDM-C1010 | FS | 0
EDM-C2010 | EDM-C2020 | SS | 4
EDM-C1010 | EDM-C2020 | SS | 39
EDM-C1010 | EDM-C1020 | SS | 35
EDM-C2020 | EDM-C2030 | FS | 0
EDM-C1020 | EDM-C2030 | FS | 0
EDM-C2010 | EDM-C2040 | FS | 0
EDM-C2010 | EDM-C2050 | FS | 4
EDM-C2020 | EDM-C2100 | FS | 0
EDM-C2030 | EDM-C2100 | FS | 0
EDM-C2040 | EDM-C2100 | FS | 0
EDM-C2050 | EDM-C2100 | FS | 0
EDM-C1020 | EDM-C2100 | FS | 0
EDM-C2100 | EDM-T1010 | FS | 0
EDM-T1010 | EDM-T1020 | FS | 0
EDM-T1020 | EDM-T1100 | FS | 0
EDM-T1020 | EDM-T2010 | FS | 0
EDM-T1020 | EDM-T2020 | FS | 0
EDM-C2100 | EDM-E1130 | FS | 0
EDM-E1130 | EDM-E1140 | FS | 0
EDM-T1100 | EDM-T3010 | FS | 0
EDM-T2010 | EDM-T3010 | FS | 0
EDM-T2020 | EDM-T3010 | FS | 0
EDM-E1140 | EDM-T3010 | FS | 0
EDM-T3010 | EDM-T3100 | FS | 0
PRJ-A1060 | NQS-E1010 | FS | 0
PRJ-M1150 | NQS-E1010 | FS | 142
NQS-E1010 | NQS-E1020 | FS | 0
NQS-E1010 | NQS-E1030 | FS | 0
NQS-E1030 | NQS-E1040 | FS | 0
NQS-E1030 | NQS-E1050 | FS | 0
NQS-E1050 | NQS-E1060 | FS | 0
NQS-E1050 | NQS-E1070 | FS | 0
NQS-E1070 | NQS-E1080 | FS | 0
NQS-E1070 | NQS-E1090 | FS | 0
NQS-E1090 | NQS-E1100 | FS | 0
NQS-E1050 | NQS-E1110 | FS | 9
NQS-E1090 | NQS-E1110 | FF | 0
NQS-E1110 | NQS-E1120 | FS | 0
NQS-E1090 | NQS-E1200 | FS | 0
NQS-E1110 | NQS-E1200 | FS | 0
NQS-E1020 | NQS-E1210 | FS | 0
NQS-E1040 | NQS-E1210 | FS | 0
NQS-E1060 | NQS-E1210 | FS | 0
NQS-E1080 | NQS-E1210 | FS | 0
NQS-E1100 | NQS-E1210 | FS | 0
NQS-E1120 | NQS-E1210 | FS | 0
NQS-E1200 | NQS-E1210 | FS | 0
NQS-E1210 | NQS-P1010 | FS | 0
NQS-E1210 | NQS-P1020 | FS | 0
NQS-E1210 | NQS-P1030 | FS | 0
NQS-E1210 | NQS-P1040 | FS | 0
NQS-P1010 | NQS-P1050 | FS | 0
NQS-P1020 | NQS-P1050 | FS | 0
NQS-P1030 | NQS-P1050 | FS | 0
NQS-P1040 | NQS-P1050 | FS | 0
NQS-P1050 | NQS-P1060 | FS | 0
NQS-P1060 | NQS-P1070 | FS | 0
NQS-P1070 | NQS-P1100 | FS | 0
NQS-P1100 | NQS-C2010 | FS | 0
NQS-E1120 | NQS-X1010 | FS | 0
NQS-X1010 | NQS-X1020 | FS | 0
NQS-X1020 | NQS-C1010 | FS | 0
NQS-C2010 | NQS-C2020 | SS | 4
NQS-C1010 | NQS-C2020 | SS | 41
NQS-C1010 | NQS-C1020 | SS | 37
NQS-C2020 | NQS-C2030 | FS | 0
NQS-C1020 | NQS-C2030 | FS | 0
NQS-C2010 | NQS-C2040 | FS | 0
NQS-C2010 | NQS-C2050 | FS | 4
NQS-C2020 | NQS-C2100 | FS | 0
NQS-C2030 | NQS-C2100 | FS | 0
NQS-C2040 | NQS-C2100 | FS | 0
NQS-C2050 | NQS-C2100 | FS | 0
NQS-C1020 | NQS-C2100 | FS | 0
NQS-C2100 | NQS-T1010 | FS | 0
NQS-T1010 | NQS-T1020 | FS | 0
NQS-T1020 | NQS-T1100 | FS | 0
NQS-T1020 | NQS-T2010 | FS | 0
NQS-T1020 | NQS-T2020 | FS | 0
NQS-C2100 | NQS-E1130 | FS | 0
NQS-E1130 | NQS-E1140 | FS | 0
NQS-T1100 | NQS-T3010 | FS | 0
NQS-T2010 | NQS-T3010 | FS | 0
NQS-T2020 | NQS-T3010 | FS | 0
NQS-E1140 | NQS-T3010 | FS | 0
NQS-T3010 | NQS-T3100 | FS | 0
PRJ-A1060 | EHF-E1010 | FS | 0
PRJ-M1150 | EHF-E1010 | FS | 142
EHF-E1010 | EHF-E1020 | FS | 0
EHF-E1010 | EHF-E1030 | FS | 0
EHF-E1030 | EHF-E1040 | FS | 0
EHF-E1030 | EHF-E1050 | FS | 0
EHF-E1050 | EHF-E1060 | FS | 0
EHF-E1050 | EHF-E1070 | FS | 0
EHF-E1070 | EHF-E1080 | FS | 0
EHF-E1070 | EHF-E1090 | FS | 0
EHF-E1090 | EHF-E1100 | FS | 0
EHF-E1050 | EHF-E1110 | FS | 9
EHF-E1090 | EHF-E1110 | FF | 0
EHF-E1110 | EHF-E1120 | FS | 0
EHF-E1090 | EHF-E1200 | FS | 0
EHF-E1110 | EHF-E1200 | FS | 0
EHF-E1020 | EHF-E1210 | FS | 0
EHF-E1040 | EHF-E1210 | FS | 0
EHF-E1060 | EHF-E1210 | FS | 0
EHF-E1080 | EHF-E1210 | FS | 0
EHF-E1100 | EHF-E1210 | FS | 0
EHF-E1120 | EHF-E1210 | FS | 0
EHF-E1200 | EHF-E1210 | FS | 0
EHF-E1210 | EHF-P1010 | FS | 0
EHF-E1210 | EHF-P1020 | FS | 0
EHF-E1210 | EHF-P1030 | FS | 0
EHF-E1210 | EHF-P1040 | FS | 0
EHF-P1010 | EHF-P1050 | FS | 0
EHF-P1020 | EHF-P1050 | FS | 0
EHF-P1030 | EHF-P1050 | FS | 0
EHF-P1040 | EHF-P1050 | FS | 0
EHF-P1050 | EHF-P1060 | FS | 0
EHF-P1060 | EHF-P1070 | FS | 0
EHF-P1070 | EHF-P1100 | FS | 0
EHF-P1100 | EHF-C2010 | FS | 0
EHF-E1120 | EHF-X1010 | FS | 0
EHF-X1010 | EHF-X1020 | FS | 0
EHF-X1020 | EHF-C1010 | FS | 0
EHF-C2010 | EHF-C2020 | SS | 4
EHF-C1010 | EHF-C2020 | SS | 38
EHF-C1010 | EHF-C1020 | SS | 34
EHF-C2020 | EHF-C2030 | FS | 0
EHF-C1020 | EHF-C2030 | FS | 0
EHF-C2010 | EHF-C2040 | FS | 0
EHF-C2010 | EHF-C2050 | FS | 4
EHF-C2020 | EHF-C2100 | FS | 0
EHF-C2030 | EHF-C2100 | FS | 0
EHF-C2040 | EHF-C2100 | FS | 0
EHF-C2050 | EHF-C2100 | FS | 0
EHF-C1020 | EHF-C2100 | FS | 0
EHF-C2100 | EHF-T1010 | FS | 0
EHF-T1010 | EHF-T1020 | FS | 0
EHF-T1020 | EHF-T1100 | FS | 0
EHF-T1020 | EHF-T2010 | FS | 0
EHF-T1020 | EHF-T2020 | FS | 0
EHF-C2100 | EHF-E1130 | FS | 0
EHF-E1130 | EHF-E1140 | FS | 0
EHF-T1100 | EHF-T3010 | FS | 0
EHF-T2010 | EHF-T3010 | FS | 0
EHF-T2020 | EHF-T3010 | FS | 0
EHF-E1140 | EHF-T3010 | FS | 0
EHF-T3010 | EHF-T3100 | FS | 0
PRJ-A1060 | NMJ-E1010 | FS | 0
PRJ-M1150 | NMJ-E1010 | FS | 175
NMJ-E1010 | NMJ-E1020 | FS | 0
NMJ-E1010 | NMJ-E1030 | FS | 0
NMJ-E1030 | NMJ-E1040 | FS | 0
NMJ-E1030 | NMJ-E1050 | FS | 0
NMJ-E1050 | NMJ-E1060 | FS | 0
NMJ-E1050 | NMJ-E1070 | FS | 0
NMJ-E1070 | NMJ-E1080 | FS | 0
NMJ-E1070 | NMJ-E1090 | FS | 0
NMJ-E1090 | NMJ-E1100 | FS | 0
NMJ-E1050 | NMJ-E1110 | FS | 10
NMJ-E1090 | NMJ-E1110 | FF | 0
NMJ-E1110 | NMJ-E1120 | FS | 0
NMJ-E1090 | NMJ-E1200 | FS | 0
NMJ-E1110 | NMJ-E1200 | FS | 0
NMJ-E1020 | NMJ-E1210 | FS | 0
NMJ-E1040 | NMJ-E1210 | FS | 0
NMJ-E1060 | NMJ-E1210 | FS | 0
NMJ-E1080 | NMJ-E1210 | FS | 0
NMJ-E1100 | NMJ-E1210 | FS | 0
NMJ-E1120 | NMJ-E1210 | FS | 0
NMJ-E1200 | NMJ-E1210 | FS | 0
NMJ-E1210 | NMJ-P1010 | FS | 0
NMJ-E1210 | NMJ-P1020 | FS | 0
NMJ-E1210 | NMJ-P1030 | FS | 0
NMJ-E1210 | NMJ-P1040 | FS | 0
NMJ-P1010 | NMJ-P1050 | FS | 0
NMJ-P1020 | NMJ-P1050 | FS | 0
NMJ-P1030 | NMJ-P1050 | FS | 0
NMJ-P1040 | NMJ-P1050 | FS | 0
NMJ-P1050 | NMJ-P1060 | FS | 0
NMJ-P1060 | NMJ-P1070 | FS | 0
NMJ-P1070 | NMJ-P1100 | FS | 0
NMJ-P1100 | NMJ-C2010 | FS | 0
NMJ-E1120 | NMJ-X1010 | FS | 0
NMJ-X1010 | NMJ-X1020 | FS | 0
NMJ-X1020 | NMJ-C1010 | FS | 0
NMJ-C2010 | NMJ-C2020 | SS | 4
NMJ-C1010 | NMJ-C2020 | SS | 41
NMJ-C1010 | NMJ-C1020 | SS | 37
NMJ-C2020 | NMJ-C2030 | FS | 0
NMJ-C1020 | NMJ-C2030 | FS | 0
NMJ-C2010 | NMJ-C2040 | FS | 0
NMJ-C2010 | NMJ-C2050 | FS | 4
NMJ-C2020 | NMJ-C2100 | FS | 0
NMJ-C2030 | NMJ-C2100 | FS | 0
NMJ-C2040 | NMJ-C2100 | FS | 0
NMJ-C2050 | NMJ-C2100 | FS | 0
NMJ-C1020 | NMJ-C2100 | FS | 0
NMJ-C2100 | NMJ-T1010 | FS | 0
NMJ-T1010 | NMJ-T1020 | FS | 0
NMJ-T1020 | NMJ-T1100 | FS | 0
NMJ-T1020 | NMJ-T2010 | FS | 0
NMJ-T1020 | NMJ-T2020 | FS | 0
NMJ-C2100 | NMJ-E1130 | FS | 0
NMJ-E1130 | NMJ-E1140 | FS | 0
NMJ-T1100 | NMJ-T3010 | FS | 0
NMJ-T2010 | NMJ-T3010 | FS | 0
NMJ-T2020 | NMJ-T3010 | FS | 0
NMJ-E1140 | NMJ-T3010 | FS | 0
NMJ-T3010 | NMJ-T3100 | FS | 0
PRJ-A1060 | HKA-E1010 | FS | 0
PRJ-M1150 | HKA-E1010 | FS | 258
HKA-E1010 | HKA-E1020 | FS | 0
HKA-E1010 | HKA-E1030 | FS | 0
HKA-E1030 | HKA-E1040 | FS | 0
HKA-E1030 | HKA-E1050 | FS | 0
HKA-E1050 | HKA-E1060 | FS | 0
HKA-E1050 | HKA-E1070 | FS | 0
HKA-E1070 | HKA-E1080 | FS | 0
HKA-E1070 | HKA-E1090 | FS | 0
HKA-E1090 | HKA-E1100 | FS | 0
HKA-E1050 | HKA-E1110 | FS | 7
HKA-E1090 | HKA-E1110 | FF | 0
HKA-E1110 | HKA-E1120 | FS | 0
HKA-E1090 | HKA-E1200 | FS | 0
HKA-E1110 | HKA-E1200 | FS | 0
HKA-E1020 | HKA-E1210 | FS | 0
HKA-E1040 | HKA-E1210 | FS | 0
HKA-E1060 | HKA-E1210 | FS | 0
HKA-E1080 | HKA-E1210 | FS | 0
HKA-E1100 | HKA-E1210 | FS | 0
HKA-E1120 | HKA-E1210 | FS | 0
HKA-E1200 | HKA-E1210 | FS | 0
HKA-E1210 | HKA-P1010 | FS | 0
HKA-E1210 | HKA-P1020 | FS | 0
HKA-E1210 | HKA-P1030 | FS | 0
HKA-E1210 | HKA-P1040 | FS | 0
HKA-P1010 | HKA-P1050 | FS | 0
HKA-P1020 | HKA-P1050 | FS | 0
HKA-P1030 | HKA-P1050 | FS | 0
HKA-P1040 | HKA-P1050 | FS | 0
HKA-P1050 | HKA-P1060 | FS | 0
HKA-P1060 | HKA-P1070 | FS | 0
HKA-P1070 | HKA-P1100 | FS | 0
HKA-P1100 | HKA-C2010 | FS | 0
HKA-E1120 | HKA-X1010 | FS | 0
HKA-X1010 | HKA-X1020 | FS | 0
HKA-X1020 | HKA-C1010 | FS | 0
HKA-C2010 | HKA-C2020 | SS | 7
HKA-C1010 | HKA-C2020 | SS | 18
HKA-C1010 | HKA-C1020 | SS | 16
HKA-C2020 | HKA-C2030 | FS | 0
HKA-C1020 | HKA-C2030 | FS | 0
HKA-C2010 | HKA-C2040 | FS | 0
HKA-C2010 | HKA-C2050 | FS | 7
HKA-C2020 | HKA-C2100 | FS | 0
HKA-C2030 | HKA-C2100 | FS | 0
HKA-C2040 | HKA-C2100 | FS | 0
HKA-C2050 | HKA-C2100 | FS | 0
HKA-C1020 | HKA-C2100 | FS | 0
HKA-C2100 | HKA-T1010 | FS | 0
HKA-T1010 | HKA-T1020 | FS | 0
HKA-T1020 | HKA-T1100 | FS | 0
HKA-T1020 | HKA-T2010 | FS | 0
HKA-T1020 | HKA-T2020 | FS | 0
HKA-C2100 | HKA-E1130 | FS | 0
HKA-E1130 | HKA-E1140 | FS | 0
HKA-T1100 | HKA-T3010 | FS | 0
HKA-T2010 | HKA-T3010 | FS | 0
HKA-T2020 | HKA-T3010 | FS | 0
HKA-E1140 | HKA-T3010 | FS | 0
HKA-T3010 | HKA-T3100 | FS | 0
PRJ-A1060 | HMD-E1010 | FS | 0
PRJ-M1150 | HMD-E1010 | FS | 258
HMD-E1010 | HMD-E1020 | FS | 0
HMD-E1010 | HMD-E1030 | FS | 0
HMD-E1030 | HMD-E1040 | FS | 0
HMD-E1030 | HMD-E1050 | FS | 0
HMD-E1050 | HMD-E1060 | FS | 0
HMD-E1050 | HMD-E1070 | FS | 0
HMD-E1070 | HMD-E1080 | FS | 0
HMD-E1070 | HMD-E1090 | FS | 0
HMD-E1090 | HMD-E1100 | FS | 0
HMD-E1050 | HMD-E1110 | FS | 7
HMD-E1090 | HMD-E1110 | FF | 0
HMD-E1110 | HMD-E1120 | FS | 0
HMD-E1090 | HMD-E1200 | FS | 0
HMD-E1110 | HMD-E1200 | FS | 0
HMD-E1020 | HMD-E1210 | FS | 0
HMD-E1040 | HMD-E1210 | FS | 0
HMD-E1060 | HMD-E1210 | FS | 0
HMD-E1080 | HMD-E1210 | FS | 0
HMD-E1100 | HMD-E1210 | FS | 0
HMD-E1120 | HMD-E1210 | FS | 0
HMD-E1200 | HMD-E1210 | FS | 0
HMD-E1210 | HMD-P1010 | FS | 0
HMD-E1210 | HMD-P1020 | FS | 0
HMD-E1210 | HMD-P1030 | FS | 0
HMD-E1210 | HMD-P1040 | FS | 0
HMD-P1010 | HMD-P1050 | FS | 0
HMD-P1020 | HMD-P1050 | FS | 0
HMD-P1030 | HMD-P1050 | FS | 0
HMD-P1040 | HMD-P1050 | FS | 0
HMD-P1050 | HMD-P1060 | FS | 0
HMD-P1060 | HMD-P1070 | FS | 0
HMD-P1070 | HMD-P1100 | FS | 0
HMD-P1100 | HMD-C2010 | FS | 0
HMD-E1120 | HMD-X1010 | FS | 0
HMD-X1010 | HMD-X1020 | FS | 0
HMD-X1020 | HMD-C1010 | FS | 0
HMD-C2010 | HMD-C2020 | SS | 7
HMD-C1010 | HMD-C2020 | SS | 22
HMD-C1010 | HMD-C1020 | SS | 20
HMD-C2020 | HMD-C2030 | FS | 0
HMD-C1020 | HMD-C2030 | FS | 0
HMD-C2010 | HMD-C2040 | FS | 0
HMD-C2010 | HMD-C2050 | FS | 7
HMD-C2020 | HMD-C2100 | FS | 0
HMD-C2030 | HMD-C2100 | FS | 0
HMD-C2040 | HMD-C2100 | FS | 0
HMD-C2050 | HMD-C2100 | FS | 0
HMD-C1020 | HMD-C2100 | FS | 0
HMD-C2100 | HMD-T1010 | FS | 0
HMD-T1010 | HMD-T1020 | FS | 0
HMD-T1020 | HMD-T1100 | FS | 0
HMD-T1020 | HMD-T2010 | FS | 0
HMD-T1020 | HMD-T2020 | FS | 0
HMD-C2100 | HMD-E1130 | FS | 0
HMD-E1130 | HMD-E1140 | FS | 0
HMD-T1100 | HMD-T3010 | FS | 0
HMD-T2010 | HMD-T3010 | FS | 0
HMD-T2020 | HMD-T3010 | FS | 0
HMD-E1140 | HMD-T3010 | FS | 0
HMD-T3010 | HMD-T3100 | FS | 0
PRJ-A1060 | EAB-E1010 | FS | 0
PRJ-M1150 | EAB-E1010 | FS | 291
EAB-E1010 | EAB-E1020 | FS | 0
EAB-E1010 | EAB-E1030 | FS | 0
EAB-E1030 | EAB-E1040 | FS | 0
EAB-E1030 | EAB-E1050 | FS | 0
EAB-E1050 | EAB-E1060 | FS | 0
EAB-E1050 | EAB-E1070 | FS | 0
EAB-E1070 | EAB-E1080 | FS | 0
EAB-E1070 | EAB-E1090 | FS | 0
EAB-E1090 | EAB-E1100 | FS | 0
EAB-E1050 | EAB-E1110 | FS | 9
EAB-E1090 | EAB-E1110 | FF | 0
EAB-E1110 | EAB-E1120 | FS | 0
EAB-E1090 | EAB-E1200 | FS | 0
EAB-E1110 | EAB-E1200 | FS | 0
EAB-E1020 | EAB-E1210 | FS | 0
EAB-E1040 | EAB-E1210 | FS | 0
EAB-E1060 | EAB-E1210 | FS | 0
EAB-E1080 | EAB-E1210 | FS | 0
EAB-E1100 | EAB-E1210 | FS | 0
EAB-E1120 | EAB-E1210 | FS | 0
EAB-E1200 | EAB-E1210 | FS | 0
EAB-E1210 | EAB-P1010 | FS | 0
EAB-E1210 | EAB-P1020 | FS | 0
EAB-E1210 | EAB-P1030 | FS | 0
EAB-E1210 | EAB-P1040 | FS | 0
EAB-P1010 | EAB-P1050 | FS | 0
EAB-P1020 | EAB-P1050 | FS | 0
EAB-P1030 | EAB-P1050 | FS | 0
EAB-P1040 | EAB-P1050 | FS | 0
EAB-P1050 | EAB-P1060 | FS | 0
EAB-P1060 | EAB-P1070 | FS | 0
EAB-P1070 | EAB-P1100 | FS | 0
EAB-P1100 | EAB-C2010 | FS | 0
EAB-E1120 | EAB-X1010 | FS | 0
EAB-X1010 | EAB-X1020 | FS | 0
EAB-X1020 | EAB-C1010 | FS | 0
EAB-C2010 | EAB-C2020 | SS | 3
EAB-C1010 | EAB-C2020 | SS | 26
EAB-C1010 | EAB-C1020 | SS | 23
EAB-C2020 | EAB-C2030 | FS | 0
EAB-C1020 | EAB-C2030 | FS | 0
EAB-C2010 | EAB-C2040 | FS | 0
EAB-C2010 | EAB-C2050 | FS | 3
EAB-C2020 | EAB-C2100 | FS | 0
EAB-C2030 | EAB-C2100 | FS | 0
EAB-C2040 | EAB-C2100 | FS | 0
EAB-C2050 | EAB-C2100 | FS | 0
EAB-C1020 | EAB-C2100 | FS | 0
EAB-C2100 | EAB-T1010 | FS | 0
EAB-T1010 | EAB-T1020 | FS | 0
EAB-T1020 | EAB-T1100 | FS | 0
EAB-T1020 | EAB-T2010 | FS | 0
EAB-T1020 | EAB-T2020 | FS | 0
EAB-C2100 | EAB-E1130 | FS | 0
EAB-E1130 | EAB-E1140 | FS | 0
EAB-T1100 | EAB-T3010 | FS | 0
EAB-T2010 | EAB-T3010 | FS | 0
EAB-T2020 | EAB-T3010 | FS | 0
EAB-E1140 | EAB-T3010 | FS | 0
EAB-T3010 | EAB-T3100 | FS | 0
PRJ-A1060 | NHL-E1010 | FS | 0
PRJ-M1150 | NHL-E1010 | FS | 308
NHL-E1010 | NHL-E1020 | FS | 0
NHL-E1010 | NHL-E1030 | FS | 0
NHL-E1030 | NHL-E1040 | FS | 0
NHL-E1030 | NHL-E1050 | FS | 0
NHL-E1050 | NHL-E1060 | FS | 0
NHL-E1050 | NHL-E1070 | FS | 0
NHL-E1070 | NHL-E1080 | FS | 0
NHL-E1070 | NHL-E1090 | FS | 0
NHL-E1090 | NHL-E1100 | FS | 0
NHL-E1050 | NHL-E1110 | FS | 9
NHL-E1090 | NHL-E1110 | FF | 0
NHL-E1110 | NHL-E1120 | FS | 0
NHL-E1090 | NHL-E1200 | FS | 0
NHL-E1110 | NHL-E1200 | FS | 0
NHL-E1020 | NHL-E1210 | FS | 0
NHL-E1040 | NHL-E1210 | FS | 0
NHL-E1060 | NHL-E1210 | FS | 0
NHL-E1080 | NHL-E1210 | FS | 0
NHL-E1100 | NHL-E1210 | FS | 0
NHL-E1120 | NHL-E1210 | FS | 0
NHL-E1200 | NHL-E1210 | FS | 0
NHL-E1210 | NHL-P1010 | FS | 0
NHL-E1210 | NHL-P1020 | FS | 0
NHL-E1210 | NHL-P1030 | FS | 0
NHL-E1210 | NHL-P1040 | FS | 0
NHL-P1010 | NHL-P1050 | FS | 0
NHL-P1020 | NHL-P1050 | FS | 0
NHL-P1030 | NHL-P1050 | FS | 0
NHL-P1040 | NHL-P1050 | FS | 0
NHL-P1050 | NHL-P1060 | FS | 0
NHL-P1060 | NHL-P1070 | FS | 0
NHL-P1070 | NHL-P1100 | FS | 0
NHL-P1100 | NHL-C2010 | FS | 0
NHL-E1120 | NHL-X1010 | FS | 0
NHL-X1010 | NHL-X1020 | FS | 0
NHL-X1020 | NHL-C1010 | FS | 0
NHL-C2010 | NHL-C2020 | SS | 4
NHL-C1010 | NHL-C2020 | SS | 41
NHL-C1010 | NHL-C1020 | SS | 37
NHL-C2020 | NHL-C2030 | FS | 0
NHL-C1020 | NHL-C2030 | FS | 0
NHL-C2010 | NHL-C2040 | FS | 0
NHL-C2010 | NHL-C2050 | FS | 4
NHL-C2020 | NHL-C2100 | FS | 0
NHL-C2030 | NHL-C2100 | FS | 0
NHL-C2040 | NHL-C2100 | FS | 0
NHL-C2050 | NHL-C2100 | FS | 0
NHL-C1020 | NHL-C2100 | FS | 0
NHL-C2100 | NHL-T1010 | FS | 0
NHL-T1010 | NHL-T1020 | FS | 0
NHL-T1020 | NHL-T1100 | FS | 0
NHL-T1020 | NHL-T2010 | FS | 0
NHL-T1020 | NHL-T2020 | FS | 0
NHL-C2100 | NHL-E1130 | FS | 0
NHL-E1130 | NHL-E1140 | FS | 0
NHL-T1100 | NHL-T3010 | FS | 0
NHL-T2010 | NHL-T3010 | FS | 0
NHL-T2020 | NHL-T3010 | FS | 0
NHL-E1140 | NHL-T3010 | FS | 0
NHL-T3010 | NHL-T3100 | FS | 0
PRJ-A1060 | NJF-E1010 | FS | 0
PRJ-M1150 | NJF-E1010 | FS | 358
NJF-E1010 | NJF-E1020 | FS | 0
NJF-E1010 | NJF-E1030 | FS | 0
NJF-E1030 | NJF-E1040 | FS | 0
NJF-E1030 | NJF-E1050 | FS | 0
NJF-E1050 | NJF-E1060 | FS | 0
NJF-E1050 | NJF-E1070 | FS | 0
NJF-E1070 | NJF-E1080 | FS | 0
NJF-E1070 | NJF-E1090 | FS | 0
NJF-E1090 | NJF-E1100 | FS | 0
NJF-E1050 | NJF-E1110 | FS | 10
NJF-E1090 | NJF-E1110 | FF | 0
NJF-E1110 | NJF-E1120 | FS | 0
NJF-E1090 | NJF-E1200 | FS | 0
NJF-E1110 | NJF-E1200 | FS | 0
NJF-E1020 | NJF-E1210 | FS | 0
NJF-E1040 | NJF-E1210 | FS | 0
NJF-E1060 | NJF-E1210 | FS | 0
NJF-E1080 | NJF-E1210 | FS | 0
NJF-E1100 | NJF-E1210 | FS | 0
NJF-E1120 | NJF-E1210 | FS | 0
NJF-E1200 | NJF-E1210 | FS | 0
NJF-E1210 | NJF-P1010 | FS | 0
NJF-E1210 | NJF-P1020 | FS | 0
NJF-E1210 | NJF-P1030 | FS | 0
NJF-E1210 | NJF-P1040 | FS | 0
NJF-P1010 | NJF-P1050 | FS | 0
NJF-P1020 | NJF-P1050 | FS | 0
NJF-P1030 | NJF-P1050 | FS | 0
NJF-P1040 | NJF-P1050 | FS | 0
NJF-P1050 | NJF-P1060 | FS | 0
NJF-P1060 | NJF-P1070 | FS | 0
NJF-P1070 | NJF-P1100 | FS | 0
NJF-P1100 | NJF-C2010 | FS | 0
NJF-E1120 | NJF-X1010 | FS | 0
NJF-X1010 | NJF-X1020 | FS | 0
NJF-X1020 | NJF-C1010 | FS | 0
NJF-C2010 | NJF-C2020 | SS | 4
NJF-C1010 | NJF-C2020 | SS | 41
NJF-C1010 | NJF-C1020 | SS | 37
NJF-C2020 | NJF-C2030 | FS | 0
NJF-C1020 | NJF-C2030 | FS | 0
NJF-C2010 | NJF-C2040 | FS | 0
NJF-C2010 | NJF-C2050 | FS | 4
NJF-C2020 | NJF-C2100 | FS | 0
NJF-C2030 | NJF-C2100 | FS | 0
NJF-C2040 | NJF-C2100 | FS | 0
NJF-C2050 | NJF-C2100 | FS | 0
NJF-C1020 | NJF-C2100 | FS | 0
NJF-C2100 | NJF-T1010 | FS | 0
NJF-T1010 | NJF-T1020 | FS | 0
NJF-T1020 | NJF-T1100 | FS | 0
NJF-T1020 | NJF-T2010 | FS | 0
NJF-T1020 | NJF-T2020 | FS | 0
NJF-C2100 | NJF-E1130 | FS | 0
NJF-E1130 | NJF-E1140 | FS | 0
NJF-T1100 | NJF-T3010 | FS | 0
NJF-T2010 | NJF-T3010 | FS | 0
NJF-T2020 | NJF-T3010 | FS | 0
NJF-E1140 | NJF-T3010 | FS | 0
NJF-T3010 | NJF-T3100 | FS | 0
PRJ-A1060 | NQR-E1010 | FS | 0
PRJ-M1150 | NQR-E1010 | FS | 391
NQR-E1010 | NQR-E1020 | FS | 0
NQR-E1010 | NQR-E1030 | FS | 0
NQR-E1030 | NQR-E1040 | FS | 0
NQR-E1030 | NQR-E1050 | FS | 0
NQR-E1050 | NQR-E1060 | FS | 0
NQR-E1050 | NQR-E1070 | FS | 0
NQR-E1070 | NQR-E1080 | FS | 0
NQR-E1070 | NQR-E1090 | FS | 0
NQR-E1090 | NQR-E1100 | FS | 0
NQR-E1050 | NQR-E1110 | FS | 10
NQR-E1090 | NQR-E1110 | FF | 0
NQR-E1110 | NQR-E1120 | FS | 0
NQR-E1090 | NQR-E1200 | FS | 0
NQR-E1110 | NQR-E1200 | FS | 0
NQR-E1020 | NQR-E1210 | FS | 0
NQR-E1040 | NQR-E1210 | FS | 0
NQR-E1060 | NQR-E1210 | FS | 0
NQR-E1080 | NQR-E1210 | FS | 0
NQR-E1100 | NQR-E1210 | FS | 0
NQR-E1120 | NQR-E1210 | FS | 0
NQR-E1200 | NQR-E1210 | FS | 0
NQR-E1210 | NQR-P1010 | FS | 0
NQR-E1210 | NQR-P1020 | FS | 0
NQR-E1210 | NQR-P1030 | FS | 0
NQR-E1210 | NQR-P1040 | FS | 0
NQR-P1010 | NQR-P1050 | FS | 0
NQR-P1020 | NQR-P1050 | FS | 0
NQR-P1030 | NQR-P1050 | FS | 0
NQR-P1040 | NQR-P1050 | FS | 0
NQR-P1050 | NQR-P1060 | FS | 0
NQR-P1060 | NQR-P1070 | FS | 0
NQR-P1070 | NQR-P1100 | FS | 0
NQR-P1100 | NQR-C2010 | FS | 0
NQR-E1120 | NQR-X1010 | FS | 0
NQR-X1010 | NQR-X1020 | FS | 0
NQR-X1020 | NQR-C1010 | FS | 0
NQR-C2010 | NQR-C2020 | SS | 4
NQR-C1010 | NQR-C2020 | SS | 41
NQR-C1010 | NQR-C1020 | SS | 37
NQR-C2020 | NQR-C2030 | FS | 0
NQR-C1020 | NQR-C2030 | FS | 0
NQR-C2010 | NQR-C2040 | FS | 0
NQR-C2010 | NQR-C2050 | FS | 4
NQR-C2020 | NQR-C2100 | FS | 0
NQR-C2030 | NQR-C2100 | FS | 0
NQR-C2040 | NQR-C2100 | FS | 0
NQR-C2050 | NQR-C2100 | FS | 0
NQR-C1020 | NQR-C2100 | FS | 0
NQR-C2100 | NQR-T1010 | FS | 0
NQR-T1010 | NQR-T1020 | FS | 0
NQR-T1020 | NQR-T1100 | FS | 0
NQR-T1020 | NQR-T2010 | FS | 0
NQR-T1020 | NQR-T2020 | FS | 0
NQR-C2100 | NQR-E1130 | FS | 0
NQR-E1130 | NQR-E1140 | FS | 0
NQR-T1100 | NQR-T3010 | FS | 0
NQR-T2010 | NQR-T3010 | FS | 0
NQR-T2020 | NQR-T3010 | FS | 0
NQR-E1140 | NQR-T3010 | FS | 0
NQR-T3010 | NQR-T3100 | FS | 0
NRY-T3100 | PRJ-C1010 | FS | 0
HMK-T3100 | PRJ-C1010 | FS | 0
ERY-T3100 | PRJ-C1010 | FS | 0
HJD-T3100 | PRJ-C1010 | FS | 0
EDM-T3100 | PRJ-C1010 | FS | 0
NQS-T3100 | PRJ-C1010 | FS | 0
EHF-T3100 | PRJ-C1010 | FS | 0
NMJ-T3100 | PRJ-C1010 | FS | 0
HKA-T3100 | PRJ-C1010 | FS | 0
HMD-T3100 | PRJ-C1010 | FS | 0
EAB-T3100 | PRJ-C1010 | FS | 0
NHL-T3100 | PRJ-C1010 | FS | 0
NJF-T3100 | PRJ-C1010 | FS | 0
NQR-T3100 | PRJ-C1010 | FS | 0
PRJ-C1010 | PRJ-MX99 | FS | 0
PRJ-M1250 | PRJ-MX99 | FS | 0
PRJ-M2100 | PRJ-MX99 | FS | 0
PRJ-M0000 | PRJ-MX99 | FS | 750

## Invoicing_Monthly
Invoices per month, detailed: each payment milestone is invoiced in the month its milestone activity is achieved in the programme
Amount = clause 15 payment milestone x Annex 3 station price (formulas link to Payment_Milestones). Invoice month = month of the trigger milestone date. Payment terms after invoicing (days to pay) are not modelled.
Invoice month | Milestone date | Milestone | Description | Station | Railway | Trigger activity ID | Trigger activity | Invoice amount (SAR) | Cumulative (SAR) | Cumulative %
2026-12-01 | 2026-12-13 | MS1 | Mobilization | All stations | Project | PRJ-M1100 | MS1 Mobilization complete (payment milestone 20%)
2027-04-01 | 2027-04-11 | MS2 | Engineering submittal | Riyadh (Thumamah) (NRY) | NSR | NRY-E1200 | MS2 Engineering submittal complete (10%) - Riyadh (Thumamah)
2027-04-01 | 2027-04-11 | MS2 | Engineering submittal | Makkah (HMK) | HHR | HMK-E1200 | MS2 Engineering submittal complete (10%) - Makkah
2027-04-01 | 2027-04-11 | MS2 | Engineering submittal | Riyadh (Malaz) (ERY) | EWR | ERY-E1200 | MS2 Engineering submittal complete (10%) - Riyadh (Malaz)
2027-05-01 | 2027-05-02 | MS3 | SAR approval of engineering | Riyadh (Thumamah) (NRY) | NSR | NRY-E1210 | MS3 Engineering approved by SAR (10%) - Riyadh (Thumamah)
2027-05-01 | 2027-05-02 | MS3 | SAR approval of engineering | Makkah (HMK) | HHR | HMK-E1210 | MS3 Engineering approved by SAR (10%) - Makkah
2027-05-01 | 2027-05-02 | MS3 | SAR approval of engineering | Riyadh (Malaz) (ERY) | EWR | ERY-E1210 | MS3 Engineering approved by SAR (10%) - Riyadh (Malaz)
2027-06-01 | 2027-06-06 | MS2 | Engineering submittal | Jeddah (HJD) | HHR | HJD-E1200 | MS2 Engineering submittal complete (10%) - Jeddah
2027-06-01 | 2027-06-27 | MS3 | SAR approval of engineering | Jeddah (HJD) | HHR | HJD-E1210 | MS3 Engineering approved by SAR (10%) - Jeddah
2027-08-01 | 2027-08-25 | MS4 | Material delivery | Riyadh (Malaz) (ERY) | EWR | ERY-P1100 | MS4 Material delivered (20%) - Riyadh (Malaz)
2027-09-01 | 2027-09-02 | MS4 | Material delivery | Riyadh (Thumamah) (NRY) | NSR | NRY-P1100 | MS4 Material delivered (20%) - Riyadh (Thumamah)
2027-09-01 | 2027-09-21 | MS2 | Engineering submittal | Dammam (EDM) | EWR | EDM-E1200 | MS2 Engineering submittal complete (10%) - Dammam
2027-10-01 | 2027-10-13 | MS3 | SAR approval of engineering | Dammam (EDM) | EWR | EDM-E1210 | MS3 Engineering approved by SAR (10%) - Dammam
2027-10-01 | 2027-10-19 | MS5 | Installation | Riyadh (Malaz) (ERY) | EWR | ERY-C2100 | MS5 Installation complete (20%) - Riyadh (Malaz)
2027-11-01 | 2027-11-04 | MS5 | Installation | Riyadh (Thumamah) (NRY) | NSR | NRY-C2100 | MS5 Installation complete (20%) - Riyadh (Thumamah)
2027-11-01 | 2027-11-04 | MS6 | Testing and commissioning (SAT) | Riyadh (Malaz) (ERY) | EWR | ERY-T1100 | MS6 SAT complete (10%) - Riyadh (Malaz)
2027-11-01 | 2027-11-09 | MS4 | Material delivery | Makkah (HMK) | HHR | HMK-P1100 | MS4 Material delivered (20%) - Makkah
2027-11-01 | 2027-11-14 | MS2 | Engineering submittal | Al Qassim (NQS) | NSR | NQS-E1200 | MS2 Engineering submittal complete (10%) - Al Qassim
2027-11-01 | 2027-11-14 | MS2 | Engineering submittal | Hufuf (EHF) | EWR | EHF-E1200 | MS2 Engineering submittal complete (10%) - Hufuf
2027-12-01 | 2027-12-05 | MS3 | SAR approval of engineering | Al Qassim (NQS) | NSR | NQS-E1210 | MS3 Engineering approved by SAR (10%) - Al Qassim
2027-12-01 | 2027-12-05 | MS3 | SAR approval of engineering | Hufuf (EHF) | EWR | EHF-E1210 | MS3 Engineering approved by SAR (10%) - Hufuf
2027-12-01 | 2027-12-06 | MS6 | Testing and commissioning (SAT) | Riyadh (Thumamah) (NRY) | NSR | NRY-T1100 | MS6 SAT complete (10%) - Riyadh (Thumamah)
2027-12-01 | 2027-12-27 | MS4 | Material delivery | Jeddah (HJD) | HHR | HJD-P1100 | MS4 Material delivered (20%) - Jeddah
2027-12-01 | 2027-12-30 | MS2 | Engineering submittal | Al Majma'ah (NMJ) | NSR | NMJ-E1200 | MS2 Engineering submittal complete (10%) - Al Majma'ah
2028-01-01 | 2028-01-17 | MS7 | Final acceptance and handover | Riyadh (Malaz) (ERY) | EWR | ERY-T3100 | MS7 Station accepted - final acceptance and handover (10%) - Riyadh (Malaz)
2028-01-01 | 2028-01-20 | MS3 | SAR approval of engineering | Al Majma'ah (NMJ) | NSR | NMJ-E1210 | MS3 Engineering approved by SAR (10%) - Al Majma'ah
2028-01-01 | 2028-01-31 | MS4 | Material delivery | Dammam (EDM) | EWR | EDM-P1100 | MS4 Material delivered (20%) - Dammam
2028-02-01 | 2028-02-03 | MS7 | Final acceptance and handover | Riyadh (Thumamah) (NRY) | NSR | NRY-T3100 | MS7 Station accepted - final acceptance and handover (10%) - Riyadh (Thumamah)
2028-03-01 | 2028-03-08 | MS5 | Installation | Makkah (HMK) | HHR | HMK-C2100 | MS5 Installation complete (20%) - Makkah
2028-03-01 | 2028-03-27 | MS4 | Material delivery | Hufuf (EHF) | EWR | EHF-P1100 | MS4 Material delivered (20%) - Hufuf
2028-03-01 | 2028-03-30 | MS5 | Installation | Dammam (EDM) | EWR | EDM-C2100 | MS5 Installation complete (20%) - Dammam
2028-04-01 | 2028-04-06 | MS4 | Material delivery | Al Qassim (NQS) | NSR | NQS-P1100 | MS4 Material delivered (20%) - Al Qassim
2028-04-01 | 2028-04-06 | MS5 | Installation | Jeddah (HJD) | HHR | HJD-C2100 | MS5 Installation complete (20%) - Jeddah
2028-04-01 | 2028-04-17 | MS6 | Testing and commissioning (SAT) | Dammam (EDM) | EWR | EDM-T1100 | MS6 SAT complete (10%) - Dammam
2028-04-01 | 2028-04-18 | MS2 | Engineering submittal | KAEC (HKA) | HHR | HKA-E1200 | MS2 Engineering submittal complete (10%) - KAEC
2028-04-01 | 2028-04-18 | MS2 | Engineering submittal | Madinah (HMD) | HHR | HMD-E1200 | MS2 Engineering submittal complete (10%) - Madinah
2028-04-01 | 2028-04-19 | MS6 | Testing and commissioning (SAT) | Makkah (HMK) | HHR | HMK-T1100 | MS6 SAT complete (10%) - Makkah
2028-05-01 | 2028-05-16 | MS3 | SAR approval of engineering | KAEC (HKA) | HHR | HKA-E1210 | MS3 Engineering approved by SAR (10%) - KAEC
2028-05-01 | 2028-05-16 | MS3 | SAR approval of engineering | Madinah (HMD) | HHR | HMD-E1210 | MS3 Engineering approved by SAR (10%) - Madinah
2028-05-01 | 2028-05-21 | MS6 | Testing and commissioning (SAT) | Jeddah (HJD) | HHR | HJD-T1100 | MS6 SAT complete (10%) - Jeddah
2028-05-01 | 2028-05-23 | MS5 | Installation | Hufuf (EHF) | EWR | EHF-C2100 | MS5 Installation complete (20%) - Hufuf
2028-05-01 | 2028-05-31 | MS4 | Material delivery | Al Majma'ah (NMJ) | NSR | NMJ-P1100 | MS4 Material delivered (20%) - Al Majma'ah
2028-06-01 | 2028-06-08 | MS6 | Testing and commissioning (SAT) | Hufuf (EHF) | EWR | EHF-T1100 | MS6 SAT complete (10%) - Hufuf
2028-06-01 | 2028-06-14 | MS5 | Installation | Al Qassim (NQS) | NSR | NQS-C2100 | MS5 Installation complete (20%) - Al Qassim
2028-06-01 | 2028-06-18 | MS2 | Engineering submittal | Abqaiq (EAB) | EWR | EAB-E1200 | MS2 Engineering submittal complete (10%) - Abqaiq
2028-07-01 | 2028-07-03 | MS6 | Testing and commissioning (SAT) | Al Qassim (NQS) | NSR | NQS-T1100 | MS6 SAT complete (10%) - Al Qassim
2028-07-01 | 2028-07-05 | MS7 | Final acceptance and handover | Dammam (EDM) | EWR | EDM-T3100 | MS7 Station accepted - final acceptance and handover (10%) - Dammam
2028-07-01 | 2028-07-09 | MS3 | SAR approval of engineering | Abqaiq (EAB) | EWR | EAB-E1210 | MS3 Engineering approved by SAR (10%) - Abqaiq
2028-07-01 | 2028-07-09 | MS7 | Final acceptance and handover | Makkah (HMK) | HHR | HMK-T3100 | MS7 Station accepted - final acceptance and handover (10%) - Makkah
2028-07-01 | 2028-07-12 | MS2 | Engineering submittal | Hail (NHL) | NSR | NHL-E1200 | MS2 Engineering submittal complete (10%) - Hail
2028-08-01 | 2028-08-01 | MS5 | Installation | Al Majma'ah (NMJ) | NSR | NMJ-C2100 | MS5 Installation complete (20%) - Al Majma'ah
2028-08-01 | 2028-08-01 | MS7 | Final acceptance and handover | Jeddah (HJD) | HHR | HJD-T3100 | MS7 Station accepted - final acceptance and handover (10%) - Jeddah
2028-08-01 | 2028-08-02 | MS3 | SAR approval of engineering | Hail (NHL) | NSR | NHL-E1210 | MS3 Engineering approved by SAR (10%) - Hail
2028-08-01 | 2028-08-20 | MS6 | Testing and commissioning (SAT) | Al Majma'ah (NMJ) | NSR | NMJ-T1100 | MS6 SAT complete (10%) - Al Majma'ah
2028-08-01 | 2028-08-21 | MS7 | Final acceptance and handover | Hufuf (EHF) | EWR | EHF-T3100 | MS7 Station accepted - final acceptance and handover (10%) - Hufuf
2028-09-01 | 2028-09-13 | MS7 | Final acceptance and handover | Al Qassim (NQS) | NSR | NQS-T3100 | MS7 Station accepted - final acceptance and handover (10%) - Al Qassim
2028-09-01 | 2028-09-27 | MS2 | Engineering submittal | Al Jouf (NJF) | NSR | NJF-E1200 | MS2 Engineering submittal complete (10%) - Al Jouf
2028-10-01 | 2028-10-04 | MS4 | Material delivery | Madinah (HMD) | HHR | HMD-P1100 | MS4 Material delivered (20%) - Madinah
2028-10-01 | 2028-10-05 | MS4 | Material delivery | KAEC (HKA) | HHR | HKA-P1100 | MS4 Material delivered (20%) - KAEC
2028-10-01 | 2028-10-18 | MS3 | SAR approval of engineering | Al Jouf (NJF) | NSR | NJF-E1210 | MS3 Engineering approved by SAR (10%) - Al Jouf
2028-10-01 | 2028-10-18 | MS4 | Material delivery | Abqaiq (EAB) | EWR | EAB-P1100 | MS4 Material delivered (20%) - Abqaiq
2028-10-01 | 2028-10-31 | MS7 | Final acceptance and handover | Al Majma'ah (NMJ) | NSR | NMJ-T3100 | MS7 Station accepted - final acceptance and handover (10%) - Al Majma'ah
2028-11-01 | 2028-11-12 | MS2 | Engineering submittal | Al Qurayyat (NQR) | NSR | NQR-E1200 | MS2 Engineering submittal complete (10%) - Al Qurayyat
2028-11-01 | 2028-11-23 | MS5 | Installation | Abqaiq (EAB) | EWR | EAB-C2100 | MS5 Installation complete (20%) - Abqaiq
2028-11-01 | 2028-11-28 | MS4 | Material delivery | Hail (NHL) | NSR | NHL-P1100 | MS4 Material delivered (20%) - Hail
2028-12-01 | 2028-12-03 | MS3 | SAR approval of engineering | Al Qurayyat (NQR) | NSR | NQR-E1210 | MS3 Engineering approved by SAR (10%) - Al Qurayyat
2028-12-01 | 2028-12-10 | MS6 | Testing and commissioning (SAT) | Abqaiq (EAB) | EWR | EAB-T1100 | MS6 SAT complete (10%) - Abqaiq
2029-01-01 | 2029-01-09 | MS5 | Installation | KAEC (HKA) | HHR | HKA-C2100 | MS5 Installation complete (20%) - KAEC
2029-01-01 | 2029-01-14 | MS5 | Installation | Madinah (HMD) | HHR | HMD-C2100 | MS5 Installation complete (20%) - Madinah
2029-01-01 | 2029-01-29 | MS5 | Installation | Hail (NHL) | NSR | NHL-C2100 | MS5 Installation complete (20%) - Hail
2029-02-01 | 2029-02-06 | MS6 | Testing and commissioning (SAT) | KAEC (HKA) | HHR | HKA-T1100 | MS6 SAT complete (10%) - KAEC
2029-02-01 | 2029-02-19 | MS6 | Testing and commissioning (SAT) | Madinah (HMD) | HHR | HMD-T1100 | MS6 SAT complete (10%) - Madinah
2029-02-01 | 2029-02-20 | MS4 | Material delivery | Al Jouf (NJF) | NSR | NJF-P1100 | MS4 Material delivered (20%) - Al Jouf
2029-02-01 | 2029-02-25 | MS6 | Testing and commissioning (SAT) | Hail (NHL) | NSR | NHL-T1100 | MS6 SAT complete (10%) - Hail
2029-02-01 | 2029-02-28 | MS7 | Final acceptance and handover | Abqaiq (EAB) | EWR | EAB-T3100 | MS7 Station accepted - final acceptance and handover (10%) - Abqaiq
2029-04-01 | 2029-04-08 | MS4 | Material delivery | Al Qurayyat (NQR) | NSR | NQR-P1100 | MS4 Material delivered (20%) - Al Qurayyat
2029-05-01 | 2029-05-01 | MS5 | Installation | Al Jouf (NJF) | NSR | NJF-C2100 | MS5 Installation complete (20%) - Al Jouf
2029-05-01 | 2029-05-06 | MS7 | Final acceptance and handover | KAEC (HKA) | HHR | HKA-T3100 | MS7 Station accepted - final acceptance and handover (10%) - KAEC
2029-05-01 | 2029-05-10 | MS7 | Final acceptance and handover | Madinah (HMD) | HHR | HMD-T3100 | MS7 Station accepted - final acceptance and handover (10%) - Madinah
2029-05-01 | 2029-05-15 | MS7 | Final acceptance and handover | Hail (NHL) | NSR | NHL-T3100 | MS7 Station accepted - final acceptance and handover (10%) - Hail
2029-05-01 | 2029-05-20 | MS6 | Testing and commissioning (SAT) | Al Jouf (NJF) | NSR | NJF-T1100 | MS6 SAT complete (10%) - Al Jouf
2029-06-01 | 2029-06-14 | MS5 | Installation | Al Qurayyat (NQR) | NSR | NQR-C2100 | MS5 Installation complete (20%) - Al Qurayyat
2029-07-01 | 2029-07-03 | MS6 | Testing and commissioning (SAT) | Al Qurayyat (NQR) | NSR | NQR-T1100 | MS6 SAT complete (10%) - Al Qurayyat
2029-07-01 | 2029-07-31 | MS7 | Final acceptance and handover | Al Jouf (NJF) | NSR | NJF-T3100 | MS7 Station accepted - final acceptance and handover (10%) - Al Jouf
2029-09-01 | 2029-09-13 | MS7 | Final acceptance and handover | Al Qurayyat (NQR) | NSR | NQR-T3100 | MS7 Station accepted - final acceptance and handover (10%) - Al Qurayyat
Total
Difference to contract price (should be 0)
Monthly invoicing by payment milestone
Month | MS1 | MS2 | MS3 | MS4 | MS5 | MS6 | MS7 | Invoiced in month (SAR) | Cumulative invoiced (SAR) | Cumulative %
2026-11-01
2026-12-01
2027-01-01
2027-02-01
2027-03-01
2027-04-01
2027-05-01
2027-06-01
2027-07-01
2027-08-01
2027-09-01
2027-10-01
2027-11-01
2027-12-01
2028-01-01
2028-02-01
2028-03-01
2028-04-01
2028-05-01
2028-06-01
2028-07-01
2028-08-01
2028-09-01
2028-10-01
2028-11-01
2028-12-01
2029-01-01
2029-02-01
2029-03-01
2029-04-01
2029-05-01
2029-06-01
2029-07-01
2029-08-01
2029-09-01
2029-10-01
Total
Monthly invoicing by station (MS2 to MS7 per station, MS1 shown as project level)
Month | All stations | Riyadh (Thumamah) (NRY) | Makkah (HMK) | Riyadh (Malaz) (ERY) | Jeddah (HJD) | Dammam (EDM) | Al Qassim (NQS) | Hufuf (EHF) | Al Majma'ah (NMJ) | KAEC (HKA) | Madinah (HMD) | Abqaiq (EAB) | Hail (NHL) | Al Jouf (NJF) | Al Qurayyat (NQR) | Total
2026-11-01
2026-12-01
2027-01-01
2027-02-01
2027-03-01
2027-04-01
2027-05-01
2027-06-01
2027-07-01
2027-08-01
2027-09-01
2027-10-01
2027-11-01
2027-12-01
2028-01-01
2028-02-01
2028-03-01
2028-04-01
2028-05-01
2028-06-01
2028-07-01
2028-08-01
2028-09-01
2028-10-01
2028-11-01
2028-12-01
2029-01-01
2029-02-01
2029-03-01
2029-04-01
2029-05-01
2029-06-01
2029-07-01
2029-08-01
2029-09-01
2029-10-01
Total