Saudi Arabia Railways (SAR)
0580-Security Technology Salutation after eliminating Passenger Checking Roles
Contract with ETECHS

Baseline Programme Narrative
For SAR review and approval

Project 0580  |  Rev 1  |  Data date and NTP: 01 November 2026  |  P6 file: 0580_Schedule_Baseline_Rev1.xer

# 1. Purpose and basis of the programme

This narrative describes the baseline programme (Rev 1) of project 0580-Security Technology Salutation after eliminating Passenger Checking Roles, covering 14 stations on three railways (North South Railway, East West Railway and Haramain High Speed Rail). It is delivered as a Primavera P6 24 XER file with 591 activities (500 tasks and 91 milestones) and 912 logic links. It runs from the Notice to Proceed milestone on 01 Nov 2026 to the contract completion milestone on 31 Oct 2029.

Source: the contract file only (conditions, Annex 2 scope of work, Annex 3 price table, Annex 4 clarifications, Annex 5 compliance table), plus the planning instructions of the Contractor in this revision. Durations, logic and station sequence are Contractor planning assumptions offered for SAR approval. They are not contract-stated, except the 36 month term, the payment milestones and the 21 day review period.

# 2. Changes in this revision

| Item | Change |
| --- | --- |
| First six months | Months 1-2 mobilization and the survey access permit (the permit takes two months); months 3-6 design (four months) which starts with the site survey. Milestones: mobilization and permits complete, design complete. |
| Design rule | At every station: two months of mobilization and survey, then four months of design starting two months after the station mobilization starts; enabling works start after the HCIS documents (finish to start) and construction follows the enabling works. At the priority stations this is months 1-2 and 3-6 of the project for permit and design. |
| Priority | Makkah and Riyadh (Thumamah) are Priority 1 and run works in parallel with design. Riyadh (Malaz) is Priority 2. |
| Review period | Every SAR review of a submission is 21 days (15 working days). Survey approval was 5 days and is now 21 days. |
| WBS | Stations are now level 3 of the WBS (project, EPC phase, station). Priority and railway are activity codes. |
| Identity | Project number 0580 and the official name on every output. Programme phase added as an activity code. |

# 3. Key dates and milestones

| ID | Milestone | Date |
| --- | --- | --- |
| PRJ-M0000 | Notice to Proceed - project start (1 Nov 2026, editable) | 01 Nov 2026 |
| PRJ-M1100 | MS1 Mobilization complete (payment milestone 20%) | 10 Dec 2026 |
| PRJ-M1150 | Mobilization and survey permits complete (end of month 2) | 31 Dec 2026 |
| PRJ-M2100 | Detailed baseline programme approved | 11 Feb 2027 |
| PRJ-M1250 | Design complete - priority stations (end of month 6) | 29 Apr 2027 |
| PRJ-MX99 | Contract completion - end of 36-month term | 31 Oct 2029 |

Contract completion is driven by logic: it is linked from NTP with a lag equal to the 36 month term and carries no date constraint. If the NTP date changes, every date moves with it.

# 4. The first six months

| Phase | Start | Finish | Content |
| --- | --- | --- | --- |
| Mobilization and survey permit (months 1-2) | 01 Nov 2026 | 31 Dec 2026 | Mobilization, initial baseline, and the two month site access permit for the surveys, applied for once for the whole project |
| Design including survey (months 3-6) | 03 Jan 2027 | 29 Apr 2027 | Site survey, concept, preliminary, detailed and IFC design with HCIS documents; each stage submitted and approved in 21 days |
| Enabling works (after the HCIS documents) | 02 May 2027 | 10 Jun 2027 | Site preparation, setting out, temporary works, cable routes, duct banks and plinths, starting when the HCIS documents are approved (finish to start); civil construction follows |

The survey needs a site access permit and the permit takes two months, so months 1 and 2 are mobilization and the permit (one project-level activity, PRJ-A1060, in the Mobilization branch of the WBS; there is no permit activity per station). The survey is the first part of design, so the survey and design start when the permit is granted and lasts four months in total, survey included. At the priority stations the two month window is held by milestone PRJ-M1150; the other stations start design in their wave, with the permit already in hand. Enabling works start two months before the end of design, so design and execution overlap by two months. No date constraint is used.

# 5. Priority stations

Priority 1: Makkah (Haramain) and Riyadh (Thumamah, North South Railway). Their permits are applied for first and their enabling and civil works run in parallel with design. Equipment is manufactured only after SAR approval of the engineering (milestone MS3), so no equipment is ordered before approval. Priority 2: Riyadh (Malaz, East West Railway), permitted in the same two months. The remaining stations start in waves counted from the end of mobilization, each with the same four month design.

| Station | Railway | Priority | Design start | Station finish |
| --- | --- | --- | --- | --- |
| Riyadh (Thumamah) | NSR | Priority 1 | 03 Jan 2027 | 02 Feb 2028 |
| Makkah | HHR | Priority 1 | 03 Jan 2027 | 06 Jul 2028 |
| Riyadh (Malaz) | EWR | Priority 2 | 03 Jan 2027 | 16 Jan 2028 |
| Jeddah | HHR | Standard | 25 Feb 2027 | 31 Jul 2028 |
| Dammam | EWR | Standard | 13 Jun 2027 | 04 Jul 2028 |
| Al Qassim | NSR | Standard | 04 Aug 2027 | 12 Sep 2028 |
| Hufuf | EWR | Standard | 04 Aug 2027 | 20 Aug 2028 |
| Al Majma'ah | NSR | Standard | 20 Sep 2027 | 30 Oct 2028 |
| KAEC | HHR | Standard | 16 Jan 2028 | 03 May 2029 |
| Madinah | HHR | Standard | 16 Jan 2028 | 09 May 2029 |
| Abqaiq | EWR | Standard | 08 Mar 2028 | 27 Feb 2029 |
| Hail | NSR | Standard | 02 Apr 2028 | 14 May 2029 |
| Al Jouf | NSR | Standard | 18 Jun 2028 | 30 Jul 2029 |
| Al Qurayyat | NSR | Standard | 02 Aug 2028 | 12 Sep 2029 |

# 6. Activity durations from station quantities

Durations are driven by the BOQ quantities of each station (Annex 3), in working days (Sunday to Thursday). Survey: 5 days plus 1 day per 30 cameras. Design is fixed at four calendar months for every station, survey included. Manufacture lead time: 40 days plus 1 day per SAR 100,000 of equipment (cameras, VMS, access control, UPS and network), capped at 100. Shipping and customs: 20 days plus 1 day per SAR 250,000 of equipment. Civil works: 20 days plus 1 day per SAR 12,000 of civil works. Installation: 15 days plus 3 cameras per crew per day, with 1 crew below 150 cameras, 2 crews up to 349 and 3 crews from 350. SAT: 10 days plus 1 day per 30 cameras. Training 10 days, trial operation 30 days and taking over 22 days (SAR issues the certificate within 30 calendar days of the application, clause 12.3) are fixed. The productivity rates are Contractor planning assumptions.

| Station | Cameras | Equip. SAR M | Civil SAR M | Survey | Manuf. | Ship | Civil | Install | SAT |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Riyadh (Thumamah) | 88 | 1.72 | 0.75 | 8 | 57 | 27 | 82 | 44 | 13 |
| Makkah | 596 | 5.07 | 0.57 | 25 | 91 | 40 | 68 | 81 | 30 |
| Riyadh (Malaz) | 68 | 1.27 | 0.70 | 8 | 53 | 25 | 78 | 38 | 12 |
| Jeddah | 475 | 5.03 | 0.52 | 21 | 90 | 40 | 63 | 68 | 26 |
| Dammam | 68 | 1.33 | 0.70 | 8 | 53 | 25 | 78 | 38 | 12 |
| Al Qassim | 88 | 1.66 | 0.75 | 8 | 57 | 27 | 82 | 44 | 13 |
| Hufuf | 60 | 1.14 | 0.66 | 8 | 51 | 25 | 75 | 35 | 12 |
| Al Majma'ah | 88 | 1.66 | 0.75 | 8 | 57 | 27 | 82 | 44 | 13 |
| KAEC | 314 | 3.05 | 0.19 | 15 | 70 | 32 | 36 | 67 | 20 |
| Madinah | 340 | 2.94 | 0.29 | 16 | 69 | 32 | 44 | 72 | 21 |
| Abqaiq | 32 | 0.90 | 0.38 | 8 | 49 | 24 | 51 | 26 | 11 |
| Hail | 88 | 1.66 | 0.75 | 8 | 57 | 27 | 82 | 44 | 13 |
| Al Jouf | 88 | 1.68 | 0.75 | 8 | 57 | 27 | 82 | 44 | 13 |
| Al Qurayyat | 88 | 1.66 | 0.75 | 8 | 57 | 27 | 82 | 44 | 13 |

# 7. Review and approval periods

All SAR reviews and approvals of submissions are 21 days. In a Sunday to Thursday calendar that is three working weeks, so each approval activity is 15 working days. This applies to the initial and detailed baseline programme, the survey, every design stage, HCIS documents, POC plan, as-built documents and the taking-over application. The POC inspection and approval, and the mock-up approval at Riyadh (Thumamah), are separate one month periods (22 working days) as instructed.

102 approval activities are loaded. Their durations: 15 days x 100, 22 days x 1, 45 days x 1 (working days).

# 8. Calendar

Single project calendar: Sunday to Thursday, 8 hours per day (08:00 to 12:00 and 13:00 to 17:00); Friday and Saturday are non-working. The contract defines a working day as a bank-open day, and dates falling on a non-working day move to the next working day. National holidays are calendar exceptions: Founding Day (22 Feb), National Day (23 Sep), Eid al-Fitr and Eid al-Adha.

The Eid dates are estimates from the Islamic calendar. Confirm them against the official announcement before the baseline is submitted.

| From | To | Holiday |
| --- | --- | --- |
| 22 Feb 2027 | 22 Feb 2027 | Founding Day |
| 07 Mar 2027 | 11 Mar 2027 | Eid al-Fitr (estimated) |
| 16 May 2027 | 20 May 2027 | Eid al-Adha (estimated) |
| 23 Sep 2027 | 23 Sep 2027 | National Day |
| 20 Feb 2028 | 24 Feb 2028 | Eid al-Fitr (estimated) |
| 22 Feb 2028 | 22 Feb 2028 | Founding Day |
| 30 Apr 2028 | 04 May 2028 | Eid al-Adha (estimated) |
| 23 Sep 2028 | 23 Sep 2028 | National Day |
| 11 Feb 2029 | 15 Feb 2029 | Eid al-Fitr (estimated) |
| 22 Feb 2029 | 22 Feb 2029 | Founding Day |
| 22 Apr 2029 | 26 Apr 2029 | Eid al-Adha (estimated) |
| 23 Sep 2029 | 23 Sep 2029 | National Day |

# 9. Work breakdown structure

The WBS follows EPC. Level 1 is the project (0580), level 2 the EPC phase (Engineering, Procurement, Construction, Commissioning and handover, plus Project management), level 3 the station, level 4 the design stage or work package (enabling works, civil, installation, POC), and level 5 the submittal, approval or area. There are 514 nodes. The survey access permits sit under Project management and mobilization, in the Mobilization branch (one node per station). Levels 6 to 8 are not used because the contract gives no zone-level data; they can be added when it does.

| WBS level | Nodes |
| --- | --- |
| 1 | 1 |
| 2 | 5 |
| 3 | 59 |
| 4 | 253 |
| 5 | 196 |

# 10. Engineering stages

Engineering is divided by recognised design stage: site survey (after the two month access permit), concept design, preliminary design, detailed design, issued for construction, HCIS submission and as-built. Within each stage there is a submittal and a 21 day SAR approval. Procurement is released after the engineering approval milestone (MS3).

# 11. Logic and sequencing

Relationships are mainly finish to start, with a few start to start and finish to finish links. There are no date constraints. Stations are not linked to each other and the railway lines are not linked to each other: every station is linked only to the mobilization (milestone PRJ-M1150), and the other stations start at a lag from it, in waves calibrated so the last station completes inside the 36 month term. Station completions feed the closeout and contract completion only. The only activity without a predecessor is NTP, and the only activity without a successor is contract completion.

# 12. Station finish dates

# 13. Longest path and near-critical activities

The contract completion milestone is held by the 36 month term, so no activity has zero float against it. The longest physical path finishes 24 working days before the contract end date, and that margin is the project float. 26 tasks sit on this longest path and 10 more are within 20 working days of it. The first 25 in date order are listed below.

| ID | Activity | Start | Finish | Float (working days) |
| --- | --- | --- | --- | --- |
| PRJ-A1060 | Site access permits for the surveys of all stations: application and approval (two months) | 01 Nov 2026 | 31 Dec 2026 | 24 |
| PRJ-A1040 | Mobilization: site establishment, offices, personnel and tools | 08 Nov 2026 | 10 Dec 2026 | 39 |
| PRJ-A1050 | Mobilization submittals: QC programme and ITP, HSE, security, procurement and shipping plan | 08 Nov 2026 | 03 Dec 2026 | 44 |
| NQR-E1010 | Survey: submittal of site survey and as-found report - Al Qurayyat | 02 Aug 2028 | 13 Aug 2028 | 24 |
| NQR-E1030 | Concept design: submittal - Al Qurayyat | 14 Aug 2028 | 27 Aug 2028 | 24 |
| NQR-E1050 | Preliminary design: submittal - Al Qurayyat | 28 Aug 2028 | 18 Sep 2028 | 24 |
| NQR-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Al Qurayyat | 19 Sep 2028 | 24 Oct 2028 | 24 |
| NQR-E1110 | HCIS Stage 3 and 4 documents: preparation - Al Qurayyat | 03 Oct 2028 | 09 Nov 2028 | 24 |
| NQR-E1080 | Detailed design: SAR review and approval - Al Qurayyat | 25 Oct 2028 | 14 Nov 2028 | 36 |
| NQR-E1090 | IFC and shop drawings: submittal - Al Qurayyat | 25 Oct 2028 | 09 Nov 2028 | 24 |
| NQR-E1100 | IFC and shop drawings: SAR approval and release - Al Qurayyat | 12 Nov 2028 | 30 Nov 2028 | 24 |
| NQR-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Al Qurayyat | 12 Nov 2028 | 30 Nov 2028 | 24 |
| NQR-X1010 | Enabling works: site preparation, setting out, temporary works and utilities clearance - Al Qurayyat | 03 Dec 2028 | 07 Dec 2028 | 37 |
| NQR-P1010 | Manufacture CCTV cameras and analytics - Al Qurayyat | 03 Dec 2028 | 05 Feb 2029 | 24 |
| NQR-P1020 | Manufacture video management servers, storage and video wall - Al Qurayyat | 03 Dec 2028 | 05 Feb 2029 | 24 |
| NQR-P1030 | Manufacture access control and intercom equipment - Al Qurayyat | 03 Dec 2028 | 05 Feb 2029 | 24 |
| NQR-P1040 | Manufacture UPS, network switches and field cabinets - Al Qurayyat | 03 Dec 2028 | 05 Feb 2029 | 24 |
| NQR-X1020 | Enabling works: cable routes, duct-bank and cabinet plinth preparation - Al Qurayyat | 10 Dec 2028 | 21 Dec 2028 | 37 |
| NQR-C1010 | Civil: platform trenches and duct banks - Al Qurayyat | 24 Dec 2028 | 20 Mar 2029 | 37 |
| NQR-P1050 | Factory acceptance test at vendor premises - Al Qurayyat | 06 Feb 2029 | 27 Feb 2029 | 24 |
| NQR-C1020 | Civil: camera and ALPR pole foundations and poles - Al Qurayyat | 20 Feb 2029 | 01 May 2029 | 37 |
| NQR-P1060 | Shipping and customs clearance - Al Qurayyat | 28 Feb 2029 | 29 Mar 2029 | 24 |
| NQR-P1070 | Delivery to station and receiving inspection - Al Qurayyat | 01 Apr 2029 | 05 Apr 2029 | 24 |
| NQR-C2010 | Install UPS, network switches and field cabinets - Al Qurayyat | 08 Apr 2029 | 01 May 2029 | 24 |
| NQR-C2020 | Cabling and termination (power, fibre, data) - Al Qurayyat | 12 Apr 2029 | 20 May 2029 | 24 |

# 14. Resources and cost loading

Every task carries two resources. Milestones carry none.

| Resource | Type | Use |
| --- | --- | --- |
| COST-SAR | Material | Contract cost quantity in SAR. Price 0. Total 62,000,000 SAR. |
| PROG-WT | Material | Progress value in SAR (progress share x 62,000,000). Price 1, so it carries the budget cost. All activities use Physical % complete. |

Because PROG-WT has price 1 and COST-SAR has price 0, the P6 budget, earned value, CPI and SPI are all in SAR on the fair EPC progress distribution. To view the contract payment-condition cost instead, swap the two prices (COST-SAR 1, PROG-WT 0). Never set both to 1.

Cost comes from the contract: the Annex 3 station price multiplied by the clause 15 payment milestone, spread to activities by distribution keys. Mobilization (MS1, 20% of the total price) sits at project level. The activity-by-activity mapping and the invoices per month are in 0580_BOQ_Cost_Mapping.xlsx. Progress is a fair EPC distribution (Engineering 12, Procurement 40, Construction 33, Commissioning and handover 15 per station), weighted by each station's price share, plus 4% for project-level activities.

| Milestone | Description | Share of price |
| --- | --- | --- |
| MS1 | Mobilization | 20% |
| MS2 | Engineering submittal | 10% |
| MS3 | SAR approval of engineering | 10% |
| MS4 | Material delivery | 20% |
| MS5 | Installation | 20% |
| MS6 | Testing and commissioning (SAT) | 10% |
| MS7 | Final acceptance and handover | 10% |

# 15. S-curve

Cost follows the contract payment milestones. Progress is smoother because it is distributed by effort. The two curves differ on purpose: cost is a payment profile, progress is physical.

# 16. Activity codes

Eleven global activity code types are loaded and every activity carries all of them: EPC phase, Area, Station, Railway, Discipline, Responsibility, Payment milestone, Design stage, Submittal or approval, Priority and Programme phase. The values are listed on the Activity_Codes sheet of the BOQ workbook.

# 17. Changing the start date

NTP is a start milestone with no constraint. To move the project, change the project Planned Start (Project > Details > Dates), then schedule with F9 using Retained Logic. All dates, including contract completion, move together. The holidays are fixed dates, so after a change review the calendar for the holidays that the new window crosses.

# 18. Assumptions and exclusions

Durations and station order are Contractor planning assumptions.

Eid dates are estimates.

The 21 day SAR review is read as 21 calendar days, which is 15 working days in the Sunday to Thursday calendar. A longer review is an extension of time matter under the contract.

Priority 1 means Makkah and Riyadh (Thumamah). Riyadh (Malaz) is treated as Priority 2.

Mock-up approval: after the installation at Riyadh (Thumamah) is complete, SAR visits the site and approves the executed works (one month, 22 working days) so that the solution can be rolled out to the other stations. It is a predecessor of the SAT milestone (MS6) and the handover at that station only; it does not gate the installation of the other stations. Cost has no Annex 3 item and is carved from 3% of the testing milestone.

POC cost is carved from the design package of Riyadh (Thumamah) because Annex 3 has no POC item. The POC inspection system is mapped to access control and intercom (section A3).

Enabling and civil works start two months before the end of design at every station, before the engineering approval milestone, at the Contractor risk; equipment is not ordered before approval.

Site access, permits and railway possessions are assumed available. No possession restrictions are modelled.

The defects liability period and post-acceptance support are not in the programme.

Cost is a payment profile at BOQ value, excluding VAT.

The official project name is used as supplied. Please confirm its spelling before issue.

The file was checked structurally and with an independent forward pass; see the read-me for what was and was not tested in P6.

# 19. Risks to the programme

| Risk | Mitigation |
| --- | --- |
| Eid dates differ from the estimate | Confirm before submission and reschedule |
| Long-lead equipment at Haramain stations (largest value) | Early procurement approval and FAT planning |
| SAR approval time above 21 days | Early submission and an approval log |
| POC not approved within one month | Early plan approval; consultant booked in advance |
| Enabling works before engineering approval | Limit to non-design-dependent work; confirm layouts at concept approval |
| Station access and railway possession | Coordinate during mobilization |
| Conflict between Annex 4 item 33 (fast-track) and Annex 5 on HCIS | Clarify with SAR before design submittals |

# 20. Submission checklist

Confirm the project name spelling and the Eid dates.

Open the XER in P6 24, schedule it, and compare dates with this narrative.

Confirm the priority order with SAR.

Check the cost mapping against the Annex 3 price table.

Submit the XER, narrative, BOQ mapping and read-me together.