## Slide 1
Passengers' Security Checking | Scope of work
1
Scope of work: integrated security at 14 passenger stations
Design, supply, installation, testing and handover of CCTV, video management and access control on NSR, EWR and HHR
14
stations
NSR 6 · EWR 4 · HHR 4
2,481
cameras supplied
per Annex 3 price table
SAR 62.0M
lump-sum price
excluding 15% VAT
36 months
contract term
from Notice to Proceed
WHAT IS DELIVERED AT EACH STATION
CCTV system
Fixed, 90°, 180° panoramic, tandem PTZ, 360°, face recognition and ANPR cameras with line-crossing and direction analytics
Video management and video wall
Servers, 24-bay storage (8 MP, 15 days, RAID 5), 55-inch video walls and operator workstations
Access control and intercom
Readers, controllers, magnetic locks, ID-card station and IP door station
UPS, poles and network
UPS with 2 hours backup, Cisco core and PoE switches, field cabinets, poles, cabling
Civil works
Platform trenches, duct banks, camera poles and ALPR poles
Services
Design, project management, factory acceptance test, commissioning spares, training, 12-month cloud storage
STATIONS BY RAILWAY (★ RIYADH PRIORITY)
NSR
Riyadh Thumamah ★ · Al Majma'ah · Qassim · Hail · Al Jouf · Qurayyat
EWR
Riyadh Malaz ★ · Dammam · Hufuf · Abqaiq
HHR
Jeddah · KAEC · Makkah · Madinah
BOUNDARIES (ANNEXES 3 AND 5)
Inside the station only, from doors to platforms
Excluded: fibre between stations, IP telephony, cyber-security hardening, maintenance programme
SAR provides: gate passes, laydown area, network to control rooms
Notes: Source: draft contract between SAR and ETECHS (22 Jan 2024) with Annexes 1 to 5. Station list: Annex 1 deliverables. Quantities and sub-systems: Annex 3 price table (Revised-02, SAR 62,000,000 ex-VAT; EWR 11,113,215, NSR 20,499,295, HHR 30,387,490). Boundaries: Annex 3 terms (exclusions) and Annex 5 SAR responses (inner areas only). Madinah is priced at 50% of the Makkah BOQ.

## Slide 2
Passengers' Security Checking | Schedule, Level 2
2
Level 2 schedule: Riyadh first, last station accepted at month 36
Level 1 project, Level 2 priority package and railways; months from Notice to Proceed (assumed 1 Nov 2026)
Q1
Q2
Q3
Q4
Q5
Q6
Q7
Q8
Q9
Q10
Q11
Q12
M0
M6
M12
M18
M24
M30
M36
Activity
SAR Passengers' Security Checking
14 stations · SAR 62.00M
NTP at M0, term ends M36
Mobilization and baseline
Baseline in 10 days, detailed one 21 days after survey
M0.0 to M2.1
Riyadh priority stations (NSR + EWR)
2 stations · SAR 6.57M
M1.4 to M12.9
NSR: North South Railway
5 stations · SAR 17.02M
M10.4 to M36.0
EWR: East West Railway
3 stations · SAR 8.02M
M8.3 to M30.0
HHR: Haramain High Speed Rail
4 stations · SAR 30.39M
M4.6 to M33.7
Closeout, warranty and support
Rolling per station; 1-year defects liability
M12.0 to M36.0
Term ends M36
M1.4
Riyadh start
M4.4
Riyadh design approved
M11.1
Riyadh SAT done
M12.9
Riyadh accepted
M36
Last station accepted
Riyadh SAT
NSR
EWR
HHR
Riyadh priority
Mobilization / closeout
Baseline assumed: not yet approved by SAR
Notes: Contract facts: 36-month term from Notice to Proceed (Annex 1); initial baseline within 10 days of the effective date, detailed baseline 21 days after the mobilization and survey works, SAR review at most 21 days (clause 3, Baseline Programme); trial operation maximum 45 days; defects liability 1 year from each Taking-Over Certificate. Everything else is a planning assumption: Riyadh starts in weeks 6 and 8 with expedited procurement; other stations are spread so the last final acceptance falls at month 36; NTP 1 Nov 2026 is an editable assumption. Level 3 and 4 detail is in the interactive dashboard.

## Slide 3
Passengers' Security Checking | Cash flow
3
Cash flow: SAR 62.0M invoiced on seven contract milestones
Amount to be invoiced in each month from Notice to Proceed (assumed 1 Nov 2026), SAR million excluding VAT
Month | M1 Nov 26 | M2 Dec 26 | M3 Jan 27 | M4 Feb 27 | M5 Mar 27 | M6 Apr 27 | M7 May 27 | M8 Jun 27 | M9 Jul 27 | M10 Aug 27 | M11 Sept 27 | M12 Oct 27
Invoiced in month | - | 12.40 | - | 0.66 | 0.66 | - | - | 0.96 | 1.65 | 0.62 | 2.30 | 0.31
Cumulative | 0.0 | 12.4 | 12.4 | 13.1 | 13.7 | 13.7 | 13.7 | 14.7 | 16.3 | 16.9 | 19.2 | 19.5
Month | M13 Nov 27 | M14 Dec 27 | M15 Jan 28 | M16 Feb 28 | M17 Mar 28 | M18 Apr 28 | M19 May 28 | M20 Jun 28 | M21 Jul 28 | M22 Aug 28 | M23 Sept 28 | M24 Oct 28
Invoiced in month | 0.97 | 0.93 | 0.68 | 2.88 | 1.61 | 0.64 | 1.56 | 4.15 | 4.00 | 1.22 | 4.20 | -
Cumulative | 20.5 | 21.5 | 22.1 | 25.0 | 26.6 | 27.3 | 28.8 | 33.0 | 37.0 | 38.2 | 42.4 | 42.4
Month | M25 Nov 28 | M26 Dec 28 | M27 Jan 29 | M28 Feb 29 | M29 Mar 29 | M30 Apr 29 | M31 May 29 | M32 Jun 29 | M33 Jul 29 | M34 Aug 29 | M35 Sept 29 | M36 Oct 29
Invoiced in month | 0.68 | 0.34 | 1.08 | 5.25 | 1.85 | 0.34 | 4.08 | 2.82 | 0.34 | 1.79 | 0.68 | 0.34
Cumulative | 43.1 | 43.4 | 44.5 | 49.8 | 51.6 | 51.9 | 56.0 | 58.8 | 59.2 | 61.0 | 61.7 | 62.0
Chart: SAR M invoiced per month, by railway
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
NSR | 0 | 4.1 | 0 | 0.348 | 0.348 | 0 | 0 | 0 | 0.696 | 0 | 1.044 | 0 | 0.688 | 0.34 | 0.68 | 0 | 0 | 0 | 0.68 | 1.36 | 0.34 | 1.02 | 1.02 | 0 | 0.682 | 0.342 | 0.68 | 0.68 | 0.68 | 0.34 | 0.685 | 1.704 | 0.342 | 0.68 | 0.682 | 0.34
EWR | 0 | 2.223 | 0 | 0.309 | 0.309 | 0 | 0 | 0 | 0 | 0.618 | 1.256 | 0.309 | 0.283 | 0.592 | 0 | 0 | 0.638 | 0.638 | 0.884 | 0.884 | 0.483 | 0.201 | 0.283 | 0 | 0 | 0 | 0.401 | 0.401 | 0.201 | 0 | 0.201 | 0 | 0 | 0 | 0 | 0
HHR | 0 | 6.077 | 0 | 0 | 0 | 0 | 0 | 0.955 | 0.955 | 0 | 0 | 0 | 0 | 0 | 0 | 2.881 | 0.971 | 0 | 0 | 1.91 | 3.18 | 0 | 2.897 | 0 | 0 | 0 | 0 | 4.167 | 0.971 | 0 | 3.196 | 1.113 | 0 | 1.113 | 0 | 0
Contract milestone | Share | SAR M | Months
Mobilization | 20% | 12.4 | 1.4
Engineering submittal | 10% | 6.2 | 3.2 to 26.1
SAR approval | 10% | 6.2 | 3.9 to 26.8
Material delivery | 20% | 12.4 | 8.5 to 31.8
Installation | 20% | 12.4 | 10.2 to 33.5
Testing & commissioning (SAT) | 10% | 6.2 | 10.8 to 34.2
Final acceptance | 10% | 6.2 | 12.7 to 35.8
Total | 100% | 62.0 | 
Notes: Monthly amounts are the invoices falling in each month, from clause 15 of the draft contract: 20% mobilization, 10% engineering submittal, 10% after SAR approval, 20% material delivery, 20% installation, 10% testing and commissioning (SAT), 10% final acceptance and handover, each prorated per station on the station value. Invoice dates follow the planning baseline on the schedule slide (assumed, not approved by SAR). Month 1 is the first month after the Notice to Proceed (1 Nov 2026 assumed). Amounts exclude 15% VAT.