## Summary
SAR Passengers Security Checking: baseline schedule, cost loading and BOQ mapping
Source of cost | Draft contract with ETECHS (22 Jan 2024): Annex 3 price table (Revised-02) and clause 15 payment milestones
Contract price | 62000000
Project start (NTP milestone) | 2026-11-01
Contract term end (36 months) | 2029-10-31
Activities | 558
Tasks (2 resources each) | 470
Milestones | 88
Cost loaded in P6 (SAR)
Difference to contract price
Progress points loaded
Working calendar | Sunday to Thursday, 8 hours; KSA official holidays; Eid dates are estimates to be updated
How to read | Station_BOQ gives the BOQ value of each station; Payment_Milestones applies the contract payment conditions; BOQ_Mapping shows each activity cost; Distribution_Keys explains the keys; S_Curve shows cost against progress.

## Station_BOQ
Annex 3 price table: BOQ value by station (SAR, excluding VAT)
A1-A6 are priced per station. Shared packages (design, PM, FAT, spares, training, cloud) are priced per railway and allocated to stations pro rata to A1-A6 hardware value.
Station | Railway | A1 CCTV | A2 Video mgmt and wall | A3 Access and intercom | A4 UPS | A5 Poles, cabinets, network | A6 Civil works | Hardware subtotal | Design and engineering | Project management | FAT | Commissioning spares | Training | Cloud (12 mo) | Shared total | Station value | Share of price
Riyadh (Thumamah) (NRY) | NSR | 338989 | 417141 | 44085 | 56211 | 860619 | 745743 |  | 82837.4 | 744951.9774 | 34510.3761 | 66982.1302 | 6573.9871 | 82141.8981
Riyadh (Malaz) (ERY) | EWR | 276849 | 350866 | 44085 | 50114 | 548042 | 701825 |  | 86494.6877 | 779124.2822 | 56538.4266 | 106509.2034 | 18847.2549 | 72225.5095
Jeddah (HJD) | HHR | 1391206 | 652091 | 44085 | 102666 | 2840354 | 521718 |  | 332247.8681 | 2976447.681 | 63879.2661 | 172484.7992 | 21294.3459 | 432406.8209
Dammam (EDM) | EWR | 276849 | 412102 | 44085 | 50114 | 548042 | 701813 |  | 89180.3565 | 803316.1702 | 58293.9505 | 109816.3249 | 19432.4641 | 74468.1189
Al Qassim (NQS) | NSR | 338989 | 359215 | 44085 | 56211 | 860619 | 745743 |  | 80889.0231 | 727430.3359 | 33698.6749 | 65406.6772 | 6419.3637 | 80209.8797
Hufuf (EHF) | EWR | 192155 | 349033 | 44085 | 50114 | 508774 | 659866 |  | 79135.9446 | 712838.4144 | 51728.2843 | 97447.6773 | 17243.7795 | 66080.7509
Al Majma'ah (NMJ) | NSR | 338989 | 359215 | 44085 | 56211 | 860619 | 745743 |  | 80889.0231 | 727430.3359 | 33698.6749 | 65406.6772 | 6419.3637 | 80209.8797
Makkah (HMK) | HHR | 1650175 | 552237 | 44085 | 110563 | 2715976 | 571639 |  | 337786.5094 | 3026065.6855 | 64944.1468 | 175360.1568 | 21649.3271 | 439615.133
KAEC (HKA) | HHR | 962039 | 406364 | 44085 | 82168 | 1552977 | 187054 |  | 193568.9178 | 1734090.1529 | 37216.3123 | 100490.324 | 12406.1699 | 251921.9185
Madinah (HMD) | HHR | 934319 | 409184 | 44085 | 74329 | 1480427 | 291036 |  | 193490.7048 | 1733389.4806 | 37201.2747 | 100449.7201 | 12401.1571 | 251820.1276
Abqaiq (EAB) | EWR | 111083 | 286032 | 44085 | 50114 | 411979 | 375936 |  | 56115.0112 | 505471.1332 | 36680.3387 | 69099.7944 | 12227.5015 | 46857.6207
Hail (NHL) | NSR | 338989 | 359215 | 44085 | 56211 | 860619 | 745743 |  | 80889.0231 | 727430.3359 | 33698.6749 | 65406.6772 | 6419.3637 | 80209.8797
Al Jouf (NJF) | NSR | 338989 | 359215 | 44085 | 56211 | 877550 | 745743 |  | 81458.5077 | 732551.6789 | 33935.9244 | 65867.1612 | 6464.5581 | 80774.583
Al Qurayyat (NQR) | NSR | 338989 | 359215 | 44085 | 56211 | 860619 | 745743 |  | 80889.0231 | 727430.3359 | 33698.6749 | 65406.6772 | 6419.3637 | 80209.8797
Total
Contract price (Annex 3) |  | 62000000
Difference (should be zero within SAR 5)

## Payment_Milestones
Contract clause 15 payment milestones applied to each station price
MS1 Mobilization is 20% of the TOTAL price. MS2 to MS7 are prorated per station on the station share of the price.
Milestone | Description | Share of price | Amount (SAR)
MS1 | Mobilization | 20%
MS2 | Engineering submittal | 10%
MS3 | SAR approval of engineering | 10%
MS4 | Material delivery | 20%
MS5 | Installation | 20%
MS6 | Testing and commissioning (SAT) | 10%
MS7 | Final acceptance and handover | 10%
Total
Station | Station share | MS2 amount | MS3 amount | MS4 amount | MS5 amount | MS6 amount | MS7 amount | Stations total MS2-MS7
Riyadh (Thumamah) (NRY)
Riyadh (Malaz) (ERY)
Jeddah (HJD)
Dammam (EDM)
Al Qassim (NQS)
Hufuf (EHF)
Al Majma'ah (NMJ)
Makkah (HMK)
KAEC (HKA)
Madinah (HMD)
Abqaiq (EAB)
Hail (NHL)
Al Jouf (NJF)
Al Qurayyat (NQR)
Total
Check: MS1 + stations MS2-MS7 = total price

## BOQ_Mapping
Activity cost mapping: how each activity cost was distributed from the BOQ
Cost = milestone amount (contract payment condition x station share of the BOQ) x distribution key. Column K recomputes it with formulas; column L is the whole-riyal value loaded in P6.
Activity ID | Activity name | WBS | EPC phase | Station | Payment milestone | Milestone % | Station price share | Milestone amount (SAR) | Distribution key | Cost recomputed | Cost in P6 (SAR) | Difference | Distribution basis | Primary BOQ source | Progress points | Progress % of project | Start | Finish | Duration (work days)
PRJ-A1010 | Performance security, insurance and key personnel approval | PM.MOB | Project management | PRJ | MS1 | 20% |  |  | 0.15 |  | 1859999 |  | MS1 Mobilization 20% of the total price (SAR 12,400,000) x key 15% | Contract price (62,000,000) x 20% mobilization payment (contract clause 15) | 400 |  | 2026-11-01 | 2026-11-12 | 10
PRJ-A1020 | Initial baseline programme (Primavera) covering mobilization and survey | PM.MOB | Project management | PRJ | MS1 | 20% |  |  | 0.1 |  | 1240000 |  | MS1 Mobilization 20% of the total price (SAR 12,400,000) x key 10% | Contract price (62,000,000) x 20% mobilization payment (contract clause 15) | 200 |  | 2026-11-01 | 2026-11-09 | 7
PRJ-A1030 | SAR review and approval of initial baseline | PM.MOB | Project management | PRJ |  | 0% |  | 0 | 0 | 0 | 0 |  | No payment milestone attached (administrative approval or review step) | - | 200 |  | 2026-11-10 | 2026-11-30 | 15
PRJ-A1040 | Mobilization: site establishment, offices, personnel and tools | PM.MOB | Project management | PRJ | MS1 | 20% |  |  | 0.45 |  | 5579999 |  | MS1 Mobilization 20% of the total price (SAR 12,400,000) x key 45% | Contract price (62,000,000) x 20% mobilization payment (contract clause 15) | 800 |  | 2026-11-08 | 2026-12-10 | 25
PRJ-A1050 | Mobilization submittals: QC programme and ITP, HSE, security, procurement and shipping plan | PM.MOB | Project management | PRJ | MS1 | 20% |  |  | 0.3 |  | 3719999 |  | MS1 Mobilization 20% of the total price (SAR 12,400,000) x key 30% | Contract price (62,000,000) x 20% mobilization payment (contract clause 15) | 600 |  | 2026-11-08 | 2026-12-03 | 20
PRJ-A2010 | Detailed baseline programme (within 21 days after survey) | PM.MOB | Project management | PRJ |  | 0% |  | 0 | 0 | 0 | 0 |  | No payment milestone attached (administrative approval or review step) | - | 300 |  | 2027-01-10 | 2027-01-28 | 15
PRJ-A2020 | SAR review and approval of detailed baseline | PM.MOB | Project management | PRJ |  | 0% |  | 0 | 0 | 0 | 0 |  | No payment milestone attached (administrative approval or review step) | - | 200 |  | 2027-01-31 | 2027-02-18 | 15
PRJ-C1010 | Contract closeout pack and handover documentation | PM.CLO | Project management | PRJ |  | 0% |  | 0 | 0 | 0 | 0 |  | No payment milestone attached (administrative approval or review step) | - | 1301 |  | 2029-09-17 | 2029-10-01 | 10
NRY-E1010 | Survey: submittal of site survey and as-found report - Riyadh (Thumamah) | ENG.RYD.NRY.SRV.SUB | Engineering | NRY | MS2 | 10% |  |  | 0.05 |  | 17404 |  | MS2 Engineering submittal 10% x station price share 5.61% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 34 |  | 2026-12-13 | 2026-12-24 | 10
NRY-E1020 | Survey: SAR approval of survey report - Riyadh (Thumamah) | ENG.RYD.NRY.SRV.APR | Engineering | NRY | MS3 | 10% |  |  | 0.05 |  | 17404 |  | MS3 SAR approval of engineering 10% x station price share 5.61% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 17 |  | 2026-12-27 | 2026-12-31 | 5
NRY-E1030 | Concept design: submittal - Riyadh (Thumamah) | ENG.RYD.NRY.CNC.SUB | Engineering | NRY | MS2 | 10% |  |  | 0.1 |  | 34808 |  | MS2 Engineering submittal 10% x station price share 5.61% ¦ Design stage key 10% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 16 |  | 2026-12-27 | 2026-12-31 | 5
NRY-E1040 | Concept design: SAR review and approval - Riyadh (Thumamah) | ENG.RYD.NRY.CNC.APR | Engineering | NRY | MS3 | 10% |  |  | 0.1 |  | 34808 |  | MS3 SAR approval of engineering 10% x station price share 5.61% ¦ Design stage key 10% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 49 |  | 2027-01-03 | 2027-01-21 | 15
NRY-E1050 | Preliminary design: submittal - Riyadh (Thumamah) | ENG.RYD.NRY.PRE.SUB | Engineering | NRY | MS2 | 10% |  |  | 0.2 |  | 69616 |  | MS2 Engineering submittal 10% x station price share 5.61% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 40 |  | 2027-01-03 | 2027-01-12 | 8
NRY-E1060 | Preliminary design: SAR review and approval - Riyadh (Thumamah) | ENG.RYD.NRY.PRE.APR | Engineering | NRY | MS3 | 10% |  |  | 0.2 |  | 69616 |  | MS3 SAR approval of engineering 10% x station price share 5.61% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 76 |  | 2027-01-13 | 2027-02-02 | 15
NRY-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Riyadh (Thumamah) | ENG.RYD.NRY.DET.SUB | Engineering | NRY | MS2 | 10% |  |  | 0.4 |  | 139231 |  | MS2 Engineering submittal 10% x station price share 5.61% ¦ Design stage key 40% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 86 |  | 2027-01-13 | 2027-01-28 | 12
NRY-E1080 | Detailed design: SAR review and approval - Riyadh (Thumamah) | ENG.RYD.NRY.DET.APR | Engineering | NRY | MS3 | 10% |  |  | 0.4 |  | 139231 |  | MS3 SAR approval of engineering 10% x station price share 5.61% ¦ Design stage key 40% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 108 |  | 2027-01-31 | 2027-02-18 | 15
NRY-E1090 | IFC and shop drawings: submittal - Riyadh (Thumamah) | ENG.RYD.NRY.IFC.SUB | Engineering | NRY | MS2 | 10% |  |  | 0.2 |  | 69616 |  | MS2 Engineering submittal 10% x station price share 5.61% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 29 |  | 2027-01-31 | 2027-02-04 | 5
NRY-E1100 | IFC and shop drawings: SAR approval and release - Riyadh (Thumamah) | ENG.RYD.NRY.IFC.APR | Engineering | NRY | MS3 | 10% |  |  | 0.2 |  | 69616 |  | MS3 SAR approval of engineering 10% x station price share 5.61% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 87 |  | 2027-02-07 | 2027-02-28 | 15
NRY-E1110 | HCIS Stage 3 and 4 documents: preparation - Riyadh (Thumamah) | ENG.RYD.NRY.HCS.SUB | Engineering | NRY | MS2 | 10% |  |  | 0.05 |  | 17404 |  | MS2 Engineering submittal 10% x station price share 5.61% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 17 |  | 2027-01-20 | 2027-02-04 | 12
NRY-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Riyadh (Thumamah) | ENG.RYD.NRY.HCS.APR | Engineering | NRY | MS3 | 10% |  |  | 0.05 |  | 17404 |  | MS3 SAR approval of engineering 10% x station price share 5.61% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 22 |  | 2027-02-07 | 2027-02-28 | 15
NRY-E1130 | As-built and O&M documentation: submittal - Riyadh (Thumamah) | ENG.RYD.NRY.ASB.SUB | Engineering | NRY | MS7 | 10% |  |  | 0.15 |  | 52212 |  | MS7 Final acceptance and handover 10% x station price share 5.61% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 43 |  | 2027-09-21 | 2027-11-02 | 30
NRY-E1140 | As-built and O&M documentation: SAR review and approval - Riyadh (Thumamah) | ENG.RYD.NRY.ASB.APR | Engineering | NRY | MS7 | 10% |  |  | 0.05 |  | 17404 |  | MS7 Final acceptance and handover 10% x station price share 5.61% ¦ Fixed key 5% | Annex 3 documentation share | 22 |  | 2027-11-03 | 2027-11-23 | 15
NRY-P1010 | Manufacture CCTV cameras and analytics - Riyadh (Thumamah) | PRO.RYD.NRY.CCT | Procurement | NRY | MS4 | 20% |  |  | 0.14807 |  | 103080 |  | MS4 Material delivery 20% x station price share 5.61% ¦ BOQ section share 19.7% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 338,989) | 255 |  | 2027-03-01 | 2027-06-06 | 60
NRY-P1020 | Manufacture video management servers, storage and video wall - Riyadh (Thumamah) | PRO.RYD.NRY.VMS | Procurement | NRY | MS4 | 20% |  |  | 0.18221 |  | 126844 |  | MS4 Material delivery 20% x station price share 5.61% ¦ BOQ section share 24.3% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 417,141) | 314 |  | 2027-03-01 | 2027-06-06 | 60
NRY-P1030 | Manufacture access control and intercom equipment - Riyadh (Thumamah) | PRO.RYD.NRY.ACC | Procurement | NRY | MS4 | 20% |  |  | 0.019256 |  | 13405 |  | MS4 Material delivery 20% x station price share 5.61% ¦ BOQ section share 2.6% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 33 |  | 2027-03-01 | 2027-06-06 | 60
NRY-P1040 | Manufacture UPS, network switches and field cabinets - Riyadh (Thumamah) | PRO.RYD.NRY.UPN | Procurement | NRY | MS4 | 20% |  |  | 0.40047 |  | 278789 |  | MS4 Material delivery 20% x station price share 5.61% ¦ BOQ section share 53.4% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 916,830) | 691 |  | 2027-03-01 | 2027-06-06 | 60
NRY-P1050 | Factory acceptance test at vendor premises - Riyadh (Thumamah) | PRO.RYD.NRY.LOG | Procurement | NRY | MS4 | 20% |  |  | 0.05 |  | 34808 |  | MS4 Material delivery 20% x station price share 5.61% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 216 |  | 2027-06-07 | 2027-06-20 | 10
NRY-P1060 | Shipping and customs clearance - Riyadh (Thumamah) | PRO.RYD.NRY.LOG | Procurement | NRY | MS4 | 20% |  |  | 0.15 |  | 104424 |  | MS4 Material delivery 20% x station price share 5.61% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 431 |  | 2027-06-21 | 2027-07-25 | 25
NRY-P1070 | Delivery to station and receiving inspection - Riyadh (Thumamah) | PRO.RYD.NRY.LOG | Procurement | NRY | MS4 | 20% |  |  | 0.05 |  | 34808 |  | MS4 Material delivery 20% x station price share 5.61% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 216 |  | 2027-07-26 | 2027-08-01 | 5
NRY-C1010 | Civil: platform trenches and duct banks - Riyadh (Thumamah) | CON.RYD.NRY.CIV | Construction | NRY | MS5 | 20% |  |  | 0.16654 |  | 115940 |  | MS5 Installation 20% x station price share 5.61% ¦ BOQ civil share 30.3% x 55% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 745,743) | 431 |  | 2027-03-01 | 2027-06-03 | 59
NRY-C1020 | Civil: camera and ALPR pole foundations and poles - Riyadh (Thumamah) | CON.RYD.NRY.CIV | Construction | NRY | MS5 | 20% |  |  | 0.13626 |  | 94860 |  | MS5 Installation 20% x station price share 5.61% ¦ BOQ civil share 30.3% x 45% (poles) | Annex 3 A6 Civil works (SAR 745,743) | 323 |  | 2027-04-29 | 2027-07-11 | 47
NRY-C2010 | Install UPS, network switches and field cabinets - Riyadh (Thumamah) | CON.RYD.NRY.INS | Construction | NRY | MS5 | 20% |  |  | 0.13944 |  | 97072 |  | MS5 Installation 20% x station price share 5.61% ¦ Installation key 20% x (1 - civil share 30.3%) | Annex 3 equipment sections A1-A5 (installation share) | 162 |  | 2027-08-02 | 2027-08-16 | 11
NRY-C2020 | Cabling and termination (power, fibre, data) - Riyadh (Thumamah) | CON.RYD.NRY.INS | Construction | NRY | MS5 | 20% |  |  | 0.20916 |  | 145607 |  | MS5 Installation 20% x station price share 5.61% ¦ Installation key 30% x (1 - civil share 30.3%) | Annex 3 equipment sections A1-A5 (installation share) | 323 |  | 2027-08-08 | 2027-08-31 | 18
NRY-C2030 | Install and aim CCTV cameras - Riyadh (Thumamah) | CON.RYD.NRY.INS | Construction | NRY | MS5 | 20% |  |  | 0.1743 |  | 121339 |  | MS5 Installation 20% x station price share 5.61% ¦ Installation key 25% x (1 - civil share 30.3%) | Annex 3 equipment sections A1-A5 (installation share) | 269 |  | 2027-09-01 | 2027-09-20 | 14
NRY-C2040 | Install video management, video wall and control-room equipment - Riyadh (Thumamah) | CON.RYD.NRY.INS | Construction | NRY | MS5 | 20% |  |  | 0.10458 |  | 72804 |  | MS5 Installation 20% x station price share 5.61% ¦ Installation key 15% x (1 - civil share 30.3%) | Annex 3 equipment sections A1-A5 (installation share) | 162 |  | 2027-08-17 | 2027-09-01 | 12
NRY-C2050 | Install access control and intercom - Riyadh (Thumamah) | CON.RYD.NRY.INS | Construction | NRY | MS5 | 20% |  |  | 0.06972 |  | 48536 |  | MS5 Installation 20% x station price share 5.61% ¦ Installation key 10% x (1 - civil share 30.3%) | Annex 3 equipment sections A1-A5 (installation share) | 108 |  | 2027-08-23 | 2027-09-06 | 11
NRY-T1010 | Pre-commissioning and loop checks - Riyadh (Thumamah) | COM.RYD.NRY.TST | Commissioning and handover | NRY | MS6 | 10% |  |  | 0.4 |  | 139231 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.61% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 162 |  | 2027-09-21 | 2027-09-29 | 6
NRY-T1020 | Site acceptance test (SAT) and commissioning - Riyadh (Thumamah) | COM.RYD.NRY.TST | Commissioning and handover | NRY | MS6 | 10% |  |  | 0.6 |  | 208847 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.61% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 216 |  | 2027-09-30 | 2027-10-12 | 9
NRY-T2010 | Operator and maintenance training - Riyadh (Thumamah) | COM.RYD.NRY.TRN | Commissioning and handover | NRY | MS7 | 10% |  |  | 0.15 |  | 52212 |  | MS7 Final acceptance and handover 10% x station price share 5.61% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 108 |  | 2027-10-13 | 2027-10-26 | 10
NRY-T2020 | Trial operation (maximum 45 days) - Riyadh (Thumamah) | COM.RYD.NRY.TOA | Commissioning and handover | NRY | MS7 | 10% |  |  | 0.35 |  | 121828 |  | MS7 Final acceptance and handover 10% x station price share 5.61% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 162 |  | 2027-10-13 | 2027-11-23 | 30
NRY-T3010 | Taking-over application, SAR review and handover - Riyadh (Thumamah) | COM.RYD.NRY.TOA | Commissioning and handover | NRY | MS7 | 10% |  |  | 0.3 |  | 104424 |  | MS7 Final acceptance and handover 10% x station price share 5.61% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 162 |  | 2027-11-24 | 2027-12-07 | 10
ERY-E1010 | Survey: submittal of site survey and as-found report - Riyadh (Malaz) | ENG.RYD.ERY.SRV.SUB | Engineering | ERY | MS2 | 10% |  |  | 0.05 |  | 15458 |  | MS2 Engineering submittal 10% x station price share 4.99% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 31 |  | 2026-12-27 | 2027-01-07 | 10
ERY-E1020 | Survey: SAR approval of survey report - Riyadh (Malaz) | ENG.RYD.ERY.SRV.APR | Engineering | ERY | MS3 | 10% |  |  | 0.05 |  | 15458 |  | MS3 SAR approval of engineering 10% x station price share 4.99% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 15 |  | 2027-01-10 | 2027-01-14 | 5
ERY-E1030 | Concept design: submittal - Riyadh (Malaz) | ENG.RYD.ERY.CNC.SUB | Engineering | ERY | MS2 | 10% |  |  | 0.1 |  | 30915 |  | MS2 Engineering submittal 10% x station price share 4.99% ¦ Design stage key 10% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 14 |  | 2027-01-10 | 2027-01-14 | 5
ERY-E1040 | Concept design: SAR review and approval - Riyadh (Malaz) | ENG.RYD.ERY.CNC.APR | Engineering | ERY | MS3 | 10% |  |  | 0.1 |  | 30915 |  | MS3 SAR approval of engineering 10% x station price share 4.99% ¦ Design stage key 10% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 43 |  | 2027-01-17 | 2027-02-04 | 15
ERY-E1050 | Preliminary design: submittal - Riyadh (Malaz) | ENG.RYD.ERY.PRE.SUB | Engineering | ERY | MS2 | 10% |  |  | 0.2 |  | 61830 |  | MS2 Engineering submittal 10% x station price share 4.99% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 36 |  | 2027-01-17 | 2027-01-26 | 8
ERY-E1060 | Preliminary design: SAR review and approval - Riyadh (Malaz) | ENG.RYD.ERY.PRE.APR | Engineering | ERY | MS3 | 10% |  |  | 0.2 |  | 61830 |  | MS3 SAR approval of engineering 10% x station price share 4.99% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 67 |  | 2027-01-27 | 2027-02-16 | 15
ERY-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Riyadh (Malaz) | ENG.RYD.ERY.DET.SUB | Engineering | ERY | MS2 | 10% |  |  | 0.4 |  | 123661 |  | MS2 Engineering submittal 10% x station price share 4.99% ¦ Design stage key 40% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 77 |  | 2027-01-27 | 2027-02-11 | 12
ERY-E1080 | Detailed design: SAR review and approval - Riyadh (Malaz) | ENG.RYD.ERY.DET.APR | Engineering | ERY | MS3 | 10% |  |  | 0.4 |  | 123661 |  | MS3 SAR approval of engineering 10% x station price share 4.99% ¦ Design stage key 40% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 96 |  | 2027-02-14 | 2027-03-14 | 15
ERY-E1090 | IFC and shop drawings: submittal - Riyadh (Malaz) | ENG.RYD.ERY.IFC.SUB | Engineering | ERY | MS2 | 10% |  |  | 0.2 |  | 61830 |  | MS2 Engineering submittal 10% x station price share 4.99% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 26 |  | 2027-02-14 | 2027-02-18 | 5
ERY-E1100 | IFC and shop drawings: SAR approval and release - Riyadh (Malaz) | ENG.RYD.ERY.IFC.APR | Engineering | ERY | MS3 | 10% |  |  | 0.2 |  | 61830 |  | MS3 SAR approval of engineering 10% x station price share 4.99% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 78 |  | 2027-02-21 | 2027-03-21 | 15
ERY-E1110 | HCIS Stage 3 and 4 documents: preparation - Riyadh (Malaz) | ENG.RYD.ERY.HCS.SUB | Engineering | ERY | MS2 | 10% |  |  | 0.05 |  | 15458 |  | MS2 Engineering submittal 10% x station price share 4.99% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 15 |  | 2027-02-03 | 2027-02-18 | 12
ERY-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Riyadh (Malaz) | ENG.RYD.ERY.HCS.APR | Engineering | ERY | MS3 | 10% |  |  | 0.05 |  | 15458 |  | MS3 SAR approval of engineering 10% x station price share 4.99% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 19 |  | 2027-02-21 | 2027-03-21 | 15
ERY-E1130 | As-built and O&M documentation: submittal - Riyadh (Malaz) | ENG.RYD.ERY.ASB.SUB | Engineering | ERY | MS7 | 10% |  |  | 0.15 |  | 46373 |  | MS7 Final acceptance and handover 10% x station price share 4.99% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 38 |  | 2027-09-28 | 2027-11-08 | 30
ERY-E1140 | As-built and O&M documentation: SAR review and approval - Riyadh (Malaz) | ENG.RYD.ERY.ASB.APR | Engineering | ERY | MS7 | 10% |  |  | 0.05 |  | 15458 |  | MS7 Final acceptance and handover 10% x station price share 4.99% ¦ Fixed key 5% | Annex 3 documentation share | 19 |  | 2027-11-09 | 2027-11-29 | 15
ERY-P1010 | Manufacture CCTV cameras and analytics - Riyadh (Malaz) | PRO.RYD.ERY.CCT | Procurement | ERY | MS4 | 20% |  |  | 0.1635 |  | 101092 |  | MS4 Material delivery 20% x station price share 4.99% ¦ BOQ section share 21.8% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 276,849) | 250 |  | 2027-03-22 | 2027-06-20 | 60
ERY-P1020 | Manufacture video management servers, storage and video wall - Riyadh (Malaz) | PRO.RYD.ERY.VMS | Procurement | ERY | MS4 | 20% |  |  | 0.20721 |  | 128120 |  | MS4 Material delivery 20% x station price share 4.99% ¦ BOQ section share 27.6% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 350,866) | 317 |  | 2027-03-22 | 2027-06-20 | 60
ERY-P1030 | Manufacture access control and intercom equipment - Riyadh (Malaz) | PRO.RYD.ERY.ACC | Procurement | ERY | MS4 | 20% |  |  | 0.026035 |  | 16098 |  | MS4 Material delivery 20% x station price share 4.99% ¦ BOQ section share 3.5% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 40 |  | 2027-03-22 | 2027-06-20 | 60
ERY-P1040 | Manufacture UPS, network switches and field cabinets - Riyadh (Malaz) | PRO.RYD.ERY.UPN | Procurement | ERY | MS4 | 20% |  |  | 0.35325 |  | 218418 |  | MS4 Material delivery 20% x station price share 4.99% ¦ BOQ section share 47.1% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 598,156) | 541 |  | 2027-03-22 | 2027-06-20 | 60
ERY-P1050 | Factory acceptance test at vendor premises - Riyadh (Malaz) | PRO.RYD.ERY.LOG | Procurement | ERY | MS4 | 20% |  |  | 0.05 |  | 30915 |  | MS4 Material delivery 20% x station price share 4.99% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 191 |  | 2027-06-21 | 2027-07-04 | 10
ERY-P1060 | Shipping and customs clearance - Riyadh (Malaz) | PRO.RYD.ERY.LOG | Procurement | ERY | MS4 | 20% |  |  | 0.15 |  | 92746 |  | MS4 Material delivery 20% x station price share 4.99% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 383 |  | 2027-07-05 | 2027-08-08 | 25
ERY-P1070 | Delivery to station and receiving inspection - Riyadh (Malaz) | PRO.RYD.ERY.LOG | Procurement | ERY | MS4 | 20% |  |  | 0.05 |  | 30915 |  | MS4 Material delivery 20% x station price share 4.99% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 191 |  | 2027-08-09 | 2027-08-15 | 5
ERY-C1010 | Civil: platform trenches and duct banks - Riyadh (Malaz) | CON.RYD.ERY.CIV | Construction | ERY | MS5 | 20% |  |  | 0.19576 |  | 121042 |  | MS5 Installation 20% x station price share 4.99% ¦ BOQ civil share 35.6% x 55% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 701,825) | 383 |  | 2027-03-22 | 2027-06-14 | 56
ERY-C1020 | Civil: camera and ALPR pole foundations and poles - Riyadh (Malaz) | CON.RYD.ERY.CIV | Construction | ERY | MS5 | 20% |  |  | 0.16017 |  | 99034 |  | MS5 Installation 20% x station price share 4.99% ¦ BOQ civil share 35.6% x 45% (poles) | Annex 3 A6 Civil works (SAR 701,825) | 287 |  | 2027-05-11 | 2027-07-18 | 44
ERY-C2010 | Install UPS, network switches and field cabinets - Riyadh (Malaz) | CON.RYD.ERY.INS | Construction | ERY | MS5 | 20% |  |  | 0.12881 |  | 79646 |  | MS5 Installation 20% x station price share 4.99% ¦ Installation key 20% x (1 - civil share 35.6%) | Annex 3 equipment sections A1-A5 (installation share) | 144 |  | 2027-08-16 | 2027-08-26 | 9
ERY-C2020 | Cabling and termination (power, fibre, data) - Riyadh (Malaz) | CON.RYD.ERY.INS | Construction | ERY | MS5 | 20% |  |  | 0.19322 |  | 119468 |  | MS5 Installation 20% x station price share 4.99% ¦ Installation key 30% x (1 - civil share 35.6%) | Annex 3 equipment sections A1-A5 (installation share) | 287 |  | 2027-08-19 | 2027-09-08 | 15
ERY-C2030 | Install and aim CCTV cameras - Riyadh (Malaz) | CON.RYD.ERY.INS | Construction | ERY | MS5 | 20% |  |  | 0.16102 |  | 99557 |  | MS5 Installation 20% x station price share 4.99% ¦ Installation key 25% x (1 - civil share 35.6%) | Annex 3 equipment sections A1-A5 (installation share) | 239 |  | 2027-09-09 | 2027-09-27 | 12
ERY-C2040 | Install video management, video wall and control-room equipment - Riyadh (Malaz) | CON.RYD.ERY.INS | Construction | ERY | MS5 | 20% |  |  | 0.09661 |  | 59734 |  | MS5 Installation 20% x station price share 4.99% ¦ Installation key 15% x (1 - civil share 35.6%) | Annex 3 equipment sections A1-A5 (installation share) | 144 |  | 2027-08-29 | 2027-09-12 | 11
ERY-C2050 | Install access control and intercom - Riyadh (Malaz) | CON.RYD.ERY.INS | Construction | ERY | MS5 | 20% |  |  | 0.064407 |  | 39823 |  | MS5 Installation 20% x station price share 4.99% ¦ Installation key 10% x (1 - civil share 35.6%) | Annex 3 equipment sections A1-A5 (installation share) | 96 |  | 2027-09-01 | 2027-09-13 | 9
ERY-T1010 | Pre-commissioning and loop checks - Riyadh (Malaz) | COM.RYD.ERY.TST | Commissioning and handover | ERY | MS6 | 10% |  |  | 0.4 |  | 123661 |  | MS6 Testing and commissioning (SAT) 10% x station price share 4.99% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 144 |  | 2027-09-28 | 2027-10-05 | 6
ERY-T1020 | Site acceptance test (SAT) and commissioning - Riyadh (Malaz) | COM.RYD.ERY.TST | Commissioning and handover | ERY | MS6 | 10% |  |  | 0.6 |  | 185491 |  | MS6 Testing and commissioning (SAT) 10% x station price share 4.99% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 191 |  | 2027-10-06 | 2027-10-18 | 9
ERY-T2010 | Operator and maintenance training - Riyadh (Malaz) | COM.RYD.ERY.TRN | Commissioning and handover | ERY | MS7 | 10% |  |  | 0.15 |  | 46373 |  | MS7 Final acceptance and handover 10% x station price share 4.99% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 96 |  | 2027-10-19 | 2027-11-01 | 10
ERY-T2020 | Trial operation (maximum 45 days) - Riyadh (Malaz) | COM.RYD.ERY.TOA | Commissioning and handover | ERY | MS7 | 10% |  |  | 0.35 |  | 108203 |  | MS7 Final acceptance and handover 10% x station price share 4.99% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 144 |  | 2027-10-19 | 2027-11-29 | 30
ERY-T3010 | Taking-over application, SAR review and handover - Riyadh (Malaz) | COM.RYD.ERY.TOA | Commissioning and handover | ERY | MS7 | 10% |  |  | 0.3 |  | 92746 |  | MS7 Final acceptance and handover 10% x station price share 4.99% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 144 |  | 2027-11-30 | 2027-12-13 | 10
HJD-E1010 | Survey: submittal of site survey and as-found report - Jeddah | ENG.HHR.HJD.SRV.SUB | Engineering | HJD | MS2 | 10% |  |  | 0.05 |  | 47754 |  | MS2 Engineering submittal 10% x station price share 15.40% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 114 |  | 2027-03-04 | 2027-04-07 | 20
HJD-E1020 | Survey: SAR approval of survey report - Jeddah | ENG.HHR.HJD.SRV.APR | Engineering | HJD | MS3 | 10% |  |  | 0.05 |  | 47754 |  | MS3 SAR approval of engineering 10% x station price share 15.40% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 28 |  | 2027-04-08 | 2027-04-14 | 5
HJD-E1030 | Concept design: submittal - Jeddah | ENG.HHR.HJD.CNC.SUB | Engineering | HJD | MS2 | 10% |  |  | 0.1 |  | 95509 |  | MS2 Engineering submittal 10% x station price share 15.40% ¦ Design stage key 10% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 62 |  | 2027-04-08 | 2027-04-19 | 8
HJD-E1040 | Concept design: SAR review and approval - Jeddah | ENG.HHR.HJD.CNC.APR | Engineering | HJD | MS3 | 10% |  |  | 0.1 |  | 95509 |  | MS3 SAR approval of engineering 10% x station price share 15.40% ¦ Design stage key 10% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 116 |  | 2027-04-20 | 2027-05-10 | 15
HJD-E1050 | Preliminary design: submittal - Jeddah | ENG.HHR.HJD.PRE.SUB | Engineering | HJD | MS2 | 10% |  |  | 0.2 |  | 191018 |  | MS2 Engineering submittal 10% x station price share 15.40% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 148 |  | 2027-04-20 | 2027-05-06 | 13
HJD-E1060 | Preliminary design: SAR review and approval - Jeddah | ENG.HHR.HJD.PRE.APR | Engineering | HJD | MS3 | 10% |  |  | 0.2 |  | 191018 |  | MS3 SAR approval of engineering 10% x station price share 15.40% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 171 |  | 2027-05-09 | 2027-06-03 | 15
HJD-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Jeddah | ENG.HHR.HJD.DET.SUB | Engineering | HJD | MS2 | 10% |  |  | 0.4 |  | 382035 |  | MS2 Engineering submittal 10% x station price share 15.40% ¦ Design stage key 40% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 304 |  | 2027-05-09 | 2027-06-10 | 20
HJD-E1080 | Detailed design: SAR review and approval - Jeddah | ENG.HHR.HJD.DET.APR | Engineering | HJD | MS3 | 10% |  |  | 0.4 |  | 382035 |  | MS3 SAR approval of engineering 10% x station price share 15.40% ¦ Design stage key 40% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 228 |  | 2027-06-13 | 2027-07-01 | 15
HJD-E1090 | IFC and shop drawings: submittal - Jeddah | ENG.HHR.HJD.IFC.SUB | Engineering | HJD | MS2 | 10% |  |  | 0.2 |  | 191018 |  | MS2 Engineering submittal 10% x station price share 15.40% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 120 |  | 2027-06-13 | 2027-06-23 | 9
HJD-E1100 | IFC and shop drawings: SAR approval and release - Jeddah | ENG.HHR.HJD.IFC.APR | Engineering | HJD | MS3 | 10% |  |  | 0.2 |  | 191018 |  | MS3 SAR approval of engineering 10% x station price share 15.40% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 200 |  | 2027-06-24 | 2027-07-14 | 15
HJD-E1110 | HCIS Stage 3 and 4 documents: preparation - Jeddah | ENG.HHR.HJD.HCS.SUB | Engineering | HJD | MS2 | 10% |  |  | 0.05 |  | 47754 |  | MS2 Engineering submittal 10% x station price share 15.40% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 62 |  | 2027-05-26 | 2027-06-23 | 21
HJD-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Jeddah | ENG.HHR.HJD.HCS.APR | Engineering | HJD | MS3 | 10% |  |  | 0.05 |  | 47754 |  | MS3 SAR approval of engineering 10% x station price share 15.40% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 44 |  | 2027-06-24 | 2027-07-14 | 15
HJD-E1130 | As-built and O&M documentation: submittal - Jeddah | ENG.HHR.HJD.ASB.SUB | Engineering | HJD | MS7 | 10% |  |  | 0.15 |  | 143263 |  | MS7 Final acceptance and handover 10% x station price share 15.40% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 129 |  | 2028-06-18 | 2028-08-10 | 40
HJD-E1140 | As-built and O&M documentation: SAR review and approval - Jeddah | ENG.HHR.HJD.ASB.APR | Engineering | HJD | MS7 | 10% |  |  | 0.05 |  | 47754 |  | MS7 Final acceptance and handover 10% x station price share 15.40% ¦ Fixed key 5% | Annex 3 documentation share | 48 |  | 2028-08-13 | 2028-08-31 | 15
HJD-P1010 | Manufacture CCTV cameras and analytics - Jeddah | PRO.HHR.HJD.CCT | Procurement | HJD | MS4 | 20% |  |  | 0.20742 |  | 396208 |  | MS4 Material delivery 20% x station price share 15.40% ¦ BOQ section share 27.7% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 1,391,206) | 982 |  | 2027-07-15 | 2027-11-18 | 90
HJD-P1020 | Manufacture video management servers, storage and video wall - Jeddah | PRO.HHR.HJD.VMS | Procurement | HJD | MS4 | 20% |  |  | 0.097222 |  | 185712 |  | MS4 Material delivery 20% x station price share 15.40% ¦ BOQ section share 13.0% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 652,091) | 460 |  | 2027-07-15 | 2027-11-18 | 90
HJD-P1030 | Manufacture access control and intercom equipment - Jeddah | PRO.HHR.HJD.ACC | Procurement | HJD | MS4 | 20% |  |  | 0.0065728 |  | 12555 |  | MS4 Material delivery 20% x station price share 15.40% ¦ BOQ section share 0.9% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 31 |  | 2027-07-15 | 2027-11-18 | 90
HJD-P1040 | Manufacture UPS, network switches and field cabinets - Jeddah | PRO.HHR.HJD.UPN | Procurement | HJD | MS4 | 20% |  |  | 0.43879 |  | 838157 |  | MS4 Material delivery 20% x station price share 15.40% ¦ BOQ section share 58.5% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 2,943,020) | 2077 |  | 2027-07-15 | 2027-11-18 | 90
HJD-P1050 | Factory acceptance test at vendor premises - Jeddah | PRO.HHR.HJD.LOG | Procurement | HJD | MS4 | 20% |  |  | 0.05 |  | 95509 |  | MS4 Material delivery 20% x station price share 15.40% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 592 |  | 2027-11-21 | 2027-12-02 | 10
HJD-P1060 | Shipping and customs clearance - Jeddah | PRO.HHR.HJD.LOG | Procurement | HJD | MS4 | 20% |  |  | 0.15 |  | 286526 |  | MS4 Material delivery 20% x station price share 15.40% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 1184 |  | 2027-12-05 | 2028-01-20 | 35
HJD-P1070 | Delivery to station and receiving inspection - Jeddah | PRO.HHR.HJD.LOG | Procurement | HJD | MS4 | 20% |  |  | 0.05 |  | 95509 |  | MS4 Material delivery 20% x station price share 15.40% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 592 |  | 2028-01-23 | 2028-01-27 | 5
HJD-C1010 | Civil: platform trenches and duct banks - Jeddah | CON.HHR.HJD.CIV | Construction | HJD | MS5 | 20% |  |  | 0.051682 |  | 98722 |  | MS5 Installation 20% x station price share 15.40% ¦ BOQ civil share 9.4% x 55% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 521,718) | 1183 |  | 2027-07-15 | 2027-09-16 | 46
HJD-C1020 | Civil: camera and ALPR pole foundations and poles - Jeddah | CON.HHR.HJD.CIV | Construction | HJD | MS5 | 20% |  |  | 0.042285 |  | 80772 |  | MS5 Installation 20% x station price share 15.40% ¦ BOQ civil share 9.4% x 45% (poles) | Annex 3 A6 Civil works (SAR 521,718) | 887 |  | 2027-08-25 | 2027-10-14 | 36
HJD-C2010 | Install UPS, network switches and field cabinets - Jeddah | CON.HHR.HJD.INS | Construction | HJD | MS5 | 20% |  |  | 0.18121 |  | 346136 |  | MS5 Installation 20% x station price share 15.40% ¦ Installation key 20% x (1 - civil share 9.4%) | Annex 3 equipment sections A1-A5 (installation share) | 444 |  | 2028-01-30 | 2028-03-13 | 27
HJD-C2020 | Cabling and termination (power, fibre, data) - Jeddah | CON.HHR.HJD.INS | Construction | HJD | MS5 | 20% |  |  | 0.27181 |  | 519205 |  | MS5 Installation 20% x station price share 15.40% ¦ Installation key 30% x (1 - civil share 9.4%) | Annex 3 equipment sections A1-A5 (installation share) | 887 |  | 2028-02-10 | 2028-04-19 | 45
HJD-C2030 | Install and aim CCTV cameras - Jeddah | CON.HHR.HJD.INS | Construction | HJD | MS5 | 20% |  |  | 0.22651 |  | 432670 |  | MS5 Installation 20% x station price share 15.40% ¦ Installation key 25% x (1 - civil share 9.4%) | Annex 3 equipment sections A1-A5 (installation share) | 739 |  | 2028-04-20 | 2028-06-15 | 36
HJD-C2040 | Install video management, video wall and control-room equipment - Jeddah | CON.HHR.HJD.INS | Construction | HJD | MS5 | 20% |  |  | 0.1359 |  | 259602 |  | MS5 Installation 20% x station price share 15.40% ¦ Installation key 15% x (1 - civil share 9.4%) | Annex 3 equipment sections A1-A5 (installation share) | 444 |  | 2028-03-14 | 2028-04-25 | 31
HJD-C2050 | Install access control and intercom - Jeddah | CON.HHR.HJD.INS | Construction | HJD | MS5 | 20% |  |  | 0.090603 |  | 173068 |  | MS5 Installation 20% x station price share 15.40% ¦ Installation key 10% x (1 - civil share 9.4%) | Annex 3 equipment sections A1-A5 (installation share) | 296 |  | 2028-03-27 | 2028-05-09 | 27
HJD-T1010 | Pre-commissioning and loop checks - Jeddah | COM.HHR.HJD.TST | Commissioning and handover | HJD | MS6 | 10% |  |  | 0.4 |  | 382035 |  | MS6 Testing and commissioning (SAT) 10% x station price share 15.40% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 444 |  | 2028-06-18 | 2028-06-29 | 10
HJD-T1020 | Site acceptance test (SAT) and commissioning - Jeddah | COM.HHR.HJD.TST | Commissioning and handover | HJD | MS6 | 10% |  |  | 0.6 |  | 573053 |  | MS6 Testing and commissioning (SAT) 10% x station price share 15.40% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 592 |  | 2028-07-02 | 2028-07-20 | 15
HJD-T2010 | Operator and maintenance training - Jeddah | COM.HHR.HJD.TRN | Commissioning and handover | HJD | MS7 | 10% |  |  | 0.15 |  | 143263 |  | MS7 Final acceptance and handover 10% x station price share 15.40% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 296 |  | 2028-07-23 | 2028-08-03 | 10
HJD-T2020 | Trial operation (maximum 45 days) - Jeddah | COM.HHR.HJD.TOA | Commissioning and handover | HJD | MS7 | 10% |  |  | 0.35 |  | 334281 |  | MS7 Final acceptance and handover 10% x station price share 15.40% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 444 |  | 2028-07-23 | 2028-08-31 | 30
HJD-T3010 | Taking-over application, SAR review and handover - Jeddah | COM.HHR.HJD.TOA | Commissioning and handover | HJD | MS7 | 10% |  |  | 0.3 |  | 286526 |  | MS7 Final acceptance and handover 10% x station price share 15.40% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 444 |  | 2028-09-03 | 2028-09-21 | 15
EDM-E1010 | Survey: submittal of site survey and as-found report - Dammam | ENG.EWR.EDM.SRV.SUB | Engineering | EDM | MS2 | 10% |  |  | 0.05 |  | 15938 |  | MS2 Engineering submittal 10% x station price share 5.14% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 32 |  | 2027-06-24 | 2027-07-07 | 10
EDM-E1020 | Survey: SAR approval of survey report - Dammam | ENG.EWR.EDM.SRV.APR | Engineering | EDM | MS3 | 10% |  |  | 0.05 |  | 15938 |  | MS3 SAR approval of engineering 10% x station price share 5.14% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 16 |  | 2027-07-08 | 2027-07-14 | 5
EDM-E1030 | Concept design: submittal - Dammam | ENG.EWR.EDM.CNC.SUB | Engineering | EDM | MS2 | 10% |  |  | 0.1 |  | 31875 |  | MS2 Engineering submittal 10% x station price share 5.14% ¦ Design stage key 10% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 15 |  | 2027-07-08 | 2027-07-14 | 5
EDM-E1040 | Concept design: SAR review and approval - Dammam | ENG.EWR.EDM.CNC.APR | Engineering | EDM | MS3 | 10% |  |  | 0.1 |  | 31875 |  | MS3 SAR approval of engineering 10% x station price share 5.14% ¦ Design stage key 10% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 44 |  | 2027-07-15 | 2027-08-04 | 15
EDM-E1050 | Preliminary design: submittal - Dammam | ENG.EWR.EDM.PRE.SUB | Engineering | EDM | MS2 | 10% |  |  | 0.2 |  | 63750 |  | MS2 Engineering submittal 10% x station price share 5.14% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 37 |  | 2027-07-15 | 2027-07-26 | 8
EDM-E1060 | Preliminary design: SAR review and approval - Dammam | ENG.EWR.EDM.PRE.APR | Engineering | EDM | MS3 | 10% |  |  | 0.2 |  | 63750 |  | MS3 SAR approval of engineering 10% x station price share 5.14% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 70 |  | 2027-07-27 | 2027-08-16 | 15
EDM-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Dammam | ENG.EWR.EDM.DET.SUB | Engineering | EDM | MS2 | 10% |  |  | 0.4 |  | 127500 |  | MS2 Engineering submittal 10% x station price share 5.14% ¦ Design stage key 40% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 79 |  | 2027-07-27 | 2027-08-11 | 12
EDM-E1080 | Detailed design: SAR review and approval - Dammam | ENG.EWR.EDM.DET.APR | Engineering | EDM | MS3 | 10% |  |  | 0.4 |  | 127500 |  | MS3 SAR approval of engineering 10% x station price share 5.14% ¦ Design stage key 40% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 99 |  | 2027-08-12 | 2027-09-01 | 15
EDM-E1090 | IFC and shop drawings: submittal - Dammam | ENG.EWR.EDM.IFC.SUB | Engineering | EDM | MS2 | 10% |  |  | 0.2 |  | 63750 |  | MS2 Engineering submittal 10% x station price share 5.14% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 27 |  | 2027-08-12 | 2027-08-18 | 5
EDM-E1100 | IFC and shop drawings: SAR approval and release - Dammam | ENG.EWR.EDM.IFC.APR | Engineering | EDM | MS3 | 10% |  |  | 0.2 |  | 63750 |  | MS3 SAR approval of engineering 10% x station price share 5.14% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 80 |  | 2027-08-19 | 2027-09-08 | 15
EDM-E1110 | HCIS Stage 3 and 4 documents: preparation - Dammam | ENG.EWR.EDM.HCS.SUB | Engineering | EDM | MS2 | 10% |  |  | 0.05 |  | 15938 |  | MS2 Engineering submittal 10% x station price share 5.14% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 16 |  | 2027-08-03 | 2027-08-18 | 12
EDM-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Dammam | ENG.EWR.EDM.HCS.APR | Engineering | EDM | MS3 | 10% |  |  | 0.05 |  | 15938 |  | MS3 SAR approval of engineering 10% x station price share 5.14% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 20 |  | 2027-08-19 | 2027-09-08 | 15
EDM-E1130 | As-built and O&M documentation: submittal - Dammam | ENG.EWR.EDM.ASB.SUB | Engineering | EDM | MS7 | 10% |  |  | 0.15 |  | 47813 |  | MS7 Final acceptance and handover 10% x station price share 5.14% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 39 |  | 2028-04-02 | 2028-05-18 | 30
EDM-E1140 | As-built and O&M documentation: SAR review and approval - Dammam | ENG.EWR.EDM.ASB.APR | Engineering | EDM | MS7 | 10% |  |  | 0.05 |  | 15938 |  | MS7 Final acceptance and handover 10% x station price share 5.14% ¦ Fixed key 5% | Annex 3 documentation share | 20 |  | 2028-05-21 | 2028-06-08 | 15
EDM-P1010 | Manufacture CCTV cameras and analytics - Dammam | PRO.EWR.EDM.CCT | Procurement | EDM | MS4 | 20% |  |  | 0.15598 |  | 99436 |  | MS4 Material delivery 20% x station price share 5.14% ¦ BOQ section share 20.8% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 276,849) | 246 |  | 2027-09-09 | 2027-12-16 | 70
EDM-P1020 | Manufacture video management servers, storage and video wall - Dammam | PRO.EWR.EDM.VMS | Procurement | EDM | MS4 | 20% |  |  | 0.23218 |  | 148015 |  | MS4 Material delivery 20% x station price share 5.14% ¦ BOQ section share 31.0% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 412,102) | 367 |  | 2027-09-09 | 2027-12-16 | 70
EDM-P1030 | Manufacture access control and intercom equipment - Dammam | PRO.EWR.EDM.ACC | Procurement | EDM | MS4 | 20% |  |  | 0.024838 |  | 15834 |  | MS4 Material delivery 20% x station price share 5.14% ¦ BOQ section share 3.3% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 39 |  | 2027-09-09 | 2027-12-16 | 70
EDM-P1040 | Manufacture UPS, network switches and field cabinets - Dammam | PRO.EWR.EDM.UPN | Procurement | EDM | MS4 | 20% |  |  | 0.337 |  | 214841 |  | MS4 Material delivery 20% x station price share 5.14% ¦ BOQ section share 44.9% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 598,156) | 532 |  | 2027-09-09 | 2027-12-16 | 70
EDM-P1050 | Factory acceptance test at vendor premises - Dammam | PRO.EWR.EDM.LOG | Procurement | EDM | MS4 | 20% |  |  | 0.05 |  | 31875 |  | MS4 Material delivery 20% x station price share 5.14% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 197 |  | 2027-12-19 | 2027-12-30 | 10
EDM-P1060 | Shipping and customs clearance - Dammam | PRO.EWR.EDM.LOG | Procurement | EDM | MS4 | 20% |  |  | 0.15 |  | 95625 |  | MS4 Material delivery 20% x station price share 5.14% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 395 |  | 2028-01-02 | 2028-02-03 | 25
EDM-P1070 | Delivery to station and receiving inspection - Dammam | PRO.EWR.EDM.LOG | Procurement | EDM | MS4 | 20% |  |  | 0.05 |  | 31875 |  | MS4 Material delivery 20% x station price share 5.14% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 197 |  | 2028-02-06 | 2028-02-10 | 5
EDM-C1010 | Civil: platform trenches and duct banks - Dammam | CON.EWR.EDM.CIV | Construction | EDM | MS5 | 20% |  |  | 0.18987 |  | 121040 |  | MS5 Installation 20% x station price share 5.14% ¦ BOQ civil share 34.5% x 55% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 701,813) | 395 |  | 2027-09-09 | 2027-11-28 | 56
EDM-C1020 | Civil: camera and ALPR pole foundations and poles - Dammam | CON.EWR.EDM.CIV | Construction | EDM | MS5 | 20% |  |  | 0.15534 |  | 99032 |  | MS5 Installation 20% x station price share 5.14% ¦ BOQ civil share 34.5% x 45% (poles) | Annex 3 A6 Civil works (SAR 701,813) | 296 |  | 2027-11-01 | 2027-12-30 | 44
EDM-C2010 | Install UPS, network switches and field cabinets - Dammam | CON.EWR.EDM.INS | Construction | EDM | MS5 | 20% |  |  | 0.13096 |  | 83486 |  | MS5 Installation 20% x station price share 5.14% ¦ Installation key 20% x (1 - civil share 34.5%) | Annex 3 equipment sections A1-A5 (installation share) | 148 |  | 2028-02-13 | 2028-03-01 | 9
EDM-C2020 | Cabling and termination (power, fibre, data) - Dammam | CON.EWR.EDM.INS | Construction | EDM | MS5 | 20% |  |  | 0.19644 |  | 125229 |  | MS5 Installation 20% x station price share 5.14% ¦ Installation key 30% x (1 - civil share 34.5%) | Annex 3 equipment sections A1-A5 (installation share) | 296 |  | 2028-02-16 | 2028-03-14 | 15
EDM-C2030 | Install and aim CCTV cameras - Dammam | CON.EWR.EDM.INS | Construction | EDM | MS5 | 20% |  |  | 0.1637 |  | 104358 |  | MS5 Installation 20% x station price share 5.14% ¦ Installation key 25% x (1 - civil share 34.5%) | Annex 3 equipment sections A1-A5 (installation share) | 247 |  | 2028-03-15 | 2028-03-30 | 12
EDM-C2040 | Install video management, video wall and control-room equipment - Dammam | CON.EWR.EDM.INS | Construction | EDM | MS5 | 20% |  |  | 0.098219 |  | 62615 |  | MS5 Installation 20% x station price share 5.14% ¦ Installation key 15% x (1 - civil share 34.5%) | Annex 3 equipment sections A1-A5 (installation share) | 148 |  | 2028-03-02 | 2028-03-16 | 11
EDM-C2050 | Install access control and intercom - Dammam | CON.EWR.EDM.INS | Construction | EDM | MS5 | 20% |  |  | 0.065479 |  | 41743 |  | MS5 Installation 20% x station price share 5.14% ¦ Installation key 10% x (1 - civil share 34.5%) | Annex 3 equipment sections A1-A5 (installation share) | 99 |  | 2028-03-07 | 2028-03-19 | 9
EDM-T1010 | Pre-commissioning and loop checks - Dammam | COM.EWR.EDM.TST | Commissioning and handover | EDM | MS6 | 10% |  |  | 0.4 |  | 127500 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.14% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 148 |  | 2028-04-02 | 2028-04-09 | 6
EDM-T1020 | Site acceptance test (SAT) and commissioning - Dammam | COM.EWR.EDM.TST | Commissioning and handover | EDM | MS6 | 10% |  |  | 0.6 |  | 191251 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.14% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 197 |  | 2028-04-10 | 2028-04-20 | 9
EDM-T2010 | Operator and maintenance training - Dammam | COM.EWR.EDM.TRN | Commissioning and handover | EDM | MS7 | 10% |  |  | 0.15 |  | 47813 |  | MS7 Final acceptance and handover 10% x station price share 5.14% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 99 |  | 2028-04-23 | 2028-05-11 | 10
EDM-T2020 | Trial operation (maximum 45 days) - Dammam | COM.EWR.EDM.TOA | Commissioning and handover | EDM | MS7 | 10% |  |  | 0.35 |  | 111563 |  | MS7 Final acceptance and handover 10% x station price share 5.14% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 148 |  | 2028-04-23 | 2028-06-08 | 30
EDM-T3010 | Taking-over application, SAR review and handover - Dammam | COM.EWR.EDM.TOA | Commissioning and handover | EDM | MS7 | 10% |  |  | 0.3 |  | 95625 |  | MS7 Final acceptance and handover 10% x station price share 5.14% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 148 |  | 2028-06-11 | 2028-06-22 | 10
NQS-E1010 | Survey: submittal of site survey and as-found report - Al Qassim | ENG.NSR.NQS.SRV.SUB | Engineering | NQS | MS2 | 10% |  |  | 0.05 |  | 16995 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 34 |  | 2027-08-19 | 2027-09-01 | 10
NQS-E1020 | Survey: SAR approval of survey report - Al Qassim | ENG.NSR.NQS.SRV.APR | Engineering | NQS | MS3 | 10% |  |  | 0.05 |  | 16995 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 17 |  | 2027-09-02 | 2027-09-08 | 5
NQS-E1030 | Concept design: submittal - Al Qassim | ENG.NSR.NQS.CNC.SUB | Engineering | NQS | MS2 | 10% |  |  | 0.1 |  | 33989 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 10% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 16 |  | 2027-09-02 | 2027-09-08 | 5
NQS-E1040 | Concept design: SAR review and approval - Al Qassim | ENG.NSR.NQS.CNC.APR | Engineering | NQS | MS3 | 10% |  |  | 0.1 |  | 33989 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 10% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 47 |  | 2027-09-09 | 2027-09-30 | 15
NQS-E1050 | Preliminary design: submittal - Al Qassim | ENG.NSR.NQS.PRE.SUB | Engineering | NQS | MS2 | 10% |  |  | 0.2 |  | 67978 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 40 |  | 2027-09-09 | 2027-09-20 | 8
NQS-E1060 | Preliminary design: SAR review and approval - Al Qassim | ENG.NSR.NQS.PRE.APR | Engineering | NQS | MS3 | 10% |  |  | 0.2 |  | 67978 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 74 |  | 2027-09-21 | 2027-10-12 | 15
NQS-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Al Qassim | ENG.NSR.NQS.DET.SUB | Engineering | NQS | MS2 | 10% |  |  | 0.4 |  | 135957 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 40% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 84 |  | 2027-09-21 | 2027-10-07 | 12
NQS-E1080 | Detailed design: SAR review and approval - Al Qassim | ENG.NSR.NQS.DET.APR | Engineering | NQS | MS3 | 10% |  |  | 0.4 |  | 135957 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 40% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 105 |  | 2027-10-10 | 2027-10-28 | 15
NQS-E1090 | IFC and shop drawings: submittal - Al Qassim | ENG.NSR.NQS.IFC.SUB | Engineering | NQS | MS2 | 10% |  |  | 0.2 |  | 67978 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 28 |  | 2027-10-10 | 2027-10-14 | 5
NQS-E1100 | IFC and shop drawings: SAR approval and release - Al Qassim | ENG.NSR.NQS.IFC.APR | Engineering | NQS | MS3 | 10% |  |  | 0.2 |  | 67978 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 85 |  | 2027-10-17 | 2027-11-04 | 15
NQS-E1110 | HCIS Stage 3 and 4 documents: preparation - Al Qassim | ENG.NSR.NQS.HCS.SUB | Engineering | NQS | MS2 | 10% |  |  | 0.05 |  | 16995 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 17 |  | 2027-09-29 | 2027-10-14 | 12
NQS-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Al Qassim | ENG.NSR.NQS.HCS.APR | Engineering | NQS | MS3 | 10% |  |  | 0.05 |  | 16995 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 21 |  | 2027-10-17 | 2027-11-04 | 15
NQS-E1130 | As-built and O&M documentation: submittal - Al Qassim | ENG.NSR.NQS.ASB.SUB | Engineering | NQS | MS7 | 10% |  |  | 0.15 |  | 50984 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 42 |  | 2028-06-12 | 2028-07-23 | 30
NQS-E1140 | As-built and O&M documentation: SAR review and approval - Al Qassim | ENG.NSR.NQS.ASB.APR | Engineering | NQS | MS7 | 10% |  |  | 0.05 |  | 16995 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 5% | Annex 3 documentation share | 21 |  | 2028-07-24 | 2028-08-13 | 15
NQS-P1010 | Manufacture CCTV cameras and analytics - Al Qassim | PRO.NSR.NQS.CCT | Procurement | NQS | MS4 | 20% |  |  | 0.15324 |  | 104169 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 20.4% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 338,989) | 258 |  | 2027-11-07 | 2028-02-10 | 70
NQS-P1020 | Manufacture video management servers, storage and video wall - Al Qassim | PRO.NSR.NQS.VMS | Procurement | NQS | MS4 | 20% |  |  | 0.16238 |  | 110385 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 21.7% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 359,215) | 273 |  | 2027-11-07 | 2028-02-10 | 70
NQS-P1030 | Manufacture access control and intercom equipment - Al Qassim | PRO.NSR.NQS.ACC | Procurement | NQS | MS4 | 20% |  |  | 0.019928 |  | 13547 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 2.7% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 34 |  | 2027-11-07 | 2028-02-10 | 70
NQS-P1040 | Manufacture UPS, network switches and field cabinets - Al Qassim | PRO.NSR.NQS.UPN | Procurement | NQS | MS4 | 20% |  |  | 0.41445 |  | 281736 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 55.3% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 916,830) | 698 |  | 2027-11-07 | 2028-02-10 | 70
NQS-P1050 | Factory acceptance test at vendor premises - Al Qassim | PRO.NSR.NQS.LOG | Procurement | NQS | MS4 | 20% |  |  | 0.05 |  | 33989 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 211 |  | 2028-02-13 | 2028-03-02 | 10
NQS-P1060 | Shipping and customs clearance - Al Qassim | PRO.NSR.NQS.LOG | Procurement | NQS | MS4 | 20% |  |  | 0.15 |  | 101967 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 421 |  | 2028-03-05 | 2028-04-06 | 25
NQS-P1070 | Delivery to station and receiving inspection - Al Qassim | PRO.NSR.NQS.LOG | Procurement | NQS | MS4 | 20% |  |  | 0.05 |  | 33989 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 211 |  | 2028-04-09 | 2028-04-13 | 5
NQS-C1010 | Civil: platform trenches and duct banks - Al Qassim | CON.NSR.NQS.CIV | Construction | NQS | MS5 | 20% |  |  | 0.17055 |  | 115940 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 55% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 745,743) | 421 |  | 2027-11-07 | 2028-01-26 | 59
NQS-C1020 | Civil: camera and ALPR pole foundations and poles - Al Qassim | CON.NSR.NQS.CIV | Construction | NQS | MS5 | 20% |  |  | 0.13954 |  | 94860 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 45% (poles) | Annex 3 A6 Civil works (SAR 745,743) | 316 |  | 2027-12-29 | 2028-03-09 | 47
NQS-C2010 | Install UPS, network switches and field cabinets - Al Qassim | CON.NSR.NQS.INS | Construction | NQS | MS5 | 20% |  |  | 0.13798 |  | 93797 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 20% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 158 |  | 2028-04-16 | 2028-05-07 | 11
NQS-C2020 | Cabling and termination (power, fibre, data) - Al Qassim | CON.NSR.NQS.INS | Construction | NQS | MS5 | 20% |  |  | 0.20697 |  | 140695 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 30% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 316 |  | 2028-04-20 | 2028-05-22 | 18
NQS-C2030 | Install and aim CCTV cameras - Al Qassim | CON.NSR.NQS.INS | Construction | NQS | MS5 | 20% |  |  | 0.17248 |  | 117246 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 25% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 263 |  | 2028-05-23 | 2028-06-11 | 14
NQS-C2040 | Install video management, video wall and control-room equipment - Al Qassim | CON.NSR.NQS.INS | Construction | NQS | MS5 | 20% |  |  | 0.10349 |  | 70348 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 15% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 158 |  | 2028-05-08 | 2028-05-23 | 12
NQS-C2050 | Install access control and intercom - Al Qassim | CON.NSR.NQS.INS | Construction | NQS | MS5 | 20% |  |  | 0.06899 |  | 46898 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 10% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 105 |  | 2028-05-14 | 2028-05-28 | 11
NQS-T1010 | Pre-commissioning and loop checks - Al Qassim | COM.NSR.NQS.TST | Commissioning and handover | NQS | MS6 | 10% |  |  | 0.4 |  | 135957 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.48% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 158 |  | 2028-06-12 | 2028-06-19 | 6
NQS-T1020 | Site acceptance test (SAT) and commissioning - Al Qassim | COM.NSR.NQS.TST | Commissioning and handover | NQS | MS6 | 10% |  |  | 0.6 |  | 203935 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.48% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 211 |  | 2028-06-20 | 2028-07-02 | 9
NQS-T2010 | Operator and maintenance training - Al Qassim | COM.NSR.NQS.TRN | Commissioning and handover | NQS | MS7 | 10% |  |  | 0.15 |  | 50984 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 105 |  | 2028-07-03 | 2028-07-16 | 10
NQS-T2020 | Trial operation (maximum 45 days) - Al Qassim | COM.NSR.NQS.TOA | Commissioning and handover | NQS | MS7 | 10% |  |  | 0.35 |  | 118962 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 158 |  | 2028-07-03 | 2028-08-13 | 30
NQS-T3010 | Taking-over application, SAR review and handover - Al Qassim | COM.NSR.NQS.TOA | Commissioning and handover | NQS | MS7 | 10% |  |  | 0.3 |  | 101967 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 158 |  | 2028-08-14 | 2028-08-27 | 10
EHF-E1010 | Survey: submittal of site survey and as-found report - Hufuf | ENG.EWR.EHF.SRV.SUB | Engineering | EHF | MS2 | 10% |  |  | 0.05 |  | 14143 |  | MS2 Engineering submittal 10% x station price share 4.56% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 28 |  | 2027-08-19 | 2027-09-01 | 10
EHF-E1020 | Survey: SAR approval of survey report - Hufuf | ENG.EWR.EHF.SRV.APR | Engineering | EHF | MS3 | 10% |  |  | 0.05 |  | 14143 |  | MS3 SAR approval of engineering 10% x station price share 4.56% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 14 |  | 2027-09-02 | 2027-09-08 | 5
EHF-E1030 | Concept design: submittal - Hufuf | ENG.EWR.EHF.CNC.SUB | Engineering | EHF | MS2 | 10% |  |  | 0.1 |  | 28285 |  | MS2 Engineering submittal 10% x station price share 4.56% ¦ Design stage key 10% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 13 |  | 2027-09-02 | 2027-09-08 | 5
EHF-E1040 | Concept design: SAR review and approval - Hufuf | ENG.EWR.EHF.CNC.APR | Engineering | EHF | MS3 | 10% |  |  | 0.1 |  | 28285 |  | MS3 SAR approval of engineering 10% x station price share 4.56% ¦ Design stage key 10% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 39 |  | 2027-09-09 | 2027-09-30 | 15
EHF-E1050 | Preliminary design: submittal - Hufuf | ENG.EWR.EHF.PRE.SUB | Engineering | EHF | MS2 | 10% |  |  | 0.2 |  | 56570 |  | MS2 Engineering submittal 10% x station price share 4.56% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 33 |  | 2027-09-09 | 2027-09-20 | 8
EHF-E1060 | Preliminary design: SAR review and approval - Hufuf | ENG.EWR.EHF.PRE.APR | Engineering | EHF | MS3 | 10% |  |  | 0.2 |  | 56570 |  | MS3 SAR approval of engineering 10% x station price share 4.56% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 62 |  | 2027-09-21 | 2027-10-12 | 15
EHF-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Hufuf | ENG.EWR.EHF.DET.SUB | Engineering | EHF | MS2 | 10% |  |  | 0.4 |  | 113140 |  | MS2 Engineering submittal 10% x station price share 4.56% ¦ Design stage key 40% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 70 |  | 2027-09-21 | 2027-10-07 | 12
EHF-E1080 | Detailed design: SAR review and approval - Hufuf | ENG.EWR.EHF.DET.APR | Engineering | EHF | MS3 | 10% |  |  | 0.4 |  | 113140 |  | MS3 SAR approval of engineering 10% x station price share 4.56% ¦ Design stage key 40% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 88 |  | 2027-10-10 | 2027-10-28 | 15
EHF-E1090 | IFC and shop drawings: submittal - Hufuf | ENG.EWR.EHF.IFC.SUB | Engineering | EHF | MS2 | 10% |  |  | 0.2 |  | 56570 |  | MS2 Engineering submittal 10% x station price share 4.56% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 24 |  | 2027-10-10 | 2027-10-14 | 5
EHF-E1100 | IFC and shop drawings: SAR approval and release - Hufuf | ENG.EWR.EHF.IFC.APR | Engineering | EHF | MS3 | 10% |  |  | 0.2 |  | 56570 |  | MS3 SAR approval of engineering 10% x station price share 4.56% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 71 |  | 2027-10-17 | 2027-11-04 | 15
EHF-E1110 | HCIS Stage 3 and 4 documents: preparation - Hufuf | ENG.EWR.EHF.HCS.SUB | Engineering | EHF | MS2 | 10% |  |  | 0.05 |  | 14143 |  | MS2 Engineering submittal 10% x station price share 4.56% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 14 |  | 2027-09-29 | 2027-10-14 | 12
EHF-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Hufuf | ENG.EWR.EHF.HCS.APR | Engineering | EHF | MS3 | 10% |  |  | 0.05 |  | 14143 |  | MS3 SAR approval of engineering 10% x station price share 4.56% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 18 |  | 2027-10-17 | 2027-11-04 | 15
EHF-E1130 | As-built and O&M documentation: submittal - Hufuf | ENG.EWR.EHF.ASB.SUB | Engineering | EHF | MS7 | 10% |  |  | 0.15 |  | 42428 |  | MS7 Final acceptance and handover 10% x station price share 4.56% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 35 |  | 2028-06-04 | 2028-07-13 | 30
EHF-E1140 | As-built and O&M documentation: SAR review and approval - Hufuf | ENG.EWR.EHF.ASB.APR | Engineering | EHF | MS7 | 10% |  |  | 0.05 |  | 14143 |  | MS7 Final acceptance and handover 10% x station price share 4.56% ¦ Fixed key 5% | Annex 3 documentation share | 18 |  | 2028-07-16 | 2028-08-03 | 15
EHF-P1010 | Manufacture CCTV cameras and analytics - Hufuf | PRO.EWR.EHF.CCT | Procurement | EHF | MS4 | 20% |  |  | 0.12596 |  | 71254 |  | MS4 Material delivery 20% x station price share 4.56% ¦ BOQ section share 16.8% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 192,155) | 177 |  | 2027-11-07 | 2028-02-10 | 70
EHF-P1020 | Manufacture video management servers, storage and video wall - Hufuf | PRO.EWR.EHF.VMS | Procurement | EHF | MS4 | 20% |  |  | 0.22879 |  | 129428 |  | MS4 Material delivery 20% x station price share 4.56% ¦ BOQ section share 30.5% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 349,033) | 321 |  | 2027-11-07 | 2028-02-10 | 70
EHF-P1030 | Manufacture access control and intercom equipment - Hufuf | PRO.EWR.EHF.ACC | Procurement | EHF | MS4 | 20% |  |  | 0.028898 |  | 16348 |  | MS4 Material delivery 20% x station price share 4.56% ¦ BOQ section share 3.9% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 40 |  | 2027-11-07 | 2028-02-10 | 70
EHF-P1040 | Manufacture UPS, network switches and field cabinets - Hufuf | PRO.EWR.EHF.UPN | Procurement | EHF | MS4 | 20% |  |  | 0.36635 |  | 207246 |  | MS4 Material delivery 20% x station price share 4.56% ¦ BOQ section share 48.8% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 558,888) | 513 |  | 2027-11-07 | 2028-02-10 | 70
EHF-P1050 | Factory acceptance test at vendor premises - Hufuf | PRO.EWR.EHF.LOG | Procurement | EHF | MS4 | 20% |  |  | 0.05 |  | 28285 |  | MS4 Material delivery 20% x station price share 4.56% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 175 |  | 2028-02-13 | 2028-03-02 | 10
EHF-P1060 | Shipping and customs clearance - Hufuf | PRO.EWR.EHF.LOG | Procurement | EHF | MS4 | 20% |  |  | 0.15 |  | 84855 |  | MS4 Material delivery 20% x station price share 4.56% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 350 |  | 2028-03-05 | 2028-04-06 | 25
EHF-P1070 | Delivery to station and receiving inspection - Hufuf | PRO.EWR.EHF.LOG | Procurement | EHF | MS4 | 20% |  |  | 0.05 |  | 28285 |  | MS4 Material delivery 20% x station price share 4.56% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 175 |  | 2028-04-09 | 2028-04-13 | 5
EHF-C1010 | Civil: platform trenches and duct banks - Hufuf | CON.EWR.EHF.CIV | Construction | EHF | MS5 | 20% |  |  | 0.20118 |  | 113805 |  | MS5 Installation 20% x station price share 4.56% ¦ BOQ civil share 36.6% x 55% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 659,866) | 350 |  | 2027-11-07 | 2028-01-18 | 53
EHF-C1020 | Civil: camera and ALPR pole foundations and poles - Hufuf | CON.EWR.EHF.CIV | Construction | EHF | MS5 | 20% |  |  | 0.1646 |  | 93113 |  | MS5 Installation 20% x station price share 4.56% ¦ BOQ civil share 36.6% x 45% (poles) | Annex 3 A6 Civil works (SAR 659,866) | 263 |  | 2027-12-23 | 2028-02-17 | 41
EHF-C2010 | Install UPS, network switches and field cabinets - Hufuf | CON.EWR.EHF.INS | Construction | EHF | MS5 | 20% |  |  | 0.12685 |  | 71756 |  | MS5 Installation 20% x station price share 4.56% ¦ Installation key 20% x (1 - civil share 36.6%) | Annex 3 equipment sections A1-A5 (installation share) | 131 |  | 2028-04-16 | 2028-04-26 | 9
EHF-C2020 | Cabling and termination (power, fibre, data) - Hufuf | CON.EWR.EHF.INS | Construction | EHF | MS5 | 20% |  |  | 0.19027 |  | 107635 |  | MS5 Installation 20% x station price share 4.56% ¦ Installation key 30% x (1 - civil share 36.6%) | Annex 3 equipment sections A1-A5 (installation share) | 263 |  | 2028-04-19 | 2028-05-16 | 15
EHF-C2030 | Install and aim CCTV cameras - Hufuf | CON.EWR.EHF.INS | Construction | EHF | MS5 | 20% |  |  | 0.15856 |  | 89695 |  | MS5 Installation 20% x station price share 4.56% ¦ Installation key 25% x (1 - civil share 36.6%) | Annex 3 equipment sections A1-A5 (installation share) | 219 |  | 2028-05-17 | 2028-06-01 | 12
EHF-C2040 | Install video management, video wall and control-room equipment - Hufuf | CON.EWR.EHF.INS | Construction | EHF | MS5 | 20% |  |  | 0.095134 |  | 53817 |  | MS5 Installation 20% x station price share 4.56% ¦ Installation key 15% x (1 - civil share 36.6%) | Annex 3 equipment sections A1-A5 (installation share) | 131 |  | 2028-04-27 | 2028-05-18 | 11
EHF-C2050 | Install access control and intercom - Hufuf | CON.EWR.EHF.INS | Construction | EHF | MS5 | 20% |  |  | 0.063423 |  | 35878 |  | MS5 Installation 20% x station price share 4.56% ¦ Installation key 10% x (1 - civil share 36.6%) | Annex 3 equipment sections A1-A5 (installation share) | 88 |  | 2028-05-09 | 2028-05-21 | 9
EHF-T1010 | Pre-commissioning and loop checks - Hufuf | COM.EWR.EHF.TST | Commissioning and handover | EHF | MS6 | 10% |  |  | 0.4 |  | 113140 |  | MS6 Testing and commissioning (SAT) 10% x station price share 4.56% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 131 |  | 2028-06-04 | 2028-06-11 | 6
EHF-T1020 | Site acceptance test (SAT) and commissioning - Hufuf | COM.EWR.EHF.TST | Commissioning and handover | EHF | MS6 | 10% |  |  | 0.6 |  | 169710 |  | MS6 Testing and commissioning (SAT) 10% x station price share 4.56% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 175 |  | 2028-06-12 | 2028-06-22 | 9
EHF-T2010 | Operator and maintenance training - Hufuf | COM.EWR.EHF.TRN | Commissioning and handover | EHF | MS7 | 10% |  |  | 0.15 |  | 42428 |  | MS7 Final acceptance and handover 10% x station price share 4.56% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 88 |  | 2028-06-25 | 2028-07-06 | 10
EHF-T2020 | Trial operation (maximum 45 days) - Hufuf | COM.EWR.EHF.TOA | Commissioning and handover | EHF | MS7 | 10% |  |  | 0.35 |  | 98998 |  | MS7 Final acceptance and handover 10% x station price share 4.56% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 131 |  | 2028-06-25 | 2028-08-03 | 30
EHF-T3010 | Taking-over application, SAR review and handover - Hufuf | COM.EWR.EHF.TOA | Commissioning and handover | EHF | MS7 | 10% |  |  | 0.3 |  | 84855 |  | MS7 Final acceptance and handover 10% x station price share 4.56% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 131 |  | 2028-08-06 | 2028-08-17 | 10
NMJ-E1010 | Survey: submittal of site survey and as-found report - Al Majma'ah | ENG.NSR.NMJ.SRV.SUB | Engineering | NMJ | MS2 | 10% |  |  | 0.05 |  | 16995 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 34 |  | 2027-10-10 | 2027-10-21 | 10
NMJ-E1020 | Survey: SAR approval of survey report - Al Majma'ah | ENG.NSR.NMJ.SRV.APR | Engineering | NMJ | MS3 | 10% |  |  | 0.05 |  | 16995 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 17 |  | 2027-10-24 | 2027-10-28 | 5
NMJ-E1030 | Concept design: submittal - Al Majma'ah | ENG.NSR.NMJ.CNC.SUB | Engineering | NMJ | MS2 | 10% |  |  | 0.1 |  | 33989 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 10% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 16 |  | 2027-10-24 | 2027-10-28 | 5
NMJ-E1040 | Concept design: SAR review and approval - Al Majma'ah | ENG.NSR.NMJ.CNC.APR | Engineering | NMJ | MS3 | 10% |  |  | 0.1 |  | 33989 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 10% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 47 |  | 2027-10-31 | 2027-11-18 | 15
NMJ-E1050 | Preliminary design: submittal - Al Majma'ah | ENG.NSR.NMJ.PRE.SUB | Engineering | NMJ | MS2 | 10% |  |  | 0.2 |  | 67978 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 40 |  | 2027-10-31 | 2027-11-09 | 8
NMJ-E1060 | Preliminary design: SAR review and approval - Al Majma'ah | ENG.NSR.NMJ.PRE.APR | Engineering | NMJ | MS3 | 10% |  |  | 0.2 |  | 67978 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 74 |  | 2027-11-10 | 2027-11-30 | 15
NMJ-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Al Majma'ah | ENG.NSR.NMJ.DET.SUB | Engineering | NMJ | MS2 | 10% |  |  | 0.4 |  | 135957 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 40% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 84 |  | 2027-11-10 | 2027-11-25 | 12
NMJ-E1080 | Detailed design: SAR review and approval - Al Majma'ah | ENG.NSR.NMJ.DET.APR | Engineering | NMJ | MS3 | 10% |  |  | 0.4 |  | 135957 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 40% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 105 |  | 2027-11-28 | 2027-12-16 | 15
NMJ-E1090 | IFC and shop drawings: submittal - Al Majma'ah | ENG.NSR.NMJ.IFC.SUB | Engineering | NMJ | MS2 | 10% |  |  | 0.2 |  | 67978 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 28 |  | 2027-11-28 | 2027-12-02 | 5
NMJ-E1100 | IFC and shop drawings: SAR approval and release - Al Majma'ah | ENG.NSR.NMJ.IFC.APR | Engineering | NMJ | MS3 | 10% |  |  | 0.2 |  | 67978 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 85 |  | 2027-12-05 | 2027-12-23 | 15
NMJ-E1110 | HCIS Stage 3 and 4 documents: preparation - Al Majma'ah | ENG.NSR.NMJ.HCS.SUB | Engineering | NMJ | MS2 | 10% |  |  | 0.05 |  | 16995 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 17 |  | 2027-11-17 | 2027-12-02 | 12
NMJ-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Al Majma'ah | ENG.NSR.NMJ.HCS.APR | Engineering | NMJ | MS3 | 10% |  |  | 0.05 |  | 16995 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 21 |  | 2027-12-05 | 2027-12-23 | 15
NMJ-E1130 | As-built and O&M documentation: submittal - Al Majma'ah | ENG.NSR.NMJ.ASB.SUB | Engineering | NMJ | MS7 | 10% |  |  | 0.15 |  | 50984 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 42 |  | 2028-07-31 | 2028-09-10 | 30
NMJ-E1140 | As-built and O&M documentation: SAR review and approval - Al Majma'ah | ENG.NSR.NMJ.ASB.APR | Engineering | NMJ | MS7 | 10% |  |  | 0.05 |  | 16995 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 5% | Annex 3 documentation share | 21 |  | 2028-09-11 | 2028-10-01 | 15
NMJ-P1010 | Manufacture CCTV cameras and analytics - Al Majma'ah | PRO.NSR.NMJ.CCT | Procurement | NMJ | MS4 | 20% |  |  | 0.15324 |  | 104169 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 20.4% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 338,989) | 258 |  | 2027-12-26 | 2028-04-06 | 70
NMJ-P1020 | Manufacture video management servers, storage and video wall - Al Majma'ah | PRO.NSR.NMJ.VMS | Procurement | NMJ | MS4 | 20% |  |  | 0.16238 |  | 110385 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 21.7% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 359,215) | 273 |  | 2027-12-26 | 2028-04-06 | 70
NMJ-P1030 | Manufacture access control and intercom equipment - Al Majma'ah | PRO.NSR.NMJ.ACC | Procurement | NMJ | MS4 | 20% |  |  | 0.019928 |  | 13547 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 2.7% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 34 |  | 2027-12-26 | 2028-04-06 | 70
NMJ-P1040 | Manufacture UPS, network switches and field cabinets - Al Majma'ah | PRO.NSR.NMJ.UPN | Procurement | NMJ | MS4 | 20% |  |  | 0.41445 |  | 281736 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 55.3% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 916,830) | 698 |  | 2027-12-26 | 2028-04-06 | 70
NMJ-P1050 | Factory acceptance test at vendor premises - Al Majma'ah | PRO.NSR.NMJ.LOG | Procurement | NMJ | MS4 | 20% |  |  | 0.05 |  | 33989 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 211 |  | 2028-04-09 | 2028-04-20 | 10
NMJ-P1060 | Shipping and customs clearance - Al Majma'ah | PRO.NSR.NMJ.LOG | Procurement | NMJ | MS4 | 20% |  |  | 0.15 |  | 101967 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 421 |  | 2028-04-23 | 2028-06-01 | 25
NMJ-P1070 | Delivery to station and receiving inspection - Al Majma'ah | PRO.NSR.NMJ.LOG | Procurement | NMJ | MS4 | 20% |  |  | 0.05 |  | 33989 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 211 |  | 2028-06-04 | 2028-06-08 | 5
NMJ-C1010 | Civil: platform trenches and duct banks - Al Majma'ah | CON.NSR.NMJ.CIV | Construction | NMJ | MS5 | 20% |  |  | 0.17055 |  | 115940 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 55% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 745,743) | 421 |  | 2027-12-26 | 2028-03-22 | 59
NMJ-C1020 | Civil: camera and ALPR pole foundations and poles - Al Majma'ah | CON.NSR.NMJ.CIV | Construction | NMJ | MS5 | 20% |  |  | 0.13954 |  | 94860 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 45% (poles) | Annex 3 A6 Civil works (SAR 745,743) | 316 |  | 2028-02-16 | 2028-04-27 | 47
NMJ-C2010 | Install UPS, network switches and field cabinets - Al Majma'ah | CON.NSR.NMJ.INS | Construction | NMJ | MS5 | 20% |  |  | 0.13798 |  | 93797 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 20% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 158 |  | 2028-06-11 | 2028-06-25 | 11
NMJ-C2020 | Cabling and termination (power, fibre, data) - Al Majma'ah | CON.NSR.NMJ.INS | Construction | NMJ | MS5 | 20% |  |  | 0.20697 |  | 140695 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 30% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 316 |  | 2028-06-15 | 2028-07-10 | 18
NMJ-C2030 | Install and aim CCTV cameras - Al Majma'ah | CON.NSR.NMJ.INS | Construction | NMJ | MS5 | 20% |  |  | 0.17248 |  | 117246 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 25% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 263 |  | 2028-07-11 | 2028-07-30 | 14
NMJ-C2040 | Install video management, video wall and control-room equipment - Al Majma'ah | CON.NSR.NMJ.INS | Construction | NMJ | MS5 | 20% |  |  | 0.10349 |  | 70348 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 15% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 158 |  | 2028-06-26 | 2028-07-11 | 12
NMJ-C2050 | Install access control and intercom - Al Majma'ah | CON.NSR.NMJ.INS | Construction | NMJ | MS5 | 20% |  |  | 0.06899 |  | 46898 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 10% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 105 |  | 2028-07-02 | 2028-07-16 | 11
NMJ-T1010 | Pre-commissioning and loop checks - Al Majma'ah | COM.NSR.NMJ.TST | Commissioning and handover | NMJ | MS6 | 10% |  |  | 0.4 |  | 135957 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.48% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 158 |  | 2028-07-31 | 2028-08-07 | 6
NMJ-T1020 | Site acceptance test (SAT) and commissioning - Al Majma'ah | COM.NSR.NMJ.TST | Commissioning and handover | NMJ | MS6 | 10% |  |  | 0.6 |  | 203935 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.48% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 211 |  | 2028-08-08 | 2028-08-20 | 9
NMJ-T2010 | Operator and maintenance training - Al Majma'ah | COM.NSR.NMJ.TRN | Commissioning and handover | NMJ | MS7 | 10% |  |  | 0.15 |  | 50984 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 105 |  | 2028-08-21 | 2028-09-03 | 10
NMJ-T2020 | Trial operation (maximum 45 days) - Al Majma'ah | COM.NSR.NMJ.TOA | Commissioning and handover | NMJ | MS7 | 10% |  |  | 0.35 |  | 118962 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 158 |  | 2028-08-21 | 2028-10-01 | 30
NMJ-T3010 | Taking-over application, SAR review and handover - Al Majma'ah | COM.NSR.NMJ.TOA | Commissioning and handover | NMJ | MS7 | 10% |  |  | 0.3 |  | 101967 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 158 |  | 2028-10-02 | 2028-10-15 | 10
HMK-E1010 | Survey: submittal of site survey and as-found report - Makkah | ENG.HHR.HMK.SRV.SUB | Engineering | HMK | MS2 | 10% |  |  | 0.05 |  | 48550 |  | MS2 Engineering submittal 10% x station price share 15.66% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 115 |  | 2027-10-10 | 2027-11-04 | 20
HMK-E1020 | Survey: SAR approval of survey report - Makkah | ENG.HHR.HMK.SRV.APR | Engineering | HMK | MS3 | 10% |  |  | 0.05 |  | 48550 |  | MS3 SAR approval of engineering 10% x station price share 15.66% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 29 |  | 2027-11-07 | 2027-11-11 | 5
HMK-E1030 | Concept design: submittal - Makkah | ENG.HHR.HMK.CNC.SUB | Engineering | HMK | MS2 | 10% |  |  | 0.1 |  | 97101 |  | MS2 Engineering submittal 10% x station price share 15.66% ¦ Design stage key 10% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 63 |  | 2027-11-07 | 2027-11-16 | 8
HMK-E1040 | Concept design: SAR review and approval - Makkah | ENG.HHR.HMK.CNC.APR | Engineering | HMK | MS3 | 10% |  |  | 0.1 |  | 97101 |  | MS3 SAR approval of engineering 10% x station price share 15.66% ¦ Design stage key 10% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 118 |  | 2027-11-17 | 2027-12-07 | 15
HMK-E1050 | Preliminary design: submittal - Makkah | ENG.HHR.HMK.PRE.SUB | Engineering | HMK | MS2 | 10% |  |  | 0.2 |  | 194202 |  | MS2 Engineering submittal 10% x station price share 15.66% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 151 |  | 2027-11-17 | 2027-12-05 | 13
HMK-E1060 | Preliminary design: SAR review and approval - Makkah | ENG.HHR.HMK.PRE.APR | Engineering | HMK | MS3 | 10% |  |  | 0.2 |  | 194202 |  | MS3 SAR approval of engineering 10% x station price share 15.66% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 174 |  | 2027-12-06 | 2027-12-26 | 15
HMK-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Makkah | ENG.HHR.HMK.DET.SUB | Engineering | HMK | MS2 | 10% |  |  | 0.4 |  | 388404 |  | MS2 Engineering submittal 10% x station price share 15.66% ¦ Design stage key 40% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 309 |  | 2027-12-06 | 2028-01-02 | 20
HMK-E1080 | Detailed design: SAR review and approval - Makkah | ENG.HHR.HMK.DET.APR | Engineering | HMK | MS3 | 10% |  |  | 0.4 |  | 388404 |  | MS3 SAR approval of engineering 10% x station price share 15.66% ¦ Design stage key 40% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 232 |  | 2028-01-03 | 2028-01-23 | 15
HMK-E1090 | IFC and shop drawings: submittal - Makkah | ENG.HHR.HMK.IFC.SUB | Engineering | HMK | MS2 | 10% |  |  | 0.2 |  | 194202 |  | MS2 Engineering submittal 10% x station price share 15.66% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 122 |  | 2028-01-03 | 2028-01-13 | 9
HMK-E1100 | IFC and shop drawings: SAR approval and release - Makkah | ENG.HHR.HMK.IFC.APR | Engineering | HMK | MS3 | 10% |  |  | 0.2 |  | 194202 |  | MS3 SAR approval of engineering 10% x station price share 15.66% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 203 |  | 2028-01-16 | 2028-02-03 | 15
HMK-E1110 | HCIS Stage 3 and 4 documents: preparation - Makkah | ENG.HHR.HMK.HCS.SUB | Engineering | HMK | MS2 | 10% |  |  | 0.05 |  | 48550 |  | MS2 Engineering submittal 10% x station price share 15.66% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 63 |  | 2027-12-16 | 2028-01-13 | 21
HMK-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Makkah | ENG.HHR.HMK.HCS.APR | Engineering | HMK | MS3 | 10% |  |  | 0.05 |  | 48550 |  | MS3 SAR approval of engineering 10% x station price share 15.66% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 45 |  | 2028-01-16 | 2028-02-03 | 15
HMK-E1130 | As-built and O&M documentation: submittal - Makkah | ENG.HHR.HMK.ASB.SUB | Engineering | HMK | MS7 | 10% |  |  | 0.15 |  | 145651 |  | MS7 Final acceptance and handover 10% x station price share 15.66% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 131 |  | 2029-01-29 | 2029-04-02 | 40
HMK-E1140 | As-built and O&M documentation: SAR review and approval - Makkah | ENG.HHR.HMK.ASB.APR | Engineering | HMK | MS7 | 10% |  |  | 0.05 |  | 48550 |  | MS7 Final acceptance and handover 10% x station price share 15.66% ¦ Fixed key 5% | Annex 3 documentation share | 49 |  | 2029-04-03 | 2029-04-30 | 15
HMK-P1010 | Manufacture CCTV cameras and analytics - Makkah | PRO.HHR.HMK.CCT | Procurement | HMK | MS4 | 20% |  |  | 0.24396 |  | 473780 |  | MS4 Material delivery 20% x station price share 15.66% ¦ BOQ section share 32.5% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 1,650,175) | 1174 |  | 2028-02-06 | 2028-06-22 | 90
HMK-P1020 | Manufacture video management servers, storage and video wall - Makkah | PRO.HHR.HMK.VMS | Procurement | HMK | MS4 | 20% |  |  | 0.081643 |  | 158552 |  | MS4 Material delivery 20% x station price share 15.66% ¦ BOQ section share 10.9% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 552,237) | 393 |  | 2028-02-06 | 2028-06-22 | 90
HMK-P1030 | Manufacture access control and intercom equipment - Makkah | PRO.HHR.HMK.ACC | Procurement | HMK | MS4 | 20% |  |  | 0.0065175 |  | 12657 |  | MS4 Material delivery 20% x station price share 15.66% ¦ BOQ section share 0.9% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 31 |  | 2028-02-06 | 2028-06-22 | 90
HMK-P1040 | Manufacture UPS, network switches and field cabinets - Makkah | PRO.HHR.HMK.UPN | Procurement | HMK | MS4 | 20% |  |  | 0.41788 |  | 811525 |  | MS4 Material delivery 20% x station price share 15.66% ¦ BOQ section share 55.7% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 2,826,539) | 2011 |  | 2028-02-06 | 2028-06-22 | 90
HMK-P1050 | Factory acceptance test at vendor premises - Makkah | PRO.HHR.HMK.LOG | Procurement | HMK | MS4 | 20% |  |  | 0.05 |  | 97101 |  | MS4 Material delivery 20% x station price share 15.66% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 601 |  | 2028-06-25 | 2028-07-06 | 10
HMK-P1060 | Shipping and customs clearance - Makkah | PRO.HHR.HMK.LOG | Procurement | HMK | MS4 | 20% |  |  | 0.15 |  | 291303 |  | MS4 Material delivery 20% x station price share 15.66% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 1204 |  | 2028-07-09 | 2028-08-24 | 35
HMK-P1070 | Delivery to station and receiving inspection - Makkah | PRO.HHR.HMK.LOG | Procurement | HMK | MS4 | 20% |  |  | 0.05 |  | 97101 |  | MS4 Material delivery 20% x station price share 15.66% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 601 |  | 2028-08-27 | 2028-08-31 | 5
HMK-C1010 | Civil: platform trenches and duct banks - Makkah | CON.HHR.HMK.CIV | Construction | HMK | MS5 | 20% |  |  | 0.055699 |  | 108168 |  | MS5 Installation 20% x station price share 15.66% ¦ BOQ civil share 10.1% x 55% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 571,639) | 1204 |  | 2028-02-06 | 2028-04-19 | 49
HMK-C1020 | Civil: camera and ALPR pole foundations and poles - Makkah | CON.HHR.HMK.CIV | Construction | HMK | MS5 | 20% |  |  | 0.045572 |  | 88501 |  | MS5 Installation 20% x station price share 15.66% ¦ BOQ civil share 10.1% x 45% (poles) | Annex 3 A6 Civil works (SAR 571,639) | 902 |  | 2028-03-28 | 2028-05-28 | 39
HMK-C2010 | Install UPS, network switches and field cabinets - Makkah | CON.HHR.HMK.INS | Construction | HMK | MS5 | 20% |  |  | 0.17975 |  | 349070 |  | MS5 Installation 20% x station price share 15.66% ¦ Installation key 20% x (1 - civil share 10.1%) | Annex 3 equipment sections A1-A5 (installation share) | 451 |  | 2028-09-03 | 2028-10-16 | 32
HMK-C2020 | Cabling and termination (power, fibre, data) - Makkah | CON.HHR.HMK.INS | Construction | HMK | MS5 | 20% |  |  | 0.26962 |  | 523605 |  | MS5 Installation 20% x station price share 15.66% ¦ Installation key 30% x (1 - civil share 10.1%) | Annex 3 equipment sections A1-A5 (installation share) | 902 |  | 2028-09-18 | 2028-11-29 | 53
HMK-C2030 | Install and aim CCTV cameras - Makkah | CON.HHR.HMK.INS | Construction | HMK | MS5 | 20% |  |  | 0.22468 |  | 436337 |  | MS5 Installation 20% x station price share 15.66% ¦ Installation key 25% x (1 - civil share 10.1%) | Annex 3 equipment sections A1-A5 (installation share) | 752 |  | 2028-11-30 | 2029-01-28 | 42
HMK-C2040 | Install video management, video wall and control-room equipment - Makkah | CON.HHR.HMK.INS | Construction | HMK | MS5 | 20% |  |  | 0.13481 |  | 261802 |  | MS5 Installation 20% x station price share 15.66% ¦ Installation key 15% x (1 - civil share 10.1%) | Annex 3 equipment sections A1-A5 (installation share) | 451 |  | 2028-10-17 | 2028-12-06 | 37
HMK-C2050 | Install access control and intercom - Makkah | CON.HHR.HMK.INS | Construction | HMK | MS5 | 20% |  |  | 0.089873 |  | 174535 |  | MS5 Installation 20% x station price share 15.66% ¦ Installation key 10% x (1 - civil share 10.1%) | Annex 3 equipment sections A1-A5 (installation share) | 301 |  | 2028-11-01 | 2028-12-14 | 32
HMK-T1010 | Pre-commissioning and loop checks - Makkah | COM.HHR.HMK.TST | Commissioning and handover | HMK | MS6 | 10% |  |  | 0.4 |  | 388404 |  | MS6 Testing and commissioning (SAT) 10% x station price share 15.66% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 451 |  | 2029-01-29 | 2029-02-18 | 10
HMK-T1020 | Site acceptance test (SAT) and commissioning - Makkah | COM.HHR.HMK.TST | Commissioning and handover | HMK | MS6 | 10% |  |  | 0.6 |  | 582606 |  | MS6 Testing and commissioning (SAT) 10% x station price share 15.66% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 601 |  | 2029-02-19 | 2029-03-12 | 15
HMK-T2010 | Operator and maintenance training - Makkah | COM.HHR.HMK.TRN | Commissioning and handover | HMK | MS7 | 10% |  |  | 0.15 |  | 145651 |  | MS7 Final acceptance and handover 10% x station price share 15.66% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 301 |  | 2029-03-13 | 2029-03-26 | 10
HMK-T2020 | Trial operation (maximum 45 days) - Makkah | COM.HHR.HMK.TOA | Commissioning and handover | HMK | MS7 | 10% |  |  | 0.35 |  | 339853 |  | MS7 Final acceptance and handover 10% x station price share 15.66% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 451 |  | 2029-03-13 | 2029-04-30 | 30
HMK-T3010 | Taking-over application, SAR review and handover - Makkah | COM.HHR.HMK.TOA | Commissioning and handover | HMK | MS7 | 10% |  |  | 0.3 |  | 291303 |  | MS7 Final acceptance and handover 10% x station price share 15.66% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 451 |  | 2029-05-01 | 2029-05-21 | 15
HKA-E1010 | Survey: submittal of site survey and as-found report - KAEC | ENG.HHR.HKA.SRV.SUB | Engineering | HKA | MS2 | 10% |  |  | 0.05 |  | 27822 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 66 |  | 2028-02-09 | 2028-03-14 | 20
HKA-E1020 | Survey: SAR approval of survey report - KAEC | ENG.HHR.HKA.SRV.APR | Engineering | HKA | MS3 | 10% |  |  | 0.05 |  | 27822 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 17 |  | 2028-03-15 | 2028-03-21 | 5
HKA-E1030 | Concept design: submittal - KAEC | ENG.HHR.HKA.CNC.SUB | Engineering | HKA | MS2 | 10% |  |  | 0.1 |  | 55644 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 10% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 36 |  | 2028-03-15 | 2028-03-26 | 8
HKA-E1040 | Concept design: SAR review and approval - KAEC | ENG.HHR.HKA.CNC.APR | Engineering | HKA | MS3 | 10% |  |  | 0.1 |  | 55644 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 10% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 67 |  | 2028-03-27 | 2028-04-16 | 15
HKA-E1050 | Preliminary design: submittal - KAEC | ENG.HHR.HKA.PRE.SUB | Engineering | HKA | MS2 | 10% |  |  | 0.2 |  | 111288 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 86 |  | 2028-03-27 | 2028-04-12 | 13
HKA-E1060 | Preliminary design: SAR review and approval - KAEC | ENG.HHR.HKA.PRE.APR | Engineering | HKA | MS3 | 10% |  |  | 0.2 |  | 111288 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 100 |  | 2028-04-13 | 2028-05-10 | 15
HKA-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - KAEC | ENG.HHR.HKA.DET.SUB | Engineering | HKA | MS2 | 10% |  |  | 0.4 |  | 222575 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 40% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 177 |  | 2028-04-13 | 2028-05-17 | 20
HKA-E1080 | Detailed design: SAR review and approval - KAEC | ENG.HHR.HKA.DET.APR | Engineering | HKA | MS3 | 10% |  |  | 0.4 |  | 222575 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 40% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 133 |  | 2028-05-18 | 2028-06-07 | 15
HKA-E1090 | IFC and shop drawings: submittal - KAEC | ENG.HHR.HKA.IFC.SUB | Engineering | HKA | MS2 | 10% |  |  | 0.2 |  | 111288 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 70 |  | 2028-05-18 | 2028-05-30 | 9
HKA-E1100 | IFC and shop drawings: SAR approval and release - KAEC | ENG.HHR.HKA.IFC.APR | Engineering | HKA | MS3 | 10% |  |  | 0.2 |  | 111288 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 116 |  | 2028-05-31 | 2028-06-20 | 15
HKA-E1110 | HCIS Stage 3 and 4 documents: preparation - KAEC | ENG.HHR.HKA.HCS.SUB | Engineering | HKA | MS2 | 10% |  |  | 0.05 |  | 27822 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 36 |  | 2028-04-25 | 2028-05-30 | 21
HKA-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - KAEC | ENG.HHR.HKA.HCS.APR | Engineering | HKA | MS3 | 10% |  |  | 0.05 |  | 27822 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 26 |  | 2028-05-31 | 2028-06-20 | 15
HKA-E1130 | As-built and O&M documentation: submittal - KAEC | ENG.HHR.HKA.ASB.SUB | Engineering | HKA | MS7 | 10% |  |  | 0.15 |  | 83466 |  | MS7 Final acceptance and handover 10% x station price share 8.97% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 75 |  | 2029-04-15 | 2029-06-14 | 40
HKA-E1140 | As-built and O&M documentation: SAR review and approval - KAEC | ENG.HHR.HKA.ASB.APR | Engineering | HKA | MS7 | 10% |  |  | 0.05 |  | 27822 |  | MS7 Final acceptance and handover 10% x station price share 8.97% ¦ Fixed key 5% | Annex 3 documentation share | 28 |  | 2029-06-17 | 2029-07-05 | 15
HKA-P1010 | Manufacture CCTV cameras and analytics - KAEC | PRO.HHR.HKA.CCT | Procurement | HKA | MS4 | 20% |  |  | 0.23675 |  | 263474 |  | MS4 Material delivery 20% x station price share 8.97% ¦ BOQ section share 31.6% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 962,039) | 653 |  | 2028-06-21 | 2028-10-24 | 90
HKA-P1020 | Manufacture video management servers, storage and video wall - KAEC | PRO.HHR.HKA.VMS | Procurement | HKA | MS4 | 20% |  |  | 0.1 |  | 111291 |  | MS4 Material delivery 20% x station price share 8.97% ¦ BOQ section share 13.3% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 406,364) | 276 |  | 2028-06-21 | 2028-10-24 | 90
HKA-P1030 | Manufacture access control and intercom equipment - KAEC | PRO.HHR.HKA.ACC | Procurement | HKA | MS4 | 20% |  |  | 0.010849 |  | 12074 |  | MS4 Material delivery 20% x station price share 8.97% ¦ BOQ section share 1.4% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 30 |  | 2028-06-21 | 2028-10-24 | 90
HKA-P1040 | Manufacture UPS, network switches and field cabinets - KAEC | PRO.HHR.HKA.UPN | Procurement | HKA | MS4 | 20% |  |  | 0.4024 |  | 447818 |  | MS4 Material delivery 20% x station price share 8.97% ¦ BOQ section share 53.7% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 1,635,145) | 1109 |  | 2028-06-21 | 2028-10-24 | 90
HKA-P1050 | Factory acceptance test at vendor premises - KAEC | PRO.HHR.HKA.LOG | Procurement | HKA | MS4 | 20% |  |  | 0.05 |  | 55644 |  | MS4 Material delivery 20% x station price share 8.97% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 345 |  | 2028-10-25 | 2028-11-07 | 10
HKA-P1060 | Shipping and customs clearance - KAEC | PRO.HHR.HKA.LOG | Procurement | HKA | MS4 | 20% |  |  | 0.15 |  | 166931 |  | MS4 Material delivery 20% x station price share 8.97% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 689 |  | 2028-11-08 | 2028-12-26 | 35
HKA-P1070 | Delivery to station and receiving inspection - KAEC | PRO.HHR.HKA.LOG | Procurement | HKA | MS4 | 20% |  |  | 0.05 |  | 55644 |  | MS4 Material delivery 20% x station price share 8.97% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 345 |  | 2028-12-27 | 2029-01-02 | 5
HKA-C1010 | Civil: platform trenches and duct banks - KAEC | CON.HHR.HKA.CIV | Construction | HKA | MS5 | 20% |  |  | 0.031805 |  | 35395 |  | MS5 Installation 20% x station price share 8.97% ¦ BOQ civil share 5.8% x 55% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 187,054) | 689 |  | 2028-06-21 | 2028-08-02 | 31
HKA-C1020 | Civil: camera and ALPR pole foundations and poles - KAEC | CON.HHR.HKA.CIV | Construction | HKA | MS5 | 20% |  |  | 0.026022 |  | 28960 |  | MS5 Installation 20% x station price share 8.97% ¦ BOQ civil share 5.8% x 45% (poles) | Annex 3 A6 Civil works (SAR 187,054) | 517 |  | 2028-07-19 | 2028-08-22 | 25
HKA-C2010 | Install UPS, network switches and field cabinets - KAEC | CON.HHR.HKA.INS | Construction | HKA | MS5 | 20% |  |  | 0.18843 |  | 209704 |  | MS5 Installation 20% x station price share 8.97% ¦ Installation key 20% x (1 - civil share 5.8%) | Annex 3 equipment sections A1-A5 (installation share) | 258 |  | 2029-01-03 | 2029-01-30 | 20
HKA-C2020 | Cabling and termination (power, fibre, data) - KAEC | CON.HHR.HKA.INS | Construction | HKA | MS5 | 20% |  |  | 0.28265 |  | 314556 |  | MS5 Installation 20% x station price share 8.97% ¦ Installation key 30% x (1 - civil share 5.8%) | Annex 3 equipment sections A1-A5 (installation share) | 517 |  | 2029-01-14 | 2029-03-07 | 33
HKA-C2030 | Install and aim CCTV cameras - KAEC | CON.HHR.HKA.INS | Construction | HKA | MS5 | 20% |  |  | 0.23554 |  | 262130 |  | MS5 Installation 20% x station price share 8.97% ¦ Installation key 25% x (1 - civil share 5.8%) | Annex 3 equipment sections A1-A5 (installation share) | 431 |  | 2029-03-08 | 2029-04-12 | 26
HKA-C2040 | Install video management, video wall and control-room equipment - KAEC | CON.HHR.HKA.INS | Construction | HKA | MS5 | 20% |  |  | 0.14133 |  | 157278 |  | MS5 Installation 20% x station price share 8.97% ¦ Installation key 15% x (1 - civil share 5.8%) | Annex 3 equipment sections A1-A5 (installation share) | 258 |  | 2029-01-31 | 2029-03-12 | 23
HKA-C2050 | Install access control and intercom - KAEC | CON.HHR.HKA.INS | Construction | HKA | MS5 | 20% |  |  | 0.094217 |  | 104852 |  | MS5 Installation 20% x station price share 8.97% ¦ Installation key 10% x (1 - civil share 5.8%) | Annex 3 equipment sections A1-A5 (installation share) | 172 |  | 2029-02-18 | 2029-03-18 | 20
HKA-T1010 | Pre-commissioning and loop checks - KAEC | COM.HHR.HKA.TST | Commissioning and handover | HKA | MS6 | 10% |  |  | 0.4 |  | 222575 |  | MS6 Testing and commissioning (SAT) 10% x station price share 8.97% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 258 |  | 2029-04-15 | 2029-05-03 | 10
HKA-T1020 | Site acceptance test (SAT) and commissioning - KAEC | COM.HHR.HKA.TST | Commissioning and handover | HKA | MS6 | 10% |  |  | 0.6 |  | 333863 |  | MS6 Testing and commissioning (SAT) 10% x station price share 8.97% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 345 |  | 2029-05-06 | 2029-05-24 | 15
HKA-T2010 | Operator and maintenance training - KAEC | COM.HHR.HKA.TRN | Commissioning and handover | HKA | MS7 | 10% |  |  | 0.15 |  | 83466 |  | MS7 Final acceptance and handover 10% x station price share 8.97% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 172 |  | 2029-05-27 | 2029-06-07 | 10
HKA-T2020 | Trial operation (maximum 45 days) - KAEC | COM.HHR.HKA.TOA | Commissioning and handover | HKA | MS7 | 10% |  |  | 0.35 |  | 194753 |  | MS7 Final acceptance and handover 10% x station price share 8.97% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 258 |  | 2029-05-27 | 2029-07-05 | 30
HKA-T3010 | Taking-over application, SAR review and handover - KAEC | COM.HHR.HKA.TOA | Commissioning and handover | HKA | MS7 | 10% |  |  | 0.3 |  | 166931 |  | MS7 Final acceptance and handover 10% x station price share 8.97% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 258 |  | 2029-07-08 | 2029-07-26 | 15
HMD-E1010 | Survey: submittal of site survey and as-found report - Madinah | ENG.HHR.HMD.SRV.SUB | Engineering | HMD | MS2 | 10% |  |  | 0.05 |  | 27811 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 66 |  | 2028-02-09 | 2028-03-14 | 20
HMD-E1020 | Survey: SAR approval of survey report - Madinah | ENG.HHR.HMD.SRV.APR | Engineering | HMD | MS3 | 10% |  |  | 0.05 |  | 27811 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 17 |  | 2028-03-15 | 2028-03-21 | 5
HMD-E1030 | Concept design: submittal - Madinah | ENG.HHR.HMD.CNC.SUB | Engineering | HMD | MS2 | 10% |  |  | 0.1 |  | 55621 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 10% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 36 |  | 2028-03-15 | 2028-03-26 | 8
HMD-E1040 | Concept design: SAR review and approval - Madinah | ENG.HHR.HMD.CNC.APR | Engineering | HMD | MS3 | 10% |  |  | 0.1 |  | 55621 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 10% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 67 |  | 2028-03-27 | 2028-04-16 | 15
HMD-E1050 | Preliminary design: submittal - Madinah | ENG.HHR.HMD.PRE.SUB | Engineering | HMD | MS2 | 10% |  |  | 0.2 |  | 111243 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 86 |  | 2028-03-27 | 2028-04-12 | 13
HMD-E1060 | Preliminary design: SAR review and approval - Madinah | ENG.HHR.HMD.PRE.APR | Engineering | HMD | MS3 | 10% |  |  | 0.2 |  | 111243 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 100 |  | 2028-04-13 | 2028-05-10 | 15
HMD-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Madinah | ENG.HHR.HMD.DET.SUB | Engineering | HMD | MS2 | 10% |  |  | 0.4 |  | 222485 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 40% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 177 |  | 2028-04-13 | 2028-05-17 | 20
HMD-E1080 | Detailed design: SAR review and approval - Madinah | ENG.HHR.HMD.DET.APR | Engineering | HMD | MS3 | 10% |  |  | 0.4 |  | 222485 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 40% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 133 |  | 2028-05-18 | 2028-06-07 | 15
HMD-E1090 | IFC and shop drawings: submittal - Madinah | ENG.HHR.HMD.IFC.SUB | Engineering | HMD | MS2 | 10% |  |  | 0.2 |  | 111243 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 70 |  | 2028-05-18 | 2028-05-30 | 9
HMD-E1100 | IFC and shop drawings: SAR approval and release - Madinah | ENG.HHR.HMD.IFC.APR | Engineering | HMD | MS3 | 10% |  |  | 0.2 |  | 111243 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 116 |  | 2028-05-31 | 2028-06-20 | 15
HMD-E1110 | HCIS Stage 3 and 4 documents: preparation - Madinah | ENG.HHR.HMD.HCS.SUB | Engineering | HMD | MS2 | 10% |  |  | 0.05 |  | 27811 |  | MS2 Engineering submittal 10% x station price share 8.97% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 36 |  | 2028-04-25 | 2028-05-30 | 21
HMD-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Madinah | ENG.HHR.HMD.HCS.APR | Engineering | HMD | MS3 | 10% |  |  | 0.05 |  | 27811 |  | MS3 SAR approval of engineering 10% x station price share 8.97% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 26 |  | 2028-05-31 | 2028-06-20 | 15
HMD-E1130 | As-built and O&M documentation: submittal - Madinah | ENG.HHR.HMD.ASB.SUB | Engineering | HMD | MS7 | 10% |  |  | 0.15 |  | 83432 |  | MS7 Final acceptance and handover 10% x station price share 8.97% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 75 |  | 2029-04-19 | 2029-06-20 | 40
HMD-E1140 | As-built and O&M documentation: SAR review and approval - Madinah | ENG.HHR.HMD.ASB.APR | Engineering | HMD | MS7 | 10% |  |  | 0.05 |  | 27811 |  | MS7 Final acceptance and handover 10% x station price share 8.97% ¦ Fixed key 5% | Annex 3 documentation share | 28 |  | 2029-06-21 | 2029-07-11 | 15
HMD-P1010 | Manufacture CCTV cameras and analytics - Madinah | PRO.HHR.HMD.CCT | Procurement | HMD | MS4 | 20% |  |  | 0.23816 |  | 264932 |  | MS4 Material delivery 20% x station price share 8.97% ¦ BOQ section share 31.8% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 934,319) | 656 |  | 2028-06-21 | 2028-10-24 | 90
HMD-P1020 | Manufacture video management servers, storage and video wall - Madinah | PRO.HHR.HMD.VMS | Procurement | HMD | MS4 | 20% |  |  | 0.1043 |  | 116027 |  | MS4 Material delivery 20% x station price share 8.97% ¦ BOQ section share 13.9% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 409,184) | 287 |  | 2028-06-21 | 2028-10-24 | 90
HMD-P1030 | Manufacture access control and intercom equipment - Madinah | PRO.HHR.HMD.ACC | Procurement | HMD | MS4 | 20% |  |  | 0.011237 |  | 12501 |  | MS4 Material delivery 20% x station price share 8.97% ¦ BOQ section share 1.5% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 31 |  | 2028-06-21 | 2028-10-24 | 90
HMD-P1040 | Manufacture UPS, network switches and field cabinets - Madinah | PRO.HHR.HMD.UPN | Procurement | HMD | MS4 | 20% |  |  | 0.39631 |  | 440861 |  | MS4 Material delivery 20% x station price share 8.97% ¦ BOQ section share 52.8% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 1,554,756) | 1092 |  | 2028-06-21 | 2028-10-24 | 90
HMD-P1050 | Factory acceptance test at vendor premises - Madinah | PRO.HHR.HMD.LOG | Procurement | HMD | MS4 | 20% |  |  | 0.05 |  | 55621 |  | MS4 Material delivery 20% x station price share 8.97% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 344 |  | 2028-10-25 | 2028-11-07 | 10
HMD-P1060 | Shipping and customs clearance - Madinah | PRO.HHR.HMD.LOG | Procurement | HMD | MS4 | 20% |  |  | 0.15 |  | 166864 |  | MS4 Material delivery 20% x station price share 8.97% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 689 |  | 2028-11-08 | 2028-12-26 | 35
HMD-P1070 | Delivery to station and receiving inspection - Madinah | PRO.HHR.HMD.LOG | Procurement | HMD | MS4 | 20% |  |  | 0.05 |  | 55621 |  | MS4 Material delivery 20% x station price share 8.97% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 344 |  | 2028-12-27 | 2029-01-02 | 5
HMD-C1010 | Civil: platform trenches and duct banks - Madinah | CON.HHR.HMD.CIV | Construction | HMD | MS5 | 20% |  |  | 0.049505 |  | 55071 |  | MS5 Installation 20% x station price share 8.97% ¦ BOQ civil share 9.0% x 55% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 291,036) | 689 |  | 2028-06-21 | 2028-08-08 | 35
HMD-C1020 | Civil: camera and ALPR pole foundations and poles - Madinah | CON.HHR.HMD.CIV | Construction | HMD | MS5 | 20% |  |  | 0.040504 |  | 45058 |  | MS5 Installation 20% x station price share 8.97% ¦ BOQ civil share 9.0% x 45% (poles) | Annex 3 A6 Civil works (SAR 291,036) | 517 |  | 2028-07-24 | 2028-08-30 | 28
HMD-C2010 | Install UPS, network switches and field cabinets - Madinah | CON.HHR.HMD.INS | Construction | HMD | MS5 | 20% |  |  | 0.182 |  | 202459 |  | MS5 Installation 20% x station price share 8.97% ¦ Installation key 20% x (1 - civil share 9.0%) | Annex 3 equipment sections A1-A5 (installation share) | 258 |  | 2029-01-03 | 2029-01-31 | 21
HMD-C2020 | Cabling and termination (power, fibre, data) - Madinah | CON.HHR.HMD.INS | Construction | HMD | MS5 | 20% |  |  | 0.273 |  | 303689 |  | MS5 Installation 20% x station price share 8.97% ¦ Installation key 30% x (1 - civil share 9.0%) | Annex 3 equipment sections A1-A5 (installation share) | 517 |  | 2029-01-14 | 2029-03-11 | 35
HMD-C2030 | Install and aim CCTV cameras - Madinah | CON.HHR.HMD.INS | Construction | HMD | MS5 | 20% |  |  | 0.2275 |  | 253074 |  | MS5 Installation 20% x station price share 8.97% ¦ Installation key 25% x (1 - civil share 9.0%) | Annex 3 equipment sections A1-A5 (installation share) | 431 |  | 2029-03-12 | 2029-04-18 | 28
HMD-C2040 | Install video management, video wall and control-room equipment - Madinah | CON.HHR.HMD.INS | Construction | HMD | MS5 | 20% |  |  | 0.1365 |  | 151845 |  | MS5 Installation 20% x station price share 8.97% ¦ Installation key 15% x (1 - civil share 9.0%) | Annex 3 equipment sections A1-A5 (installation share) | 258 |  | 2029-02-01 | 2029-03-15 | 25
HMD-C2050 | Install access control and intercom - Madinah | CON.HHR.HMD.INS | Construction | HMD | MS5 | 20% |  |  | 0.090999 |  | 101230 |  | MS5 Installation 20% x station price share 8.97% ¦ Installation key 10% x (1 - civil share 9.0%) | Annex 3 equipment sections A1-A5 (installation share) | 172 |  | 2029-02-19 | 2029-03-20 | 21
HMD-T1010 | Pre-commissioning and loop checks - Madinah | COM.HHR.HMD.TST | Commissioning and handover | HMD | MS6 | 10% |  |  | 0.4 |  | 222485 |  | MS6 Testing and commissioning (SAT) 10% x station price share 8.97% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 258 |  | 2029-04-19 | 2029-05-09 | 10
HMD-T1020 | Site acceptance test (SAT) and commissioning - Madinah | COM.HHR.HMD.TST | Commissioning and handover | HMD | MS6 | 10% |  |  | 0.6 |  | 333728 |  | MS6 Testing and commissioning (SAT) 10% x station price share 8.97% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 344 |  | 2029-05-10 | 2029-05-30 | 15
HMD-T2010 | Operator and maintenance training - Madinah | COM.HHR.HMD.TRN | Commissioning and handover | HMD | MS7 | 10% |  |  | 0.15 |  | 83432 |  | MS7 Final acceptance and handover 10% x station price share 8.97% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 172 |  | 2029-05-31 | 2029-06-13 | 10
HMD-T2020 | Trial operation (maximum 45 days) - Madinah | COM.HHR.HMD.TOA | Commissioning and handover | HMD | MS7 | 10% |  |  | 0.35 |  | 194675 |  | MS7 Final acceptance and handover 10% x station price share 8.97% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 258 |  | 2029-05-31 | 2029-07-11 | 30
HMD-T3010 | Taking-over application, SAR review and handover - Madinah | COM.HHR.HMD.TOA | Commissioning and handover | HMD | MS7 | 10% |  |  | 0.3 |  | 166864 |  | MS7 Final acceptance and handover 10% x station price share 8.97% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 258 |  | 2029-07-12 | 2029-08-01 | 15
EAB-E1010 | Survey: submittal of site survey and as-found report - Abqaiq | ENG.EWR.EAB.SRV.SUB | Engineering | EAB | MS2 | 10% |  |  | 0.05 |  | 10028 |  | MS2 Engineering submittal 10% x station price share 3.23% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 20 |  | 2028-04-05 | 2028-04-18 | 10
EAB-E1020 | Survey: SAR approval of survey report - Abqaiq | ENG.EWR.EAB.SRV.APR | Engineering | EAB | MS3 | 10% |  |  | 0.05 |  | 10028 |  | MS3 SAR approval of engineering 10% x station price share 3.23% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 10 |  | 2028-04-19 | 2028-04-25 | 5
EAB-E1030 | Concept design: submittal - Abqaiq | ENG.EWR.EAB.CNC.SUB | Engineering | EAB | MS2 | 10% |  |  | 0.1 |  | 20057 |  | MS2 Engineering submittal 10% x station price share 3.23% ¦ Design stage key 10% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 9 |  | 2028-04-19 | 2028-04-25 | 5
EAB-E1040 | Concept design: SAR review and approval - Abqaiq | ENG.EWR.EAB.CNC.APR | Engineering | EAB | MS3 | 10% |  |  | 0.1 |  | 20057 |  | MS3 SAR approval of engineering 10% x station price share 3.23% ¦ Design stage key 10% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 28 |  | 2028-04-26 | 2028-05-23 | 15
EAB-E1050 | Preliminary design: submittal - Abqaiq | ENG.EWR.EAB.PRE.SUB | Engineering | EAB | MS2 | 10% |  |  | 0.2 |  | 40114 |  | MS2 Engineering submittal 10% x station price share 3.23% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 23 |  | 2028-04-26 | 2028-05-14 | 8
EAB-E1060 | Preliminary design: SAR review and approval - Abqaiq | ENG.EWR.EAB.PRE.APR | Engineering | EAB | MS3 | 10% |  |  | 0.2 |  | 40114 |  | MS3 SAR approval of engineering 10% x station price share 3.23% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 44 |  | 2028-05-15 | 2028-06-04 | 15
EAB-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Abqaiq | ENG.EWR.EAB.DET.SUB | Engineering | EAB | MS2 | 10% |  |  | 0.4 |  | 80227 |  | MS2 Engineering submittal 10% x station price share 3.23% ¦ Design stage key 40% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 50 |  | 2028-05-15 | 2028-05-30 | 12
EAB-E1080 | Detailed design: SAR review and approval - Abqaiq | ENG.EWR.EAB.DET.APR | Engineering | EAB | MS3 | 10% |  |  | 0.4 |  | 80227 |  | MS3 SAR approval of engineering 10% x station price share 3.23% ¦ Design stage key 40% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 62 |  | 2028-05-31 | 2028-06-20 | 15
EAB-E1090 | IFC and shop drawings: submittal - Abqaiq | ENG.EWR.EAB.IFC.SUB | Engineering | EAB | MS2 | 10% |  |  | 0.2 |  | 40114 |  | MS2 Engineering submittal 10% x station price share 3.23% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 17 |  | 2028-05-31 | 2028-06-06 | 5
EAB-E1100 | IFC and shop drawings: SAR approval and release - Abqaiq | ENG.EWR.EAB.IFC.APR | Engineering | EAB | MS3 | 10% |  |  | 0.2 |  | 40114 |  | MS3 SAR approval of engineering 10% x station price share 3.23% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 50 |  | 2028-06-07 | 2028-06-27 | 15
EAB-E1110 | HCIS Stage 3 and 4 documents: preparation - Abqaiq | ENG.EWR.EAB.HCS.SUB | Engineering | EAB | MS2 | 10% |  |  | 0.05 |  | 10028 |  | MS2 Engineering submittal 10% x station price share 3.23% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 10 |  | 2028-05-22 | 2028-06-06 | 12
EAB-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Abqaiq | ENG.EWR.EAB.HCS.APR | Engineering | EAB | MS3 | 10% |  |  | 0.05 |  | 10028 |  | MS3 SAR approval of engineering 10% x station price share 3.23% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 12 |  | 2028-06-07 | 2028-06-27 | 15
EAB-E1130 | As-built and O&M documentation: submittal - Abqaiq | ENG.EWR.EAB.ASB.SUB | Engineering | EAB | MS7 | 10% |  |  | 0.15 |  | 30085 |  | MS7 Final acceptance and handover 10% x station price share 3.23% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 25 |  | 2029-01-04 | 2029-02-21 | 30
EAB-E1140 | As-built and O&M documentation: SAR review and approval - Abqaiq | ENG.EWR.EAB.ASB.APR | Engineering | EAB | MS7 | 10% |  |  | 0.05 |  | 10028 |  | MS7 Final acceptance and handover 10% x station price share 3.23% ¦ Fixed key 5% | Annex 3 documentation share | 12 |  | 2029-02-25 | 2029-03-15 | 15
EAB-P1010 | Manufacture CCTV cameras and analytics - Abqaiq | PRO.EWR.EAB.CCT | Procurement | EAB | MS4 | 20% |  |  | 0.092232 |  | 36997 |  | MS4 Material delivery 20% x station price share 3.23% ¦ BOQ section share 12.3% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 111,083) | 92 |  | 2028-06-28 | 2028-10-03 | 70
EAB-P1020 | Manufacture video management servers, storage and video wall - Abqaiq | PRO.EWR.EAB.VMS | Procurement | EAB | MS4 | 20% |  |  | 0.23749 |  | 95266 |  | MS4 Material delivery 20% x station price share 3.23% ¦ BOQ section share 31.7% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 286,032) | 236 |  | 2028-06-28 | 2028-10-03 | 70
EAB-P1030 | Manufacture access control and intercom equipment - Abqaiq | PRO.EWR.EAB.ACC | Procurement | EAB | MS4 | 20% |  |  | 0.036604 |  | 14683 |  | MS4 Material delivery 20% x station price share 3.23% ¦ BOQ section share 4.9% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 36 |  | 2028-06-28 | 2028-10-03 | 70
EAB-P1040 | Manufacture UPS, network switches and field cabinets - Abqaiq | PRO.EWR.EAB.UPN | Procurement | EAB | MS4 | 20% |  |  | 0.38367 |  | 153905 |  | MS4 Material delivery 20% x station price share 3.23% ¦ BOQ section share 51.2% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 462,093) | 381 |  | 2028-06-28 | 2028-10-03 | 70
EAB-P1050 | Factory acceptance test at vendor premises - Abqaiq | PRO.EWR.EAB.LOG | Procurement | EAB | MS4 | 20% |  |  | 0.05 |  | 20057 |  | MS4 Material delivery 20% x station price share 3.23% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 124 |  | 2028-10-04 | 2028-10-17 | 10
EAB-P1060 | Shipping and customs clearance - Abqaiq | PRO.EWR.EAB.LOG | Procurement | EAB | MS4 | 20% |  |  | 0.15 |  | 60170 |  | MS4 Material delivery 20% x station price share 3.23% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 248 |  | 2028-10-18 | 2028-11-21 | 25
EAB-P1070 | Delivery to station and receiving inspection - Abqaiq | PRO.EWR.EAB.LOG | Procurement | EAB | MS4 | 20% |  |  | 0.05 |  | 20057 |  | MS4 Material delivery 20% x station price share 3.23% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 124 |  | 2028-11-22 | 2028-11-28 | 5
EAB-C1010 | Civil: platform trenches and duct banks - Abqaiq | CON.EWR.EAB.CIV | Construction | EAB | MS5 | 20% |  |  | 0.16163 |  | 64837 |  | MS5 Installation 20% x station price share 3.23% ¦ BOQ civil share 29.4% x 55% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 375,936) | 248 |  | 2028-06-28 | 2028-08-21 | 39
EAB-C1020 | Civil: camera and ALPR pole foundations and poles - Abqaiq | CON.EWR.EAB.CIV | Construction | EAB | MS5 | 20% |  |  | 0.13224 |  | 53048 |  | MS5 Installation 20% x station price share 3.23% ¦ BOQ civil share 29.4% x 45% (poles) | Annex 3 A6 Civil works (SAR 375,936) | 186 |  | 2028-08-02 | 2028-09-12 | 30
EAB-C2010 | Install UPS, network switches and field cabinets - Abqaiq | CON.EWR.EAB.INS | Construction | EAB | MS5 | 20% |  |  | 0.14122 |  | 56650 |  | MS5 Installation 20% x station price share 3.23% ¦ Installation key 20% x (1 - civil share 29.4%) | Annex 3 equipment sections A1-A5 (installation share) | 93 |  | 2028-11-29 | 2028-12-10 | 8
EAB-C2020 | Cabling and termination (power, fibre, data) - Abqaiq | CON.EWR.EAB.INS | Construction | EAB | MS5 | 20% |  |  | 0.21184 |  | 84975 |  | MS5 Installation 20% x station price share 3.23% ¦ Installation key 30% x (1 - civil share 29.4%) | Annex 3 equipment sections A1-A5 (installation share) | 186 |  | 2028-12-04 | 2028-12-20 | 13
EAB-C2030 | Install and aim CCTV cameras - Abqaiq | CON.EWR.EAB.INS | Construction | EAB | MS5 | 20% |  |  | 0.17653 |  | 70813 |  | MS5 Installation 20% x station price share 3.23% ¦ Installation key 25% x (1 - civil share 29.4%) | Annex 3 equipment sections A1-A5 (installation share) | 155 |  | 2028-12-21 | 2029-01-03 | 10
EAB-C2040 | Install video management, video wall and control-room equipment - Abqaiq | CON.EWR.EAB.INS | Construction | EAB | MS5 | 20% |  |  | 0.10592 |  | 42488 |  | MS5 Installation 20% x station price share 3.23% ¦ Installation key 15% x (1 - civil share 29.4%) | Annex 3 equipment sections A1-A5 (installation share) | 93 |  | 2028-12-11 | 2028-12-21 | 9
EAB-C2050 | Install access control and intercom - Abqaiq | CON.EWR.EAB.INS | Construction | EAB | MS5 | 20% |  |  | 0.070612 |  | 28325 |  | MS5 Installation 20% x station price share 3.23% ¦ Installation key 10% x (1 - civil share 29.4%) | Annex 3 equipment sections A1-A5 (installation share) | 62 |  | 2028-12-14 | 2028-12-25 | 8
EAB-T1010 | Pre-commissioning and loop checks - Abqaiq | COM.EWR.EAB.TST | Commissioning and handover | EAB | MS6 | 10% |  |  | 0.4 |  | 80227 |  | MS6 Testing and commissioning (SAT) 10% x station price share 3.23% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 93 |  | 2029-01-04 | 2029-01-11 | 6
EAB-T1020 | Site acceptance test (SAT) and commissioning - Abqaiq | COM.EWR.EAB.TST | Commissioning and handover | EAB | MS6 | 10% |  |  | 0.6 |  | 120341 |  | MS6 Testing and commissioning (SAT) 10% x station price share 3.23% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 124 |  | 2029-01-14 | 2029-01-24 | 9
EAB-T2010 | Operator and maintenance training - Abqaiq | COM.EWR.EAB.TRN | Commissioning and handover | EAB | MS7 | 10% |  |  | 0.15 |  | 30085 |  | MS7 Final acceptance and handover 10% x station price share 3.23% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 62 |  | 2029-01-25 | 2029-02-07 | 10
EAB-T2020 | Trial operation (maximum 45 days) - Abqaiq | COM.EWR.EAB.TOA | Commissioning and handover | EAB | MS7 | 10% |  |  | 0.35 |  | 70199 |  | MS7 Final acceptance and handover 10% x station price share 3.23% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 93 |  | 2029-01-25 | 2029-03-15 | 30
EAB-T3010 | Taking-over application, SAR review and handover - Abqaiq | COM.EWR.EAB.TOA | Commissioning and handover | EAB | MS7 | 10% |  |  | 0.3 |  | 60170 |  | MS7 Final acceptance and handover 10% x station price share 3.23% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 93 |  | 2029-03-18 | 2029-03-29 | 10
NHL-E1010 | Survey: submittal of site survey and as-found report - Hail | ENG.NSR.NHL.SRV.SUB | Engineering | NHL | MS2 | 10% |  |  | 0.05 |  | 16995 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 34 |  | 2028-05-08 | 2028-05-21 | 10
NHL-E1020 | Survey: SAR approval of survey report - Hail | ENG.NSR.NHL.SRV.APR | Engineering | NHL | MS3 | 10% |  |  | 0.05 |  | 16995 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 17 |  | 2028-05-22 | 2028-05-28 | 5
NHL-E1030 | Concept design: submittal - Hail | ENG.NSR.NHL.CNC.SUB | Engineering | NHL | MS2 | 10% |  |  | 0.1 |  | 33989 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 10% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 16 |  | 2028-05-22 | 2028-05-28 | 5
NHL-E1040 | Concept design: SAR review and approval - Hail | ENG.NSR.NHL.CNC.APR | Engineering | NHL | MS3 | 10% |  |  | 0.1 |  | 33989 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 10% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 47 |  | 2028-05-29 | 2028-06-18 | 15
NHL-E1050 | Preliminary design: submittal - Hail | ENG.NSR.NHL.PRE.SUB | Engineering | NHL | MS2 | 10% |  |  | 0.2 |  | 67978 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 40 |  | 2028-05-29 | 2028-06-07 | 8
NHL-E1060 | Preliminary design: SAR review and approval - Hail | ENG.NSR.NHL.PRE.APR | Engineering | NHL | MS3 | 10% |  |  | 0.2 |  | 67978 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 74 |  | 2028-06-08 | 2028-06-28 | 15
NHL-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Hail | ENG.NSR.NHL.DET.SUB | Engineering | NHL | MS2 | 10% |  |  | 0.4 |  | 135957 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 40% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 84 |  | 2028-06-08 | 2028-06-25 | 12
NHL-E1080 | Detailed design: SAR review and approval - Hail | ENG.NSR.NHL.DET.APR | Engineering | NHL | MS3 | 10% |  |  | 0.4 |  | 135957 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 40% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 105 |  | 2028-06-26 | 2028-07-16 | 15
NHL-E1090 | IFC and shop drawings: submittal - Hail | ENG.NSR.NHL.IFC.SUB | Engineering | NHL | MS2 | 10% |  |  | 0.2 |  | 67978 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 28 |  | 2028-06-26 | 2028-07-02 | 5
NHL-E1100 | IFC and shop drawings: SAR approval and release - Hail | ENG.NSR.NHL.IFC.APR | Engineering | NHL | MS3 | 10% |  |  | 0.2 |  | 67978 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 85 |  | 2028-07-03 | 2028-07-23 | 15
NHL-E1110 | HCIS Stage 3 and 4 documents: preparation - Hail | ENG.NSR.NHL.HCS.SUB | Engineering | NHL | MS2 | 10% |  |  | 0.05 |  | 16995 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 17 |  | 2028-06-15 | 2028-07-02 | 12
NHL-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Hail | ENG.NSR.NHL.HCS.APR | Engineering | NHL | MS3 | 10% |  |  | 0.05 |  | 16995 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 21 |  | 2028-07-03 | 2028-07-23 | 15
NHL-E1130 | As-built and O&M documentation: submittal - Hail | ENG.NSR.NHL.ASB.SUB | Engineering | NHL | MS7 | 10% |  |  | 0.15 |  | 50984 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 42 |  | 2029-02-20 | 2029-04-03 | 30
NHL-E1140 | As-built and O&M documentation: SAR review and approval - Hail | ENG.NSR.NHL.ASB.APR | Engineering | NHL | MS7 | 10% |  |  | 0.05 |  | 16995 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 5% | Annex 3 documentation share | 21 |  | 2029-04-04 | 2029-05-01 | 15
NHL-P1010 | Manufacture CCTV cameras and analytics - Hail | PRO.NSR.NHL.CCT | Procurement | NHL | MS4 | 20% |  |  | 0.15324 |  | 104169 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 20.4% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 338,989) | 258 |  | 2028-07-24 | 2028-10-29 | 70
NHL-P1020 | Manufacture video management servers, storage and video wall - Hail | PRO.NSR.NHL.VMS | Procurement | NHL | MS4 | 20% |  |  | 0.16238 |  | 110385 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 21.7% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 359,215) | 273 |  | 2028-07-24 | 2028-10-29 | 70
NHL-P1030 | Manufacture access control and intercom equipment - Hail | PRO.NSR.NHL.ACC | Procurement | NHL | MS4 | 20% |  |  | 0.019928 |  | 13547 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 2.7% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 34 |  | 2028-07-24 | 2028-10-29 | 70
NHL-P1040 | Manufacture UPS, network switches and field cabinets - Hail | PRO.NSR.NHL.UPN | Procurement | NHL | MS4 | 20% |  |  | 0.41445 |  | 281736 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 55.3% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 916,830) | 698 |  | 2028-07-24 | 2028-10-29 | 70
NHL-P1050 | Factory acceptance test at vendor premises - Hail | PRO.NSR.NHL.LOG | Procurement | NHL | MS4 | 20% |  |  | 0.05 |  | 33989 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 211 |  | 2028-10-30 | 2028-11-12 | 10
NHL-P1060 | Shipping and customs clearance - Hail | PRO.NSR.NHL.LOG | Procurement | NHL | MS4 | 20% |  |  | 0.15 |  | 101967 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 421 |  | 2028-11-13 | 2028-12-17 | 25
NHL-P1070 | Delivery to station and receiving inspection - Hail | PRO.NSR.NHL.LOG | Procurement | NHL | MS4 | 20% |  |  | 0.05 |  | 33989 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 211 |  | 2028-12-18 | 2028-12-24 | 5
NHL-C1010 | Civil: platform trenches and duct banks - Hail | CON.NSR.NHL.CIV | Construction | NHL | MS5 | 20% |  |  | 0.17055 |  | 115940 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 55% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 745,743) | 421 |  | 2028-07-24 | 2028-10-12 | 59
NHL-C1020 | Civil: camera and ALPR pole foundations and poles - Hail | CON.NSR.NHL.CIV | Construction | NHL | MS5 | 20% |  |  | 0.13954 |  | 94860 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 45% (poles) | Annex 3 A6 Civil works (SAR 745,743) | 316 |  | 2028-09-14 | 2028-11-19 | 47
NHL-C2010 | Install UPS, network switches and field cabinets - Hail | CON.NSR.NHL.INS | Construction | NHL | MS5 | 20% |  |  | 0.13798 |  | 93797 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 20% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 158 |  | 2028-12-25 | 2029-01-08 | 11
NHL-C2020 | Cabling and termination (power, fibre, data) - Hail | CON.NSR.NHL.INS | Construction | NHL | MS5 | 20% |  |  | 0.20697 |  | 140695 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 30% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 316 |  | 2028-12-31 | 2029-01-23 | 18
NHL-C2030 | Install and aim CCTV cameras - Hail | CON.NSR.NHL.INS | Construction | NHL | MS5 | 20% |  |  | 0.17248 |  | 117246 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 25% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 263 |  | 2029-01-24 | 2029-02-19 | 14
NHL-C2040 | Install video management, video wall and control-room equipment - Hail | CON.NSR.NHL.INS | Construction | NHL | MS5 | 20% |  |  | 0.10349 |  | 70348 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 15% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 158 |  | 2029-01-09 | 2029-01-24 | 12
NHL-C2050 | Install access control and intercom - Hail | CON.NSR.NHL.INS | Construction | NHL | MS5 | 20% |  |  | 0.06899 |  | 46898 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 10% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 105 |  | 2029-01-15 | 2029-01-29 | 11
NHL-T1010 | Pre-commissioning and loop checks - Hail | COM.NSR.NHL.TST | Commissioning and handover | NHL | MS6 | 10% |  |  | 0.4 |  | 135957 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.48% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 158 |  | 2029-02-20 | 2029-02-28 | 6
NHL-T1020 | Site acceptance test (SAT) and commissioning - Hail | COM.NSR.NHL.TST | Commissioning and handover | NHL | MS6 | 10% |  |  | 0.6 |  | 203935 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.48% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 211 |  | 2029-03-01 | 2029-03-13 | 9
NHL-T2010 | Operator and maintenance training - Hail | COM.NSR.NHL.TRN | Commissioning and handover | NHL | MS7 | 10% |  |  | 0.15 |  | 50984 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 105 |  | 2029-03-14 | 2029-03-27 | 10
NHL-T2020 | Trial operation (maximum 45 days) - Hail | COM.NSR.NHL.TOA | Commissioning and handover | NHL | MS7 | 10% |  |  | 0.35 |  | 118962 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 158 |  | 2029-03-14 | 2029-05-01 | 30
NHL-T3010 | Taking-over application, SAR review and handover - Hail | COM.NSR.NHL.TOA | Commissioning and handover | NHL | MS7 | 10% |  |  | 0.3 |  | 101967 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 158 |  | 2029-05-02 | 2029-05-15 | 10
NJF-E1010 | Survey: submittal of site survey and as-found report - Al Jouf | ENG.NSR.NJF.SRV.SUB | Engineering | NJF | MS2 | 10% |  |  | 0.05 |  | 17114 |  | MS2 Engineering submittal 10% x station price share 5.52% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 34 |  | 2028-07-20 | 2028-08-02 | 10
NJF-E1020 | Survey: SAR approval of survey report - Al Jouf | ENG.NSR.NJF.SRV.APR | Engineering | NJF | MS3 | 10% |  |  | 0.05 |  | 17114 |  | MS3 SAR approval of engineering 10% x station price share 5.52% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 17 |  | 2028-08-03 | 2028-08-09 | 5
NJF-E1030 | Concept design: submittal - Al Jouf | ENG.NSR.NJF.CNC.SUB | Engineering | NJF | MS2 | 10% |  |  | 0.1 |  | 34228 |  | MS2 Engineering submittal 10% x station price share 5.52% ¦ Design stage key 10% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 16 |  | 2028-08-03 | 2028-08-09 | 5
NJF-E1040 | Concept design: SAR review and approval - Al Jouf | ENG.NSR.NJF.CNC.APR | Engineering | NJF | MS3 | 10% |  |  | 0.1 |  | 34228 |  | MS3 SAR approval of engineering 10% x station price share 5.52% ¦ Design stage key 10% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 48 |  | 2028-08-10 | 2028-08-30 | 15
NJF-E1050 | Preliminary design: submittal - Al Jouf | ENG.NSR.NJF.PRE.SUB | Engineering | NJF | MS2 | 10% |  |  | 0.2 |  | 68457 |  | MS2 Engineering submittal 10% x station price share 5.52% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 40 |  | 2028-08-10 | 2028-08-21 | 8
NJF-E1060 | Preliminary design: SAR review and approval - Al Jouf | ENG.NSR.NJF.PRE.APR | Engineering | NJF | MS3 | 10% |  |  | 0.2 |  | 68457 |  | MS3 SAR approval of engineering 10% x station price share 5.52% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 75 |  | 2028-08-22 | 2028-09-11 | 15
NJF-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Al Jouf | ENG.NSR.NJF.DET.SUB | Engineering | NJF | MS2 | 10% |  |  | 0.4 |  | 136914 |  | MS2 Engineering submittal 10% x station price share 5.52% ¦ Design stage key 40% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 85 |  | 2028-08-22 | 2028-09-06 | 12
NJF-E1080 | Detailed design: SAR review and approval - Al Jouf | ENG.NSR.NJF.DET.APR | Engineering | NJF | MS3 | 10% |  |  | 0.4 |  | 136914 |  | MS3 SAR approval of engineering 10% x station price share 5.52% ¦ Design stage key 40% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 106 |  | 2028-09-07 | 2028-09-27 | 15
NJF-E1090 | IFC and shop drawings: submittal - Al Jouf | ENG.NSR.NJF.IFC.SUB | Engineering | NJF | MS2 | 10% |  |  | 0.2 |  | 68457 |  | MS2 Engineering submittal 10% x station price share 5.52% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 29 |  | 2028-09-07 | 2028-09-13 | 5
NJF-E1100 | IFC and shop drawings: SAR approval and release - Al Jouf | ENG.NSR.NJF.IFC.APR | Engineering | NJF | MS3 | 10% |  |  | 0.2 |  | 68457 |  | MS3 SAR approval of engineering 10% x station price share 5.52% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 86 |  | 2028-09-14 | 2028-10-04 | 15
NJF-E1110 | HCIS Stage 3 and 4 documents: preparation - Al Jouf | ENG.NSR.NJF.HCS.SUB | Engineering | NJF | MS2 | 10% |  |  | 0.05 |  | 17114 |  | MS2 Engineering submittal 10% x station price share 5.52% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 17 |  | 2028-08-29 | 2028-09-13 | 12
NJF-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Al Jouf | ENG.NSR.NJF.HCS.APR | Engineering | NJF | MS3 | 10% |  |  | 0.05 |  | 17114 |  | MS3 SAR approval of engineering 10% x station price share 5.52% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 21 |  | 2028-09-14 | 2028-10-04 | 15
NJF-E1130 | As-built and O&M documentation: submittal - Al Jouf | ENG.NSR.NJF.ASB.SUB | Engineering | NJF | MS7 | 10% |  |  | 0.15 |  | 51343 |  | MS7 Final acceptance and handover 10% x station price share 5.52% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 42 |  | 2029-05-14 | 2029-06-24 | 30
NJF-E1140 | As-built and O&M documentation: SAR review and approval - Al Jouf | ENG.NSR.NJF.ASB.APR | Engineering | NJF | MS7 | 10% |  |  | 0.05 |  | 17114 |  | MS7 Final acceptance and handover 10% x station price share 5.52% ¦ Fixed key 5% | Annex 3 documentation share | 21 |  | 2029-06-25 | 2029-07-15 | 15
NJF-P1010 | Manufacture CCTV cameras and analytics - Al Jouf | PRO.NSR.NJF.CCT | Procurement | NJF | MS4 | 20% |  |  | 0.15169 |  | 103843 |  | MS4 Material delivery 20% x station price share 5.52% ¦ BOQ section share 20.2% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 338,989) | 257 |  | 2028-10-05 | 2029-01-10 | 70
NJF-P1020 | Manufacture video management servers, storage and video wall - Al Jouf | PRO.NSR.NJF.VMS | Procurement | NJF | MS4 | 20% |  |  | 0.16074 |  | 110039 |  | MS4 Material delivery 20% x station price share 5.52% ¦ BOQ section share 21.4% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 359,215) | 273 |  | 2028-10-05 | 2029-01-10 | 70
NJF-P1030 | Manufacture access control and intercom equipment - Al Jouf | PRO.NSR.NJF.ACC | Procurement | NJF | MS4 | 20% |  |  | 0.019727 |  | 13505 |  | MS4 Material delivery 20% x station price share 5.52% ¦ BOQ section share 2.6% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 33 |  | 2028-10-05 | 2029-01-10 | 70
NJF-P1040 | Manufacture UPS, network switches and field cabinets - Al Jouf | PRO.NSR.NJF.UPN | Procurement | NJF | MS4 | 20% |  |  | 0.41784 |  | 286040 |  | MS4 Material delivery 20% x station price share 5.52% ¦ BOQ section share 55.7% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 933,761) | 709 |  | 2028-10-05 | 2029-01-10 | 70
NJF-P1050 | Factory acceptance test at vendor premises - Al Jouf | PRO.NSR.NJF.LOG | Procurement | NJF | MS4 | 20% |  |  | 0.05 |  | 34228 |  | MS4 Material delivery 20% x station price share 5.52% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 212 |  | 2029-01-11 | 2029-01-24 | 10
NJF-P1060 | Shipping and customs clearance - Al Jouf | PRO.NSR.NJF.LOG | Procurement | NJF | MS4 | 20% |  |  | 0.15 |  | 102685 |  | MS4 Material delivery 20% x station price share 5.52% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 424 |  | 2029-01-25 | 2029-03-08 | 25
NJF-P1070 | Delivery to station and receiving inspection - Al Jouf | PRO.NSR.NJF.LOG | Procurement | NJF | MS4 | 20% |  |  | 0.05 |  | 34228 |  | MS4 Material delivery 20% x station price share 5.52% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 212 |  | 2029-03-11 | 2029-03-15 | 5
NJF-C1010 | Civil: platform trenches and duct banks - Al Jouf | CON.NSR.NJF.CIV | Construction | NJF | MS5 | 20% |  |  | 0.16936 |  | 115940 |  | MS5 Installation 20% x station price share 5.52% ¦ BOQ civil share 30.8% x 55% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 745,743) | 424 |  | 2028-10-05 | 2028-12-26 | 59
NJF-C1020 | Civil: camera and ALPR pole foundations and poles - Al Jouf | CON.NSR.NJF.CIV | Construction | NJF | MS5 | 20% |  |  | 0.13857 |  | 94860 |  | MS5 Installation 20% x station price share 5.52% ¦ BOQ civil share 30.8% x 45% (poles) | Annex 3 A6 Civil works (SAR 745,743) | 318 |  | 2028-11-28 | 2029-01-31 | 47
NJF-C2010 | Install UPS, network switches and field cabinets - Al Jouf | CON.NSR.NJF.INS | Construction | NJF | MS5 | 20% |  |  | 0.13841 |  | 94754 |  | MS5 Installation 20% x station price share 5.52% ¦ Installation key 20% x (1 - civil share 30.8%) | Annex 3 equipment sections A1-A5 (installation share) | 159 |  | 2029-03-18 | 2029-04-01 | 11
NJF-C2020 | Cabling and termination (power, fibre, data) - Al Jouf | CON.NSR.NJF.INS | Construction | NJF | MS5 | 20% |  |  | 0.20762 |  | 142131 |  | MS5 Installation 20% x station price share 5.52% ¦ Installation key 30% x (1 - civil share 30.8%) | Annex 3 equipment sections A1-A5 (installation share) | 318 |  | 2029-03-22 | 2029-04-16 | 18
NJF-C2030 | Install and aim CCTV cameras - Al Jouf | CON.NSR.NJF.INS | Construction | NJF | MS5 | 20% |  |  | 0.17302 |  | 118442 |  | MS5 Installation 20% x station price share 5.52% ¦ Installation key 25% x (1 - civil share 30.8%) | Annex 3 equipment sections A1-A5 (installation share) | 265 |  | 2029-04-17 | 2029-05-13 | 14
NJF-C2040 | Install video management, video wall and control-room equipment - Al Jouf | CON.NSR.NJF.INS | Construction | NJF | MS5 | 20% |  |  | 0.10381 |  | 71065 |  | MS5 Installation 20% x station price share 5.52% ¦ Installation key 15% x (1 - civil share 30.8%) | Annex 3 equipment sections A1-A5 (installation share) | 159 |  | 2029-04-02 | 2029-04-17 | 12
NJF-C2050 | Install access control and intercom - Al Jouf | CON.NSR.NJF.INS | Construction | NJF | MS5 | 20% |  |  | 0.069207 |  | 47377 |  | MS5 Installation 20% x station price share 5.52% ¦ Installation key 10% x (1 - civil share 30.8%) | Annex 3 equipment sections A1-A5 (installation share) | 106 |  | 2029-04-08 | 2029-04-29 | 11
NJF-T1010 | Pre-commissioning and loop checks - Al Jouf | COM.NSR.NJF.TST | Commissioning and handover | NJF | MS6 | 10% |  |  | 0.4 |  | 136914 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.52% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 159 |  | 2029-05-14 | 2029-05-21 | 6
NJF-T1020 | Site acceptance test (SAT) and commissioning - Al Jouf | COM.NSR.NJF.TST | Commissioning and handover | NJF | MS6 | 10% |  |  | 0.6 |  | 205371 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.52% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 212 |  | 2029-05-22 | 2029-06-03 | 9
NJF-T2010 | Operator and maintenance training - Al Jouf | COM.NSR.NJF.TRN | Commissioning and handover | NJF | MS7 | 10% |  |  | 0.15 |  | 51343 |  | MS7 Final acceptance and handover 10% x station price share 5.52% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 106 |  | 2029-06-04 | 2029-06-17 | 10
NJF-T2020 | Trial operation (maximum 45 days) - Al Jouf | COM.NSR.NJF.TOA | Commissioning and handover | NJF | MS7 | 10% |  |  | 0.35 |  | 119800 |  | MS7 Final acceptance and handover 10% x station price share 5.52% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 159 |  | 2029-06-04 | 2029-07-15 | 30
NJF-T3010 | Taking-over application, SAR review and handover - Al Jouf | COM.NSR.NJF.TOA | Commissioning and handover | NJF | MS7 | 10% |  |  | 0.3 |  | 102685 |  | MS7 Final acceptance and handover 10% x station price share 5.52% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 159 |  | 2029-07-16 | 2029-07-29 | 10
NQR-E1010 | Survey: submittal of site survey and as-found report - Al Qurayyat | ENG.NSR.NQR.SRV.SUB | Engineering | NQR | MS2 | 10% |  |  | 0.05 |  | 16995 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 34 |  | 2028-09-07 | 2028-09-20 | 10
NQR-E1020 | Survey: SAR approval of survey report - Al Qurayyat | ENG.NSR.NQR.SRV.APR | Engineering | NQR | MS3 | 10% |  |  | 0.05 |  | 16995 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 17 |  | 2028-09-21 | 2028-09-27 | 5
NQR-E1030 | Concept design: submittal - Al Qurayyat | ENG.NSR.NQR.CNC.SUB | Engineering | NQR | MS2 | 10% |  |  | 0.1 |  | 33989 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 10% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 16 |  | 2028-09-21 | 2028-09-27 | 5
NQR-E1040 | Concept design: SAR review and approval - Al Qurayyat | ENG.NSR.NQR.CNC.APR | Engineering | NQR | MS3 | 10% |  |  | 0.1 |  | 33989 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 10% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 47 |  | 2028-09-28 | 2028-10-18 | 15
NQR-E1050 | Preliminary design: submittal - Al Qurayyat | ENG.NSR.NQR.PRE.SUB | Engineering | NQR | MS2 | 10% |  |  | 0.2 |  | 67978 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 40 |  | 2028-09-28 | 2028-10-09 | 8
NQR-E1060 | Preliminary design: SAR review and approval - Al Qurayyat | ENG.NSR.NQR.PRE.APR | Engineering | NQR | MS3 | 10% |  |  | 0.2 |  | 67978 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 74 |  | 2028-10-10 | 2028-10-30 | 15
NQR-E1070 | Detailed design: submittal (drawings, BOQ, data sheets) - Al Qurayyat | ENG.NSR.NQR.DET.SUB | Engineering | NQR | MS2 | 10% |  |  | 0.4 |  | 135957 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 40% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 84 |  | 2028-10-10 | 2028-10-25 | 12
NQR-E1080 | Detailed design: SAR review and approval - Al Qurayyat | ENG.NSR.NQR.DET.APR | Engineering | NQR | MS3 | 10% |  |  | 0.4 |  | 135957 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 40% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 105 |  | 2028-10-26 | 2028-11-15 | 15
NQR-E1090 | IFC and shop drawings: submittal - Al Qurayyat | ENG.NSR.NQR.IFC.SUB | Engineering | NQR | MS2 | 10% |  |  | 0.2 |  | 67978 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 20% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 28 |  | 2028-10-26 | 2028-11-01 | 5
NQR-E1100 | IFC and shop drawings: SAR approval and release - Al Qurayyat | ENG.NSR.NQR.IFC.APR | Engineering | NQR | MS3 | 10% |  |  | 0.2 |  | 67978 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 20% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 85 |  | 2028-11-02 | 2028-11-22 | 15
NQR-E1110 | HCIS Stage 3 and 4 documents: preparation - Al Qurayyat | ENG.NSR.NQR.HCS.SUB | Engineering | NQR | MS2 | 10% |  |  | 0.05 |  | 16995 |  | MS2 Engineering submittal 10% x station price share 5.48% ¦ Design stage key 5% of the engineering-submittal milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 17 |  | 2028-10-17 | 2028-11-01 | 12
NQR-E1120 | HCIS Stage 3 and 4 documents: SAR final review and HCIS submission - Al Qurayyat | ENG.NSR.NQR.HCS.APR | Engineering | NQR | MS3 | 10% |  |  | 0.05 |  | 16995 |  | MS3 SAR approval of engineering 10% x station price share 5.48% ¦ Design stage key 5% of the SAR-approval milestone | Annex 3 Design and engineering package (railway) allocated by station hardware share | 21 |  | 2028-11-02 | 2028-11-22 | 15
NQR-E1130 | As-built and O&M documentation: submittal - Al Qurayyat | ENG.NSR.NQR.ASB.SUB | Engineering | NQR | MS7 | 10% |  |  | 0.15 |  | 50984 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 15% of final-acceptance milestone | Annex 3 documentation and training share | 42 |  | 2029-07-02 | 2029-08-12 | 30
NQR-E1140 | As-built and O&M documentation: SAR review and approval - Al Qurayyat | ENG.NSR.NQR.ASB.APR | Engineering | NQR | MS7 | 10% |  |  | 0.05 |  | 16995 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 5% | Annex 3 documentation share | 21 |  | 2029-08-13 | 2029-09-02 | 15
NQR-P1010 | Manufacture CCTV cameras and analytics - Al Qurayyat | PRO.NSR.NQR.CCT | Procurement | NQR | MS4 | 20% |  |  | 0.15324 |  | 104169 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 20.4% of station equipment x 75% (manufacture) | Annex 3 A1 CCTV system (SAR 338,989) | 258 |  | 2028-11-23 | 2029-03-08 | 70
NQR-P1020 | Manufacture video management servers, storage and video wall - Al Qurayyat | PRO.NSR.NQR.VMS | Procurement | NQR | MS4 | 20% |  |  | 0.16238 |  | 110385 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 21.7% of station equipment x 75% (manufacture) | Annex 3 A2 Video management and wall (SAR 359,215) | 273 |  | 2028-11-23 | 2029-03-08 | 70
NQR-P1030 | Manufacture access control and intercom equipment - Al Qurayyat | PRO.NSR.NQR.ACC | Procurement | NQR | MS4 | 20% |  |  | 0.019928 |  | 13547 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 2.7% of station equipment x 75% (manufacture) | Annex 3 A3 Access control and intercom (SAR 44,085) | 34 |  | 2028-11-23 | 2029-03-08 | 70
NQR-P1040 | Manufacture UPS, network switches and field cabinets - Al Qurayyat | PRO.NSR.NQR.UPN | Procurement | NQR | MS4 | 20% |  |  | 0.41445 |  | 281736 |  | MS4 Material delivery 20% x station price share 5.48% ¦ BOQ section share 55.3% of station equipment x 75% (manufacture) | Annex 3 A4 UPS + A5 poles, cabinets and network (SAR 916,830) | 698 |  | 2028-11-23 | 2029-03-08 | 70
NQR-P1050 | Factory acceptance test at vendor premises - Al Qurayyat | PRO.NSR.NQR.LOG | Procurement | NQR | MS4 | 20% |  |  | 0.05 |  | 33989 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 5% (FAT) | Annex 3 Factory acceptance test (railway), allocated by hardware share | 211 |  | 2029-03-11 | 2029-03-22 | 10
NQR-P1060 | Shipping and customs clearance - Al Qurayyat | PRO.NSR.NQR.LOG | Procurement | NQR | MS4 | 20% |  |  | 0.15 |  | 101967 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 15% (shipping and customs) | Annex 3 equipment sections A1-A5 (logistics share) | 421 |  | 2029-03-25 | 2029-05-03 | 25
NQR-P1070 | Delivery to station and receiving inspection - Al Qurayyat | PRO.NSR.NQR.LOG | Procurement | NQR | MS4 | 20% |  |  | 0.05 |  | 33989 |  | MS4 Material delivery 20% x station price share 5.48% ¦ Fixed key 5% (delivery, receiving) incl. commissioning spares | Annex 3 Commissioning spares (railway), allocated by hardware share | 211 |  | 2029-05-06 | 2029-05-10 | 5
NQR-C1010 | Civil: platform trenches and duct banks - Al Qurayyat | CON.NSR.NQR.CIV | Construction | NQR | MS5 | 20% |  |  | 0.17055 |  | 115940 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 55% (trenches and duct banks) | Annex 3 A6 Civil works (SAR 745,743) | 421 |  | 2028-11-23 | 2029-02-20 | 59
NQR-C1020 | Civil: camera and ALPR pole foundations and poles - Al Qurayyat | CON.NSR.NQR.CIV | Construction | NQR | MS5 | 20% |  |  | 0.13954 |  | 94860 |  | MS5 Installation 20% x station price share 5.48% ¦ BOQ civil share 31.0% x 45% (poles) | Annex 3 A6 Civil works (SAR 745,743) | 316 |  | 2029-01-16 | 2029-03-29 | 47
NQR-C2010 | Install UPS, network switches and field cabinets - Al Qurayyat | CON.NSR.NQR.INS | Construction | NQR | MS5 | 20% |  |  | 0.13798 |  | 93797 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 20% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 158 |  | 2029-05-13 | 2029-05-27 | 11
NQR-C2020 | Cabling and termination (power, fibre, data) - Al Qurayyat | CON.NSR.NQR.INS | Construction | NQR | MS5 | 20% |  |  | 0.20697 |  | 140695 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 30% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 316 |  | 2029-05-17 | 2029-06-11 | 18
NQR-C2030 | Install and aim CCTV cameras - Al Qurayyat | CON.NSR.NQR.INS | Construction | NQR | MS5 | 20% |  |  | 0.17248 |  | 117246 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 25% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 263 |  | 2029-06-12 | 2029-07-01 | 14
NQR-C2040 | Install video management, video wall and control-room equipment - Al Qurayyat | CON.NSR.NQR.INS | Construction | NQR | MS5 | 20% |  |  | 0.10349 |  | 70348 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 15% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 158 |  | 2029-05-28 | 2029-06-12 | 12
NQR-C2050 | Install access control and intercom - Al Qurayyat | CON.NSR.NQR.INS | Construction | NQR | MS5 | 20% |  |  | 0.06899 |  | 46898 |  | MS5 Installation 20% x station price share 5.48% ¦ Installation key 10% x (1 - civil share 31.0%) | Annex 3 equipment sections A1-A5 (installation share) | 105 |  | 2029-06-03 | 2029-06-17 | 11
NQR-T1010 | Pre-commissioning and loop checks - Al Qurayyat | COM.NSR.NQR.TST | Commissioning and handover | NQR | MS6 | 10% |  |  | 0.4 |  | 135957 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.48% ¦ Fixed key 40% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 158 |  | 2029-07-02 | 2029-07-09 | 6
NQR-T1020 | Site acceptance test (SAT) and commissioning - Al Qurayyat | COM.NSR.NQR.TST | Commissioning and handover | NQR | MS6 | 10% |  |  | 0.6 |  | 203935 |  | MS6 Testing and commissioning (SAT) 10% x station price share 5.48% ¦ Fixed key 60% of SAT milestone | Annex 3 equipment sections A1-A5 (testing share) | 211 |  | 2029-07-10 | 2029-07-22 | 9
NQR-T2010 | Operator and maintenance training - Al Qurayyat | COM.NSR.NQR.TRN | Commissioning and handover | NQR | MS7 | 10% |  |  | 0.15 |  | 50984 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 15% | Annex 3 Training (railway), allocated by hardware share | 105 |  | 2029-07-23 | 2029-08-05 | 10
NQR-T2020 | Trial operation (maximum 45 days) - Al Qurayyat | COM.NSR.NQR.TOA | Commissioning and handover | NQR | MS7 | 10% |  |  | 0.35 |  | 118962 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 35% | Annex 3 equipment sections A1-A5 (trial operation share) | 158 |  | 2029-07-23 | 2029-09-02 | 30
NQR-T3010 | Taking-over application, SAR review and handover - Al Qurayyat | COM.NSR.NQR.TOA | Commissioning and handover | NQR | MS7 | 10% |  |  | 0.3 |  | 101967 |  | MS7 Final acceptance and handover 10% x station price share 5.48% ¦ Fixed key 30% | Annex 3 equipment sections A1-A5 (handover share) | 158 |  | 2029-09-03 | 2029-09-16 | 10
Total

## Distribution_Keys
Distribution keys (cost within each payment milestone, and progress weights)
Milestone | Activity template | Key | Basis
MS2 | Survey, concept, preliminary, detailed, IFC, HCIS submittals | 5 / 10 / 20 / 40 / 20 / 5 % | Design effort split by stage; the railway design and engineering package sits inside the station price
MS3 | Approval activities of the same six stages | 5 / 10 / 20 / 40 / 20 / 5 % | Mirror of the submittal key (SAR review windows of 21 days)
MS4 | Manufacture CCTV, VMS, access control, UPS and network | 75% split by BOQ section share | A1, A2, A3 and A4+A5 shares of the station equipment value
MS4 | FAT / shipping and customs / delivery and receiving | 5 / 15 / 5 % | Fixed keys; spares and logistics sit inside delivery
MS5 | Civil trenches and duct banks / poles and foundations | 55 / 45 % of the A6 share | A6 civil works share of station hardware
MS5 | Install cabinets / cabling / CCTV / VMS / access control | 20 / 30 / 25 / 15 / 10 % of (1 - A6 share) | Installation is included in the unit prices (Annex 3 works included)
MS6 | Pre-commissioning / SAT | 40 / 60 % | Fixed keys
MS7 | As-built submittal / approval / training / trial operation / handover | 15 / 5 / 15 / 35 / 30 % | Fixed keys
MS1 | Performance security / initial baseline / site establishment / mobilization submittals | 15 / 10 / 45 / 30 % | Project level, 20% of the total price
EPC phase | Component | Weight (% of station progress) | Basis
Engineering | Survey 8, concept 10, preliminary 18, detailed 30, IFC 18, HCIS 6, as-built 10 (of 12%); each stage split submittal / approval by duration | 12 | Typical EPC effort weighting for design
Procurement | Manufacture 24 (split by BOQ package share), FAT 4, shipping 8, delivery 4 | 40 | Procurement carries the largest share of a supply-led security contract
Construction | Trenches 8, poles 6, cabinets 3, cabling 6, CCTV 5, VMS 3, access 2 | 33 | Site works
Commissioning and handover | Pre-commissioning 3, SAT 4, training 2, trial operation 3, handover 3 | 15 | Testing, trial and acceptance
Total stations |  |  | Station weights sum to 100%
Project level | Mobilization and baseline 2.7% and closeout pack 1.3% of the whole project | 4 | Stations carry 96% of the project, each station weighted by its BOQ price share

## S_Curve
S-curve: cost (contract payment conditions) against progress (fair EPC distribution), spread linearly over each activity
Month | Cost in month (SAR) | Cumulative cost (SAR) | Cumulative cost % | Progress in month % | Cumulative progress %
2026-11-01 | 10056397.47 |  |  | 1.854%
2026-12-01 | 2420944.53 |  |  | 0.4285%
2027-01-01 | 520681.05 |  |  | 0.7232%
2027-02-01 | 623690.2833 |  |  | 0.6956%
2027-03-01 | 399690.2064 |  |  | 0.9093%
2027-04-01 | 757411.0993 |  |  | 1.43%
2027-05-01 | 915463.8862 |  |  | 1.556%
2027-06-01 | 1222215.4636 |  |  | 1.882%
2027-07-01 | 787551.2726 |  |  | 1.966%
2027-08-01 | 1424402.4764 |  |  | 3.384%
2027-09-01 | 1691122.4011 |  |  | 3.592%
2027-10-01 | 2028280.0444 |  |  | 3.115%
2027-11-01 | 1901292.7792 |  |  | 3.529%
2027-12-01 | 1819386.9864 |  |  | 3.54%
2028-01-01 | 1804103.8005 |  |  | 3.869%
2028-02-01 | 1160169.6839 |  |  | 3.072%
2028-03-01 | 1921580.3758 |  |  | 4.672%
2028-04-01 | 2499904.1254 |  |  | 5.122%
2028-05-01 | 2419429.0077 |  |  | 4.057%
2028-06-01 | 3093462.0943 |  |  | 4.803%
2028-07-01 | 2508248.3825 |  |  | 5.891%
2028-08-01 | 2463009.7481 |  |  | 5.846%
2028-09-01 | 1819517.6043 |  |  | 3.146%
2028-10-01 | 1816161.2685 |  |  | 3.746%
2028-11-01 | 1357954.5694 |  |  | 3.571%
2028-12-01 | 1342590.8357 |  |  | 3.828%
2029-01-01 | 2070598.7371 |  |  | 4.077%
2029-02-01 | 1585187.7653 |  |  | 2.547%
2029-03-01 | 2092583.7051 |  |  | 3.623%
2029-04-01 | 1141004.5717 |  |  | 1.955%
2029-05-01 | 2142480.9535 |  |  | 3.006%
2029-06-01 | 895545.2413 |  |  | 1.495%
2029-07-01 | 1047756.181 |  |  | 1.407%
2029-08-01 | 143116 |  |  | 0.1954%
2029-09-01 | 107065.4 |  |  | 1.336%
2029-10-01 | 0 |  |  | 0.1301%

## Resources
Resource ID | Name | Type | Unit | Price per unit | Meaning | How P6 uses it
COST-SAR | Contract cost (BOQ x payment milestones) | Material | SAR | 1 | Budgeted cost of the activity in SAR from the contract payment conditions applied to the BOQ station value | Material resource: cost only. Budgeted units = SAR, so budgeted cost = units x 1. Not counted in Units % complete.
PROG-WT | Progress weight (fair EPC distribution) | Nonlabor | pt | 0 | Progress points: 100,000 points = 100% of the project. Fair EPC distribution (see Distribution_Keys) | Nonlabor resource with zero price. Activity % complete type is Units, so P6 measures progress with these points and the S-curve follows the points

## Activity_Codes
Code type | Code value | Description | Activities
Area | EWR |  | 117
Area | HHR |  | 156
Area | NSR |  | 195
Area | PRJ |  | 12
Area | RYD |  | 78
Discipline | ACC |  | 28
Discipline | CCTV |  | 42
Discipline | CIVIL |  | 28
Discipline | DOCS |  | 224
Discipline | PM |  | 82
Discipline | TC |  | 98
Discipline | UPSNET |  | 28
Discipline | VMS |  | 28
EPC phase | COM |  | 70
EPC phase | CON |  | 98
EPC phase | ENG |  | 196
EPC phase | MS |  | 88
EPC phase | PMG |  | 8
EPC phase | PRO |  | 98
Payment milestone | - |  | 6
Payment milestone | MS1 |  | 6
Payment milestone | MS2 |  | 98
Payment milestone | MS3 |  | 98
Payment milestone | MS4 |  | 112
Payment milestone | MS5 |  | 112
Payment milestone | MS6 |  | 42
Payment milestone | MS7 |  | 84
Priority | Riyadh priority |  | 78
Priority | Standard |  | 480
Railway | ALL |  | 12
Railway | EWR |  | 156
Railway | HHR |  | 156
Railway | NSR |  | 234
Responsibility | ETECHS |  | 314
Responsibility | SAR |  | 160
Responsibility | SAR/HCIS |  | 14
Responsibility | Vendor |  | 70
Design stage | - |  | 362
Design stage | As-built |  | 28
Design stage | Concept |  | 28
Design stage | Detailed |  | 28
Design stage | HCIS |  | 28
Design stage | IFC |  | 28
Design stage | Preliminary |  | 28
Design stage | Survey |  | 28
Station | EAB |  | 39
Station | EDM |  | 39
Station | EHF |  | 39
Station | ERY |  | 39
Station | HJD |  | 39
Station | HKA |  | 39
Station | HMD |  | 39
Station | HMK |  | 39
Station | NHL |  | 39
Station | NJF |  | 39
Station | NMJ |  | 39
Station | NQR |  | 39
Station | NQS |  | 39
Station | NRY |  | 39
Station | PRJ |  | 12
Submittal or approval | - |  | 357
Submittal or approval | Approval |  | 100
Submittal or approval | Submittal |  | 101

## WBS
WBS code | Name | Level | Parent
SAR-SEC | SAR Passengers Security Checking - HHR, EWR, NSR (14 stations) | 1
PM | Project Management and Mobilization | 2 | SAR-SEC
ENG | Engineering | 2 | SAR-SEC
PRO | Procurement | 2 | SAR-SEC
CON | Construction | 2 | SAR-SEC
COM | Commissioning and Handover | 2 | SAR-SEC
PM.MOB | Mobilization and baseline programme | 3 | PM
PM.MST | Contract milestones | 3 | PM
PM.CLO | Closeout | 3 | PM
ENG.RYD | Riyadh priority stations (NSR + EWR) | 3 | ENG
ENG.NSR | NSR - North South Railway | 3 | ENG
ENG.EWR | EWR - East West Railway | 3 | ENG
ENG.HHR | HHR - Haramain High Speed Rail | 3 | ENG
PRO.RYD | Riyadh priority stations (NSR + EWR) | 3 | PRO
PRO.NSR | NSR - North South Railway | 3 | PRO
PRO.EWR | EWR - East West Railway | 3 | PRO
PRO.HHR | HHR - Haramain High Speed Rail | 3 | PRO
CON.RYD | Riyadh priority stations (NSR + EWR) | 3 | CON
CON.NSR | NSR - North South Railway | 3 | CON
CON.EWR | EWR - East West Railway | 3 | CON
CON.HHR | HHR - Haramain High Speed Rail | 3 | CON
COM.RYD | Riyadh priority stations (NSR + EWR) | 3 | COM
COM.NSR | NSR - North South Railway | 3 | COM
COM.EWR | EWR - East West Railway | 3 | COM
COM.HHR | HHR - Haramain High Speed Rail | 3 | COM
ENG.RYD.NRY | Riyadh (Thumamah) (NSR) | 4 | ENG.RYD
PRO.RYD.NRY | Riyadh (Thumamah) (NSR) | 4 | PRO.RYD
CON.RYD.NRY | Riyadh (Thumamah) (NSR) | 4 | CON.RYD
COM.RYD.NRY | Riyadh (Thumamah) (NSR) | 4 | COM.RYD
ENG.RYD.NRY.SRV | Site survey and as-found verification | 5 | ENG.RYD.NRY
ENG.RYD.NRY.SRV.SUB | Submittal | 6 | ENG.RYD.NRY.SRV
ENG.RYD.NRY.SRV.APR | Approval | 6 | ENG.RYD.NRY.SRV
ENG.RYD.NRY.CNC | Concept design | 5 | ENG.RYD.NRY
ENG.RYD.NRY.CNC.SUB | Submittal | 6 | ENG.RYD.NRY.CNC
ENG.RYD.NRY.CNC.APR | Approval | 6 | ENG.RYD.NRY.CNC
ENG.RYD.NRY.PRE | Preliminary (schematic) design | 5 | ENG.RYD.NRY
ENG.RYD.NRY.PRE.SUB | Submittal | 6 | ENG.RYD.NRY.PRE
ENG.RYD.NRY.PRE.APR | Approval | 6 | ENG.RYD.NRY.PRE
ENG.RYD.NRY.DET | Detailed design | 5 | ENG.RYD.NRY
ENG.RYD.NRY.DET.SUB | Submittal | 6 | ENG.RYD.NRY.DET
ENG.RYD.NRY.DET.APR | Approval | 6 | ENG.RYD.NRY.DET
ENG.RYD.NRY.IFC | IFC and shop drawings | 5 | ENG.RYD.NRY
ENG.RYD.NRY.IFC.SUB | Submittal | 6 | ENG.RYD.NRY.IFC
ENG.RYD.NRY.IFC.APR | Approval | 6 | ENG.RYD.NRY.IFC
ENG.RYD.NRY.HCS | HCIS documentation (Stage 3 and 4) | 5 | ENG.RYD.NRY
ENG.RYD.NRY.HCS.SUB | Submittal | 6 | ENG.RYD.NRY.HCS
ENG.RYD.NRY.HCS.APR | Approval | 6 | ENG.RYD.NRY.HCS
ENG.RYD.NRY.ASB | As-built and O&M documentation | 5 | ENG.RYD.NRY
ENG.RYD.NRY.ASB.SUB | Submittal | 6 | ENG.RYD.NRY.ASB
ENG.RYD.NRY.ASB.APR | Approval | 6 | ENG.RYD.NRY.ASB
PRO.RYD.NRY.CCT | CCTV system | 5 | PRO.RYD.NRY
PRO.RYD.NRY.VMS | Video management and video wall | 5 | PRO.RYD.NRY
PRO.RYD.NRY.ACC | Access control and intercom | 5 | PRO.RYD.NRY
PRO.RYD.NRY.UPN | UPS, network and cabinets | 5 | PRO.RYD.NRY
PRO.RYD.NRY.LOG | FAT and logistics | 5 | PRO.RYD.NRY
CON.RYD.NRY.CIV | Civil works | 5 | CON.RYD.NRY
CON.RYD.NRY.INS | Installation | 5 | CON.RYD.NRY
COM.RYD.NRY.TST | Testing and commissioning | 5 | COM.RYD.NRY
COM.RYD.NRY.TRN | Training | 5 | COM.RYD.NRY
COM.RYD.NRY.TOA | Trial operation and acceptance | 5 | COM.RYD.NRY
ENG.RYD.ERY | Riyadh (Malaz) (EWR) | 4 | ENG.RYD
PRO.RYD.ERY | Riyadh (Malaz) (EWR) | 4 | PRO.RYD
CON.RYD.ERY | Riyadh (Malaz) (EWR) | 4 | CON.RYD
COM.RYD.ERY | Riyadh (Malaz) (EWR) | 4 | COM.RYD
ENG.RYD.ERY.SRV | Site survey and as-found verification | 5 | ENG.RYD.ERY
ENG.RYD.ERY.SRV.SUB | Submittal | 6 | ENG.RYD.ERY.SRV
ENG.RYD.ERY.SRV.APR | Approval | 6 | ENG.RYD.ERY.SRV
ENG.RYD.ERY.CNC | Concept design | 5 | ENG.RYD.ERY
ENG.RYD.ERY.CNC.SUB | Submittal | 6 | ENG.RYD.ERY.CNC
ENG.RYD.ERY.CNC.APR | Approval | 6 | ENG.RYD.ERY.CNC
ENG.RYD.ERY.PRE | Preliminary (schematic) design | 5 | ENG.RYD.ERY
ENG.RYD.ERY.PRE.SUB | Submittal | 6 | ENG.RYD.ERY.PRE
ENG.RYD.ERY.PRE.APR | Approval | 6 | ENG.RYD.ERY.PRE
ENG.RYD.ERY.DET | Detailed design | 5 | ENG.RYD.ERY
ENG.RYD.ERY.DET.SUB | Submittal | 6 | ENG.RYD.ERY.DET
ENG.RYD.ERY.DET.APR | Approval | 6 | ENG.RYD.ERY.DET
ENG.RYD.ERY.IFC | IFC and shop drawings | 5 | ENG.RYD.ERY
ENG.RYD.ERY.IFC.SUB | Submittal | 6 | ENG.RYD.ERY.IFC
ENG.RYD.ERY.IFC.APR | Approval | 6 | ENG.RYD.ERY.IFC
ENG.RYD.ERY.HCS | HCIS documentation (Stage 3 and 4) | 5 | ENG.RYD.ERY
ENG.RYD.ERY.HCS.SUB | Submittal | 6 | ENG.RYD.ERY.HCS
ENG.RYD.ERY.HCS.APR | Approval | 6 | ENG.RYD.ERY.HCS
ENG.RYD.ERY.ASB | As-built and O&M documentation | 5 | ENG.RYD.ERY
ENG.RYD.ERY.ASB.SUB | Submittal | 6 | ENG.RYD.ERY.ASB
ENG.RYD.ERY.ASB.APR | Approval | 6 | ENG.RYD.ERY.ASB
PRO.RYD.ERY.CCT | CCTV system | 5 | PRO.RYD.ERY
PRO.RYD.ERY.VMS | Video management and video wall | 5 | PRO.RYD.ERY
PRO.RYD.ERY.ACC | Access control and intercom | 5 | PRO.RYD.ERY
PRO.RYD.ERY.UPN | UPS, network and cabinets | 5 | PRO.RYD.ERY
PRO.RYD.ERY.LOG | FAT and logistics | 5 | PRO.RYD.ERY
CON.RYD.ERY.CIV | Civil works | 5 | CON.RYD.ERY
CON.RYD.ERY.INS | Installation | 5 | CON.RYD.ERY
COM.RYD.ERY.TST | Testing and commissioning | 5 | COM.RYD.ERY
COM.RYD.ERY.TRN | Training | 5 | COM.RYD.ERY
COM.RYD.ERY.TOA | Trial operation and acceptance | 5 | COM.RYD.ERY
ENG.HHR.HJD | Jeddah (HHR) | 4 | ENG.HHR
PRO.HHR.HJD | Jeddah (HHR) | 4 | PRO.HHR
CON.HHR.HJD | Jeddah (HHR) | 4 | CON.HHR
COM.HHR.HJD | Jeddah (HHR) | 4 | COM.HHR
ENG.HHR.HJD.SRV | Site survey and as-found verification | 5 | ENG.HHR.HJD
ENG.HHR.HJD.SRV.SUB | Submittal | 6 | ENG.HHR.HJD.SRV
ENG.HHR.HJD.SRV.APR | Approval | 6 | ENG.HHR.HJD.SRV
ENG.HHR.HJD.CNC | Concept design | 5 | ENG.HHR.HJD
ENG.HHR.HJD.CNC.SUB | Submittal | 6 | ENG.HHR.HJD.CNC
ENG.HHR.HJD.CNC.APR | Approval | 6 | ENG.HHR.HJD.CNC
ENG.HHR.HJD.PRE | Preliminary (schematic) design | 5 | ENG.HHR.HJD
ENG.HHR.HJD.PRE.SUB | Submittal | 6 | ENG.HHR.HJD.PRE
ENG.HHR.HJD.PRE.APR | Approval | 6 | ENG.HHR.HJD.PRE
ENG.HHR.HJD.DET | Detailed design | 5 | ENG.HHR.HJD
ENG.HHR.HJD.DET.SUB | Submittal | 6 | ENG.HHR.HJD.DET
ENG.HHR.HJD.DET.APR | Approval | 6 | ENG.HHR.HJD.DET
ENG.HHR.HJD.IFC | IFC and shop drawings | 5 | ENG.HHR.HJD
ENG.HHR.HJD.IFC.SUB | Submittal | 6 | ENG.HHR.HJD.IFC
ENG.HHR.HJD.IFC.APR | Approval | 6 | ENG.HHR.HJD.IFC
ENG.HHR.HJD.HCS | HCIS documentation (Stage 3 and 4) | 5 | ENG.HHR.HJD
ENG.HHR.HJD.HCS.SUB | Submittal | 6 | ENG.HHR.HJD.HCS
ENG.HHR.HJD.HCS.APR | Approval | 6 | ENG.HHR.HJD.HCS
ENG.HHR.HJD.ASB | As-built and O&M documentation | 5 | ENG.HHR.HJD
ENG.HHR.HJD.ASB.SUB | Submittal | 6 | ENG.HHR.HJD.ASB
ENG.HHR.HJD.ASB.APR | Approval | 6 | ENG.HHR.HJD.ASB
PRO.HHR.HJD.CCT | CCTV system | 5 | PRO.HHR.HJD
PRO.HHR.HJD.VMS | Video management and video wall | 5 | PRO.HHR.HJD
PRO.HHR.HJD.ACC | Access control and intercom | 5 | PRO.HHR.HJD
PRO.HHR.HJD.UPN | UPS, network and cabinets | 5 | PRO.HHR.HJD
PRO.HHR.HJD.LOG | FAT and logistics | 5 | PRO.HHR.HJD
CON.HHR.HJD.CIV | Civil works | 5 | CON.HHR.HJD
CON.HHR.HJD.INS | Installation | 5 | CON.HHR.HJD
COM.HHR.HJD.TST | Testing and commissioning | 5 | COM.HHR.HJD
COM.HHR.HJD.TRN | Training | 5 | COM.HHR.HJD
COM.HHR.HJD.TOA | Trial operation and acceptance | 5 | COM.HHR.HJD
ENG.EWR.EDM | Dammam (EWR) | 4 | ENG.EWR
PRO.EWR.EDM | Dammam (EWR) | 4 | PRO.EWR
CON.EWR.EDM | Dammam (EWR) | 4 | CON.EWR
COM.EWR.EDM | Dammam (EWR) | 4 | COM.EWR
ENG.EWR.EDM.SRV | Site survey and as-found verification | 5 | ENG.EWR.EDM
ENG.EWR.EDM.SRV.SUB | Submittal | 6 | ENG.EWR.EDM.SRV
ENG.EWR.EDM.SRV.APR | Approval | 6 | ENG.EWR.EDM.SRV
ENG.EWR.EDM.CNC | Concept design | 5 | ENG.EWR.EDM
ENG.EWR.EDM.CNC.SUB | Submittal | 6 | ENG.EWR.EDM.CNC
ENG.EWR.EDM.CNC.APR | Approval | 6 | ENG.EWR.EDM.CNC
ENG.EWR.EDM.PRE | Preliminary (schematic) design | 5 | ENG.EWR.EDM
ENG.EWR.EDM.PRE.SUB | Submittal | 6 | ENG.EWR.EDM.PRE
ENG.EWR.EDM.PRE.APR | Approval | 6 | ENG.EWR.EDM.PRE
ENG.EWR.EDM.DET | Detailed design | 5 | ENG.EWR.EDM
ENG.EWR.EDM.DET.SUB | Submittal | 6 | ENG.EWR.EDM.DET
ENG.EWR.EDM.DET.APR | Approval | 6 | ENG.EWR.EDM.DET
ENG.EWR.EDM.IFC | IFC and shop drawings | 5 | ENG.EWR.EDM
ENG.EWR.EDM.IFC.SUB | Submittal | 6 | ENG.EWR.EDM.IFC
ENG.EWR.EDM.IFC.APR | Approval | 6 | ENG.EWR.EDM.IFC
ENG.EWR.EDM.HCS | HCIS documentation (Stage 3 and 4) | 5 | ENG.EWR.EDM
ENG.EWR.EDM.HCS.SUB | Submittal | 6 | ENG.EWR.EDM.HCS
ENG.EWR.EDM.HCS.APR | Approval | 6 | ENG.EWR.EDM.HCS
ENG.EWR.EDM.ASB | As-built and O&M documentation | 5 | ENG.EWR.EDM
ENG.EWR.EDM.ASB.SUB | Submittal | 6 | ENG.EWR.EDM.ASB
ENG.EWR.EDM.ASB.APR | Approval | 6 | ENG.EWR.EDM.ASB
PRO.EWR.EDM.CCT | CCTV system | 5 | PRO.EWR.EDM
PRO.EWR.EDM.VMS | Video management and video wall | 5 | PRO.EWR.EDM
PRO.EWR.EDM.ACC | Access control and intercom | 5 | PRO.EWR.EDM
PRO.EWR.EDM.UPN | UPS, network and cabinets | 5 | PRO.EWR.EDM
PRO.EWR.EDM.LOG | FAT and logistics | 5 | PRO.EWR.EDM
CON.EWR.EDM.CIV | Civil works | 5 | CON.EWR.EDM
CON.EWR.EDM.INS | Installation | 5 | CON.EWR.EDM
COM.EWR.EDM.TST | Testing and commissioning | 5 | COM.EWR.EDM
COM.EWR.EDM.TRN | Training | 5 | COM.EWR.EDM
COM.EWR.EDM.TOA | Trial operation and acceptance | 5 | COM.EWR.EDM
ENG.NSR.NQS | Al Qassim (NSR) | 4 | ENG.NSR
PRO.NSR.NQS | Al Qassim (NSR) | 4 | PRO.NSR
CON.NSR.NQS | Al Qassim (NSR) | 4 | CON.NSR
COM.NSR.NQS | Al Qassim (NSR) | 4 | COM.NSR
ENG.NSR.NQS.SRV | Site survey and as-found verification | 5 | ENG.NSR.NQS
ENG.NSR.NQS.SRV.SUB | Submittal | 6 | ENG.NSR.NQS.SRV
ENG.NSR.NQS.SRV.APR | Approval | 6 | ENG.NSR.NQS.SRV
ENG.NSR.NQS.CNC | Concept design | 5 | ENG.NSR.NQS
ENG.NSR.NQS.CNC.SUB | Submittal | 6 | ENG.NSR.NQS.CNC
ENG.NSR.NQS.CNC.APR | Approval | 6 | ENG.NSR.NQS.CNC
ENG.NSR.NQS.PRE | Preliminary (schematic) design | 5 | ENG.NSR.NQS
ENG.NSR.NQS.PRE.SUB | Submittal | 6 | ENG.NSR.NQS.PRE
ENG.NSR.NQS.PRE.APR | Approval | 6 | ENG.NSR.NQS.PRE
ENG.NSR.NQS.DET | Detailed design | 5 | ENG.NSR.NQS
ENG.NSR.NQS.DET.SUB | Submittal | 6 | ENG.NSR.NQS.DET
ENG.NSR.NQS.DET.APR | Approval | 6 | ENG.NSR.NQS.DET
ENG.NSR.NQS.IFC | IFC and shop drawings | 5 | ENG.NSR.NQS
ENG.NSR.NQS.IFC.SUB | Submittal | 6 | ENG.NSR.NQS.IFC
ENG.NSR.NQS.IFC.APR | Approval | 6 | ENG.NSR.NQS.IFC
ENG.NSR.NQS.HCS | HCIS documentation (Stage 3 and 4) | 5 | ENG.NSR.NQS
ENG.NSR.NQS.HCS.SUB | Submittal | 6 | ENG.NSR.NQS.HCS
ENG.NSR.NQS.HCS.APR | Approval | 6 | ENG.NSR.NQS.HCS
ENG.NSR.NQS.ASB | As-built and O&M documentation | 5 | ENG.NSR.NQS
ENG.NSR.NQS.ASB.SUB | Submittal | 6 | ENG.NSR.NQS.ASB
ENG.NSR.NQS.ASB.APR | Approval | 6 | ENG.NSR.NQS.ASB
PRO.NSR.NQS.CCT | CCTV system | 5 | PRO.NSR.NQS
PRO.NSR.NQS.VMS | Video management and video wall | 5 | PRO.NSR.NQS
PRO.NSR.NQS.ACC | Access control and intercom | 5 | PRO.NSR.NQS
PRO.NSR.NQS.UPN | UPS, network and cabinets | 5 | PRO.NSR.NQS
PRO.NSR.NQS.LOG | FAT and logistics | 5 | PRO.NSR.NQS
CON.NSR.NQS.CIV | Civil works | 5 | CON.NSR.NQS
CON.NSR.NQS.INS | Installation | 5 | CON.NSR.NQS
COM.NSR.NQS.TST | Testing and commissioning | 5 | COM.NSR.NQS
COM.NSR.NQS.TRN | Training | 5 | COM.NSR.NQS
COM.NSR.NQS.TOA | Trial operation and acceptance | 5 | COM.NSR.NQS
ENG.EWR.EHF | Hufuf (EWR) | 4 | ENG.EWR
PRO.EWR.EHF | Hufuf (EWR) | 4 | PRO.EWR
CON.EWR.EHF | Hufuf (EWR) | 4 | CON.EWR
COM.EWR.EHF | Hufuf (EWR) | 4 | COM.EWR
ENG.EWR.EHF.SRV | Site survey and as-found verification | 5 | ENG.EWR.EHF
ENG.EWR.EHF.SRV.SUB | Submittal | 6 | ENG.EWR.EHF.SRV
ENG.EWR.EHF.SRV.APR | Approval | 6 | ENG.EWR.EHF.SRV
ENG.EWR.EHF.CNC | Concept design | 5 | ENG.EWR.EHF
ENG.EWR.EHF.CNC.SUB | Submittal | 6 | ENG.EWR.EHF.CNC
ENG.EWR.EHF.CNC.APR | Approval | 6 | ENG.EWR.EHF.CNC
ENG.EWR.EHF.PRE | Preliminary (schematic) design | 5 | ENG.EWR.EHF
ENG.EWR.EHF.PRE.SUB | Submittal | 6 | ENG.EWR.EHF.PRE
ENG.EWR.EHF.PRE.APR | Approval | 6 | ENG.EWR.EHF.PRE
ENG.EWR.EHF.DET | Detailed design | 5 | ENG.EWR.EHF
ENG.EWR.EHF.DET.SUB | Submittal | 6 | ENG.EWR.EHF.DET
ENG.EWR.EHF.DET.APR | Approval | 6 | ENG.EWR.EHF.DET
ENG.EWR.EHF.IFC | IFC and shop drawings | 5 | ENG.EWR.EHF
ENG.EWR.EHF.IFC.SUB | Submittal | 6 | ENG.EWR.EHF.IFC
ENG.EWR.EHF.IFC.APR | Approval | 6 | ENG.EWR.EHF.IFC
ENG.EWR.EHF.HCS | HCIS documentation (Stage 3 and 4) | 5 | ENG.EWR.EHF
ENG.EWR.EHF.HCS.SUB | Submittal | 6 | ENG.EWR.EHF.HCS
ENG.EWR.EHF.HCS.APR | Approval | 6 | ENG.EWR.EHF.HCS
ENG.EWR.EHF.ASB | As-built and O&M documentation | 5 | ENG.EWR.EHF
ENG.EWR.EHF.ASB.SUB | Submittal | 6 | ENG.EWR.EHF.ASB
ENG.EWR.EHF.ASB.APR | Approval | 6 | ENG.EWR.EHF.ASB
PRO.EWR.EHF.CCT | CCTV system | 5 | PRO.EWR.EHF
PRO.EWR.EHF.VMS | Video management and video wall | 5 | PRO.EWR.EHF
PRO.EWR.EHF.ACC | Access control and intercom | 5 | PRO.EWR.EHF
PRO.EWR.EHF.UPN | UPS, network and cabinets | 5 | PRO.EWR.EHF
PRO.EWR.EHF.LOG | FAT and logistics | 5 | PRO.EWR.EHF
CON.EWR.EHF.CIV | Civil works | 5 | CON.EWR.EHF
CON.EWR.EHF.INS | Installation | 5 | CON.EWR.EHF
COM.EWR.EHF.TST | Testing and commissioning | 5 | COM.EWR.EHF
COM.EWR.EHF.TRN | Training | 5 | COM.EWR.EHF
COM.EWR.EHF.TOA | Trial operation and acceptance | 5 | COM.EWR.EHF
ENG.NSR.NMJ | Al Majma'ah (NSR) | 4 | ENG.NSR
PRO.NSR.NMJ | Al Majma'ah (NSR) | 4 | PRO.NSR
CON.NSR.NMJ | Al Majma'ah (NSR) | 4 | CON.NSR
COM.NSR.NMJ | Al Majma'ah (NSR) | 4 | COM.NSR
ENG.NSR.NMJ.SRV | Site survey and as-found verification | 5 | ENG.NSR.NMJ
ENG.NSR.NMJ.SRV.SUB | Submittal | 6 | ENG.NSR.NMJ.SRV
ENG.NSR.NMJ.SRV.APR | Approval | 6 | ENG.NSR.NMJ.SRV
ENG.NSR.NMJ.CNC | Concept design | 5 | ENG.NSR.NMJ
ENG.NSR.NMJ.CNC.SUB | Submittal | 6 | ENG.NSR.NMJ.CNC
ENG.NSR.NMJ.CNC.APR | Approval | 6 | ENG.NSR.NMJ.CNC
ENG.NSR.NMJ.PRE | Preliminary (schematic) design | 5 | ENG.NSR.NMJ
ENG.NSR.NMJ.PRE.SUB | Submittal | 6 | ENG.NSR.NMJ.PRE
ENG.NSR.NMJ.PRE.APR | Approval | 6 | ENG.NSR.NMJ.PRE
ENG.NSR.NMJ.DET | Detailed design | 5 | ENG.NSR.NMJ
ENG.NSR.NMJ.DET.SUB | Submittal | 6 | ENG.NSR.NMJ.DET
ENG.NSR.NMJ.DET.APR | Approval | 6 | ENG.NSR.NMJ.DET
ENG.NSR.NMJ.IFC | IFC and shop drawings | 5 | ENG.NSR.NMJ
ENG.NSR.NMJ.IFC.SUB | Submittal | 6 | ENG.NSR.NMJ.IFC
ENG.NSR.NMJ.IFC.APR | Approval | 6 | ENG.NSR.NMJ.IFC
ENG.NSR.NMJ.HCS | HCIS documentation (Stage 3 and 4) | 5 | ENG.NSR.NMJ
ENG.NSR.NMJ.HCS.SUB | Submittal | 6 | ENG.NSR.NMJ.HCS
ENG.NSR.NMJ.HCS.APR | Approval | 6 | ENG.NSR.NMJ.HCS
ENG.NSR.NMJ.ASB | As-built and O&M documentation | 5 | ENG.NSR.NMJ
ENG.NSR.NMJ.ASB.SUB | Submittal | 6 | ENG.NSR.NMJ.ASB
ENG.NSR.NMJ.ASB.APR | Approval | 6 | ENG.NSR.NMJ.ASB
PRO.NSR.NMJ.CCT | CCTV system | 5 | PRO.NSR.NMJ
PRO.NSR.NMJ.VMS | Video management and video wall | 5 | PRO.NSR.NMJ
PRO.NSR.NMJ.ACC | Access control and intercom | 5 | PRO.NSR.NMJ
PRO.NSR.NMJ.UPN | UPS, network and cabinets | 5 | PRO.NSR.NMJ
PRO.NSR.NMJ.LOG | FAT and logistics | 5 | PRO.NSR.NMJ
CON.NSR.NMJ.CIV | Civil works | 5 | CON.NSR.NMJ
CON.NSR.NMJ.INS | Installation | 5 | CON.NSR.NMJ
COM.NSR.NMJ.TST | Testing and commissioning | 5 | COM.NSR.NMJ
COM.NSR.NMJ.TRN | Training | 5 | COM.NSR.NMJ
COM.NSR.NMJ.TOA | Trial operation and acceptance | 5 | COM.NSR.NMJ
ENG.HHR.HMK | Makkah (HHR) | 4 | ENG.HHR
PRO.HHR.HMK | Makkah (HHR) | 4 | PRO.HHR
CON.HHR.HMK | Makkah (HHR) | 4 | CON.HHR
COM.HHR.HMK | Makkah (HHR) | 4 | COM.HHR
ENG.HHR.HMK.SRV | Site survey and as-found verification | 5 | ENG.HHR.HMK
ENG.HHR.HMK.SRV.SUB | Submittal | 6 | ENG.HHR.HMK.SRV
ENG.HHR.HMK.SRV.APR | Approval | 6 | ENG.HHR.HMK.SRV
ENG.HHR.HMK.CNC | Concept design | 5 | ENG.HHR.HMK
ENG.HHR.HMK.CNC.SUB | Submittal | 6 | ENG.HHR.HMK.CNC
ENG.HHR.HMK.CNC.APR | Approval | 6 | ENG.HHR.HMK.CNC
ENG.HHR.HMK.PRE | Preliminary (schematic) design | 5 | ENG.HHR.HMK
ENG.HHR.HMK.PRE.SUB | Submittal | 6 | ENG.HHR.HMK.PRE
ENG.HHR.HMK.PRE.APR | Approval | 6 | ENG.HHR.HMK.PRE
ENG.HHR.HMK.DET | Detailed design | 5 | ENG.HHR.HMK
ENG.HHR.HMK.DET.SUB | Submittal | 6 | ENG.HHR.HMK.DET
ENG.HHR.HMK.DET.APR | Approval | 6 | ENG.HHR.HMK.DET
ENG.HHR.HMK.IFC | IFC and shop drawings | 5 | ENG.HHR.HMK
ENG.HHR.HMK.IFC.SUB | Submittal | 6 | ENG.HHR.HMK.IFC
ENG.HHR.HMK.IFC.APR | Approval | 6 | ENG.HHR.HMK.IFC
ENG.HHR.HMK.HCS | HCIS documentation (Stage 3 and 4) | 5 | ENG.HHR.HMK
ENG.HHR.HMK.HCS.SUB | Submittal | 6 | ENG.HHR.HMK.HCS
ENG.HHR.HMK.HCS.APR | Approval | 6 | ENG.HHR.HMK.HCS
ENG.HHR.HMK.ASB | As-built and O&M documentation | 5 | ENG.HHR.HMK
ENG.HHR.HMK.ASB.SUB | Submittal | 6 | ENG.HHR.HMK.ASB
ENG.HHR.HMK.ASB.APR | Approval | 6 | ENG.HHR.HMK.ASB
PRO.HHR.HMK.CCT | CCTV system | 5 | PRO.HHR.HMK
PRO.HHR.HMK.VMS | Video management and video wall | 5 | PRO.HHR.HMK
PRO.HHR.HMK.ACC | Access control and intercom | 5 | PRO.HHR.HMK
PRO.HHR.HMK.UPN | UPS, network and cabinets | 5 | PRO.HHR.HMK
PRO.HHR.HMK.LOG | FAT and logistics | 5 | PRO.HHR.HMK
CON.HHR.HMK.CIV | Civil works | 5 | CON.HHR.HMK
CON.HHR.HMK.INS | Installation | 5 | CON.HHR.HMK
COM.HHR.HMK.TST | Testing and commissioning | 5 | COM.HHR.HMK
COM.HHR.HMK.TRN | Training | 5 | COM.HHR.HMK
COM.HHR.HMK.TOA | Trial operation and acceptance | 5 | COM.HHR.HMK
ENG.HHR.HKA | KAEC (HHR) | 4 | ENG.HHR
PRO.HHR.HKA | KAEC (HHR) | 4 | PRO.HHR
CON.HHR.HKA | KAEC (HHR) | 4 | CON.HHR
COM.HHR.HKA | KAEC (HHR) | 4 | COM.HHR
ENG.HHR.HKA.SRV | Site survey and as-found verification | 5 | ENG.HHR.HKA
ENG.HHR.HKA.SRV.SUB | Submittal | 6 | ENG.HHR.HKA.SRV
ENG.HHR.HKA.SRV.APR | Approval | 6 | ENG.HHR.HKA.SRV
ENG.HHR.HKA.CNC | Concept design | 5 | ENG.HHR.HKA
ENG.HHR.HKA.CNC.SUB | Submittal | 6 | ENG.HHR.HKA.CNC
ENG.HHR.HKA.CNC.APR | Approval | 6 | ENG.HHR.HKA.CNC
ENG.HHR.HKA.PRE | Preliminary (schematic) design | 5 | ENG.HHR.HKA
ENG.HHR.HKA.PRE.SUB | Submittal | 6 | ENG.HHR.HKA.PRE
ENG.HHR.HKA.PRE.APR | Approval | 6 | ENG.HHR.HKA.PRE
ENG.HHR.HKA.DET | Detailed design | 5 | ENG.HHR.HKA
ENG.HHR.HKA.DET.SUB | Submittal | 6 | ENG.HHR.HKA.DET
ENG.HHR.HKA.DET.APR | Approval | 6 | ENG.HHR.HKA.DET
ENG.HHR.HKA.IFC | IFC and shop drawings | 5 | ENG.HHR.HKA
ENG.HHR.HKA.IFC.SUB | Submittal | 6 | ENG.HHR.HKA.IFC
ENG.HHR.HKA.IFC.APR | Approval | 6 | ENG.HHR.HKA.IFC
ENG.HHR.HKA.HCS | HCIS documentation (Stage 3 and 4) | 5 | ENG.HHR.HKA
ENG.HHR.HKA.HCS.SUB | Submittal | 6 | ENG.HHR.HKA.HCS
ENG.HHR.HKA.HCS.APR | Approval | 6 | ENG.HHR.HKA.HCS
ENG.HHR.HKA.ASB | As-built and O&M documentation | 5 | ENG.HHR.HKA
ENG.HHR.HKA.ASB.SUB | Submittal | 6 | ENG.HHR.HKA.ASB
ENG.HHR.HKA.ASB.APR | Approval | 6 | ENG.HHR.HKA.ASB
PRO.HHR.HKA.CCT | CCTV system | 5 | PRO.HHR.HKA
PRO.HHR.HKA.VMS | Video management and video wall | 5 | PRO.HHR.HKA
PRO.HHR.HKA.ACC | Access control and intercom | 5 | PRO.HHR.HKA
PRO.HHR.HKA.UPN | UPS, network and cabinets | 5 | PRO.HHR.HKA
PRO.HHR.HKA.LOG | FAT and logistics | 5 | PRO.HHR.HKA
CON.HHR.HKA.CIV | Civil works | 5 | CON.HHR.HKA
CON.HHR.HKA.INS | Installation | 5 | CON.HHR.HKA
COM.HHR.HKA.TST | Testing and commissioning | 5 | COM.HHR.HKA
COM.HHR.HKA.TRN | Training | 5 | COM.HHR.HKA
COM.HHR.HKA.TOA | Trial operation and acceptance | 5 | COM.HHR.HKA
ENG.HHR.HMD | Madinah (HHR) | 4 | ENG.HHR
PRO.HHR.HMD | Madinah (HHR) | 4 | PRO.HHR
CON.HHR.HMD | Madinah (HHR) | 4 | CON.HHR
COM.HHR.HMD | Madinah (HHR) | 4 | COM.HHR
ENG.HHR.HMD.SRV | Site survey and as-found verification | 5 | ENG.HHR.HMD
ENG.HHR.HMD.SRV.SUB | Submittal | 6 | ENG.HHR.HMD.SRV
ENG.HHR.HMD.SRV.APR | Approval | 6 | ENG.HHR.HMD.SRV
ENG.HHR.HMD.CNC | Concept design | 5 | ENG.HHR.HMD
ENG.HHR.HMD.CNC.SUB | Submittal | 6 | ENG.HHR.HMD.CNC
ENG.HHR.HMD.CNC.APR | Approval | 6 | ENG.HHR.HMD.CNC
ENG.HHR.HMD.PRE | Preliminary (schematic) design | 5 | ENG.HHR.HMD
ENG.HHR.HMD.PRE.SUB | Submittal | 6 | ENG.HHR.HMD.PRE
ENG.HHR.HMD.PRE.APR | Approval | 6 | ENG.HHR.HMD.PRE
ENG.HHR.HMD.DET | Detailed design | 5 | ENG.HHR.HMD
ENG.HHR.HMD.DET.SUB | Submittal | 6 | ENG.HHR.HMD.DET
ENG.HHR.HMD.DET.APR | Approval | 6 | ENG.HHR.HMD.DET
ENG.HHR.HMD.IFC | IFC and shop drawings | 5 | ENG.HHR.HMD
ENG.HHR.HMD.IFC.SUB | Submittal | 6 | ENG.HHR.HMD.IFC
ENG.HHR.HMD.IFC.APR | Approval | 6 | ENG.HHR.HMD.IFC
ENG.HHR.HMD.HCS | HCIS documentation (Stage 3 and 4) | 5 | ENG.HHR.HMD
ENG.HHR.HMD.HCS.SUB | Submittal | 6 | ENG.HHR.HMD.HCS
ENG.HHR.HMD.HCS.APR | Approval | 6 | ENG.HHR.HMD.HCS
ENG.HHR.HMD.ASB | As-built and O&M documentation | 5 | ENG.HHR.HMD
ENG.HHR.HMD.ASB.SUB | Submittal | 6 | ENG.HHR.HMD.ASB
ENG.HHR.HMD.ASB.APR | Approval | 6 | ENG.HHR.HMD.ASB
PRO.HHR.HMD.CCT | CCTV system | 5 | PRO.HHR.HMD
PRO.HHR.HMD.VMS | Video management and video wall | 5 | PRO.HHR.HMD
PRO.HHR.HMD.ACC | Access control and intercom | 5 | PRO.HHR.HMD
PRO.HHR.HMD.UPN | UPS, network and cabinets | 5 | PRO.HHR.HMD
PRO.HHR.HMD.LOG | FAT and logistics | 5 | PRO.HHR.HMD
CON.HHR.HMD.CIV | Civil works | 5 | CON.HHR.HMD
CON.HHR.HMD.INS | Installation | 5 | CON.HHR.HMD
COM.HHR.HMD.TST | Testing and commissioning | 5 | COM.HHR.HMD
COM.HHR.HMD.TRN | Training | 5 | COM.HHR.HMD
COM.HHR.HMD.TOA | Trial operation and acceptance | 5 | COM.HHR.HMD
ENG.EWR.EAB | Abqaiq (EWR) | 4 | ENG.EWR
PRO.EWR.EAB | Abqaiq (EWR) | 4 | PRO.EWR
CON.EWR.EAB | Abqaiq (EWR) | 4 | CON.EWR
COM.EWR.EAB | Abqaiq (EWR) | 4 | COM.EWR
ENG.EWR.EAB.SRV | Site survey and as-found verification | 5 | ENG.EWR.EAB
ENG.EWR.EAB.SRV.SUB | Submittal | 6 | ENG.EWR.EAB.SRV
ENG.EWR.EAB.SRV.APR | Approval | 6 | ENG.EWR.EAB.SRV
ENG.EWR.EAB.CNC | Concept design | 5 | ENG.EWR.EAB
ENG.EWR.EAB.CNC.SUB | Submittal | 6 | ENG.EWR.EAB.CNC
ENG.EWR.EAB.CNC.APR | Approval | 6 | ENG.EWR.EAB.CNC
ENG.EWR.EAB.PRE | Preliminary (schematic) design | 5 | ENG.EWR.EAB
ENG.EWR.EAB.PRE.SUB | Submittal | 6 | ENG.EWR.EAB.PRE
ENG.EWR.EAB.PRE.APR | Approval | 6 | ENG.EWR.EAB.PRE
ENG.EWR.EAB.DET | Detailed design | 5 | ENG.EWR.EAB
ENG.EWR.EAB.DET.SUB | Submittal | 6 | ENG.EWR.EAB.DET
ENG.EWR.EAB.DET.APR | Approval | 6 | ENG.EWR.EAB.DET
ENG.EWR.EAB.IFC | IFC and shop drawings | 5 | ENG.EWR.EAB
ENG.EWR.EAB.IFC.SUB | Submittal | 6 | ENG.EWR.EAB.IFC
ENG.EWR.EAB.IFC.APR | Approval | 6 | ENG.EWR.EAB.IFC
ENG.EWR.EAB.HCS | HCIS documentation (Stage 3 and 4) | 5 | ENG.EWR.EAB
ENG.EWR.EAB.HCS.SUB | Submittal | 6 | ENG.EWR.EAB.HCS
ENG.EWR.EAB.HCS.APR | Approval | 6 | ENG.EWR.EAB.HCS
ENG.EWR.EAB.ASB | As-built and O&M documentation | 5 | ENG.EWR.EAB
ENG.EWR.EAB.ASB.SUB | Submittal | 6 | ENG.EWR.EAB.ASB
ENG.EWR.EAB.ASB.APR | Approval | 6 | ENG.EWR.EAB.ASB
PRO.EWR.EAB.CCT | CCTV system | 5 | PRO.EWR.EAB
PRO.EWR.EAB.VMS | Video management and video wall | 5 | PRO.EWR.EAB
PRO.EWR.EAB.ACC | Access control and intercom | 5 | PRO.EWR.EAB
PRO.EWR.EAB.UPN | UPS, network and cabinets | 5 | PRO.EWR.EAB
PRO.EWR.EAB.LOG | FAT and logistics | 5 | PRO.EWR.EAB
CON.EWR.EAB.CIV | Civil works | 5 | CON.EWR.EAB
CON.EWR.EAB.INS | Installation | 5 | CON.EWR.EAB
COM.EWR.EAB.TST | Testing and commissioning | 5 | COM.EWR.EAB
COM.EWR.EAB.TRN | Training | 5 | COM.EWR.EAB
COM.EWR.EAB.TOA | Trial operation and acceptance | 5 | COM.EWR.EAB
ENG.NSR.NHL | Hail (NSR) | 4 | ENG.NSR
PRO.NSR.NHL | Hail (NSR) | 4 | PRO.NSR
CON.NSR.NHL | Hail (NSR) | 4 | CON.NSR
COM.NSR.NHL | Hail (NSR) | 4 | COM.NSR
ENG.NSR.NHL.SRV | Site survey and as-found verification | 5 | ENG.NSR.NHL
ENG.NSR.NHL.SRV.SUB | Submittal | 6 | ENG.NSR.NHL.SRV
ENG.NSR.NHL.SRV.APR | Approval | 6 | ENG.NSR.NHL.SRV
ENG.NSR.NHL.CNC | Concept design | 5 | ENG.NSR.NHL
ENG.NSR.NHL.CNC.SUB | Submittal | 6 | ENG.NSR.NHL.CNC
ENG.NSR.NHL.CNC.APR | Approval | 6 | ENG.NSR.NHL.CNC
ENG.NSR.NHL.PRE | Preliminary (schematic) design | 5 | ENG.NSR.NHL
ENG.NSR.NHL.PRE.SUB | Submittal | 6 | ENG.NSR.NHL.PRE
ENG.NSR.NHL.PRE.APR | Approval | 6 | ENG.NSR.NHL.PRE
ENG.NSR.NHL.DET | Detailed design | 5 | ENG.NSR.NHL
ENG.NSR.NHL.DET.SUB | Submittal | 6 | ENG.NSR.NHL.DET
ENG.NSR.NHL.DET.APR | Approval | 6 | ENG.NSR.NHL.DET
ENG.NSR.NHL.IFC | IFC and shop drawings | 5 | ENG.NSR.NHL
ENG.NSR.NHL.IFC.SUB | Submittal | 6 | ENG.NSR.NHL.IFC
ENG.NSR.NHL.IFC.APR | Approval | 6 | ENG.NSR.NHL.IFC
ENG.NSR.NHL.HCS | HCIS documentation (Stage 3 and 4) | 5 | ENG.NSR.NHL
ENG.NSR.NHL.HCS.SUB | Submittal | 6 | ENG.NSR.NHL.HCS
ENG.NSR.NHL.HCS.APR | Approval | 6 | ENG.NSR.NHL.HCS
ENG.NSR.NHL.ASB | As-built and O&M documentation | 5 | ENG.NSR.NHL
ENG.NSR.NHL.ASB.SUB | Submittal | 6 | ENG.NSR.NHL.ASB
ENG.NSR.NHL.ASB.APR | Approval | 6 | ENG.NSR.NHL.ASB
PRO.NSR.NHL.CCT | CCTV system | 5 | PRO.NSR.NHL
PRO.NSR.NHL.VMS | Video management and video wall | 5 | PRO.NSR.NHL
PRO.NSR.NHL.ACC | Access control and intercom | 5 | PRO.NSR.NHL
PRO.NSR.NHL.UPN | UPS, network and cabinets | 5 | PRO.NSR.NHL
PRO.NSR.NHL.LOG | FAT and logistics | 5 | PRO.NSR.NHL
CON.NSR.NHL.CIV | Civil works | 5 | CON.NSR.NHL
CON.NSR.NHL.INS | Installation | 5 | CON.NSR.NHL
COM.NSR.NHL.TST | Testing and commissioning | 5 | COM.NSR.NHL
COM.NSR.NHL.TRN | Training | 5 | COM.NSR.NHL
COM.NSR.NHL.TOA | Trial operation and acceptance | 5 | COM.NSR.NHL
ENG.NSR.NJF | Al Jouf (NSR) | 4 | ENG.NSR
PRO.NSR.NJF | Al Jouf (NSR) | 4 | PRO.NSR
CON.NSR.NJF | Al Jouf (NSR) | 4 | CON.NSR
COM.NSR.NJF | Al Jouf (NSR) | 4 | COM.NSR
ENG.NSR.NJF.SRV | Site survey and as-found verification | 5 | ENG.NSR.NJF
ENG.NSR.NJF.SRV.SUB | Submittal | 6 | ENG.NSR.NJF.SRV
ENG.NSR.NJF.SRV.APR | Approval | 6 | ENG.NSR.NJF.SRV
ENG.NSR.NJF.CNC | Concept design | 5 | ENG.NSR.NJF
ENG.NSR.NJF.CNC.SUB | Submittal | 6 | ENG.NSR.NJF.CNC
ENG.NSR.NJF.CNC.APR | Approval | 6 | ENG.NSR.NJF.CNC
ENG.NSR.NJF.PRE | Preliminary (schematic) design | 5 | ENG.NSR.NJF
ENG.NSR.NJF.PRE.SUB | Submittal | 6 | ENG.NSR.NJF.PRE
ENG.NSR.NJF.PRE.APR | Approval | 6 | ENG.NSR.NJF.PRE
ENG.NSR.NJF.DET | Detailed design | 5 | ENG.NSR.NJF
ENG.NSR.NJF.DET.SUB | Submittal | 6 | ENG.NSR.NJF.DET
ENG.NSR.NJF.DET.APR | Approval | 6 | ENG.NSR.NJF.DET
ENG.NSR.NJF.IFC | IFC and shop drawings | 5 | ENG.NSR.NJF
ENG.NSR.NJF.IFC.SUB | Submittal | 6 | ENG.NSR.NJF.IFC
ENG.NSR.NJF.IFC.APR | Approval | 6 | ENG.NSR.NJF.IFC
ENG.NSR.NJF.HCS | HCIS documentation (Stage 3 and 4) | 5 | ENG.NSR.NJF
ENG.NSR.NJF.HCS.SUB | Submittal | 6 | ENG.NSR.NJF.HCS
ENG.NSR.NJF.HCS.APR | Approval | 6 | ENG.NSR.NJF.HCS
ENG.NSR.NJF.ASB | As-built and O&M documentation | 5 | ENG.NSR.NJF
ENG.NSR.NJF.ASB.SUB | Submittal | 6 | ENG.NSR.NJF.ASB
ENG.NSR.NJF.ASB.APR | Approval | 6 | ENG.NSR.NJF.ASB
PRO.NSR.NJF.CCT | CCTV system | 5 | PRO.NSR.NJF
PRO.NSR.NJF.VMS | Video management and video wall | 5 | PRO.NSR.NJF
PRO.NSR.NJF.ACC | Access control and intercom | 5 | PRO.NSR.NJF
PRO.NSR.NJF.UPN | UPS, network and cabinets | 5 | PRO.NSR.NJF
PRO.NSR.NJF.LOG | FAT and logistics | 5 | PRO.NSR.NJF
CON.NSR.NJF.CIV | Civil works | 5 | CON.NSR.NJF
CON.NSR.NJF.INS | Installation | 5 | CON.NSR.NJF
COM.NSR.NJF.TST | Testing and commissioning | 5 | COM.NSR.NJF
COM.NSR.NJF.TRN | Training | 5 | COM.NSR.NJF
COM.NSR.NJF.TOA | Trial operation and acceptance | 5 | COM.NSR.NJF
ENG.NSR.NQR | Al Qurayyat (NSR) | 4 | ENG.NSR
PRO.NSR.NQR | Al Qurayyat (NSR) | 4 | PRO.NSR
CON.NSR.NQR | Al Qurayyat (NSR) | 4 | CON.NSR
COM.NSR.NQR | Al Qurayyat (NSR) | 4 | COM.NSR
ENG.NSR.NQR.SRV | Site survey and as-found verification | 5 | ENG.NSR.NQR
ENG.NSR.NQR.SRV.SUB | Submittal | 6 | ENG.NSR.NQR.SRV
ENG.NSR.NQR.SRV.APR | Approval | 6 | ENG.NSR.NQR.SRV
ENG.NSR.NQR.CNC | Concept design | 5 | ENG.NSR.NQR
ENG.NSR.NQR.CNC.SUB | Submittal | 6 | ENG.NSR.NQR.CNC
ENG.NSR.NQR.CNC.APR | Approval | 6 | ENG.NSR.NQR.CNC
ENG.NSR.NQR.PRE | Preliminary (schematic) design | 5 | ENG.NSR.NQR
ENG.NSR.NQR.PRE.SUB | Submittal | 6 | ENG.NSR.NQR.PRE
ENG.NSR.NQR.PRE.APR | Approval | 6 | ENG.NSR.NQR.PRE
ENG.NSR.NQR.DET | Detailed design | 5 | ENG.NSR.NQR
ENG.NSR.NQR.DET.SUB | Submittal | 6 | ENG.NSR.NQR.DET
ENG.NSR.NQR.DET.APR | Approval | 6 | ENG.NSR.NQR.DET
ENG.NSR.NQR.IFC | IFC and shop drawings | 5 | ENG.NSR.NQR
ENG.NSR.NQR.IFC.SUB | Submittal | 6 | ENG.NSR.NQR.IFC
ENG.NSR.NQR.IFC.APR | Approval | 6 | ENG.NSR.NQR.IFC
ENG.NSR.NQR.HCS | HCIS documentation (Stage 3 and 4) | 5 | ENG.NSR.NQR
ENG.NSR.NQR.HCS.SUB | Submittal | 6 | ENG.NSR.NQR.HCS
ENG.NSR.NQR.HCS.APR | Approval | 6 | ENG.NSR.NQR.HCS
ENG.NSR.NQR.ASB | As-built and O&M documentation | 5 | ENG.NSR.NQR
ENG.NSR.NQR.ASB.SUB | Submittal | 6 | ENG.NSR.NQR.ASB
ENG.NSR.NQR.ASB.APR | Approval | 6 | ENG.NSR.NQR.ASB
PRO.NSR.NQR.CCT | CCTV system | 5 | PRO.NSR.NQR
PRO.NSR.NQR.VMS | Video management and video wall | 5 | PRO.NSR.NQR
PRO.NSR.NQR.ACC | Access control and intercom | 5 | PRO.NSR.NQR
PRO.NSR.NQR.UPN | UPS, network and cabinets | 5 | PRO.NSR.NQR
PRO.NSR.NQR.LOG | FAT and logistics | 5 | PRO.NSR.NQR
CON.NSR.NQR.CIV | Civil works | 5 | CON.NSR.NQR
CON.NSR.NQR.INS | Installation | 5 | CON.NSR.NQR
COM.NSR.NQR.TST | Testing and commissioning | 5 | COM.NSR.NQR
COM.NSR.NQR.TRN | Training | 5 | COM.NSR.NQR
COM.NSR.NQR.TOA | Trial operation and acceptance | 5 | COM.NSR.NQR

## Relationships
Predecessor | Successor | Type | Lag (work days)
PRJ-M0000 | PRJ-A1010 | FS | 0
PRJ-M0000 | PRJ-A1020 | FS | 0
PRJ-A1020 | PRJ-A1030 | FS | 0
PRJ-M0000 | PRJ-A1040 | FS | 5
PRJ-M0000 | PRJ-A1050 | FS | 5
PRJ-A1010 | PRJ-M1100 | FS | 0
PRJ-A1030 | PRJ-M1100 | FS | 0
PRJ-A1040 | PRJ-M1100 | FS | 0
PRJ-A1050 | PRJ-M1100 | FS | 0
PRJ-M1100 | NRY-E1010 | FS | 0
PRJ-M1100 | ERY-E1010 | FS | 10
NRY-E1010 | PRJ-A2010 | FS | 0
ERY-E1010 | PRJ-A2010 | FS | 0
PRJ-A2010 | PRJ-A2020 | FS | 0
PRJ-A2020 | PRJ-M2100 | FS | 0
NRY-E1010 | NRY-E1020 | FS | 0
NRY-E1010 | NRY-E1030 | FS | 0
NRY-E1030 | NRY-E1040 | FS | 0
NRY-E1030 | NRY-E1050 | FS | 0
NRY-E1050 | NRY-E1060 | FS | 0
NRY-E1050 | NRY-E1070 | FS | 0
NRY-E1070 | NRY-E1080 | FS | 0
NRY-E1070 | NRY-E1090 | FS | 0
NRY-E1090 | NRY-E1100 | FS | 0
NRY-E1050 | NRY-E1110 | FS | 5
NRY-E1090 | NRY-E1110 | FF | 0
NRY-E1110 | NRY-E1120 | FS | 0
NRY-E1090 | NRY-E1200 | FS | 0
NRY-E1110 | NRY-E1200 | FS | 0
NRY-E1020 | NRY-E1210 | FS | 0
NRY-E1040 | NRY-E1210 | FS | 0
NRY-E1060 | NRY-E1210 | FS | 0
NRY-E1080 | NRY-E1210 | FS | 0
NRY-E1100 | NRY-E1210 | FS | 0
NRY-E1120 | NRY-E1210 | FS | 0
NRY-E1200 | NRY-E1210 | FS | 0
NRY-E1210 | NRY-P1010 | FS | 0
NRY-E1210 | NRY-P1020 | FS | 0
NRY-E1210 | NRY-P1030 | FS | 0
NRY-E1210 | NRY-P1040 | FS | 0
NRY-P1010 | NRY-P1050 | FS | 0
NRY-P1020 | NRY-P1050 | FS | 0
NRY-P1030 | NRY-P1050 | FS | 0
NRY-P1040 | NRY-P1050 | FS | 0
NRY-P1050 | NRY-P1060 | FS | 0
NRY-P1060 | NRY-P1070 | FS | 0
NRY-P1070 | NRY-P1100 | FS | 0
NRY-P1100 | NRY-C2010 | FS | 0
NRY-E1210 | NRY-C1010 | FS | 0
NRY-C2010 | NRY-C2020 | SS | 4
NRY-C1010 | NRY-C2020 | SS | 43
NRY-C1010 | NRY-C1020 | SS | 38
NRY-C2020 | NRY-C2030 | FS | 0
NRY-C1020 | NRY-C2030 | FS | 0
NRY-C2010 | NRY-C2040 | FS | 0
NRY-C2010 | NRY-C2050 | FS | 4
NRY-C2020 | NRY-C2100 | FS | 0
NRY-C2030 | NRY-C2100 | FS | 0
NRY-C2040 | NRY-C2100 | FS | 0
NRY-C2050 | NRY-C2100 | FS | 0
NRY-C1020 | NRY-C2100 | FS | 0
NRY-C2100 | NRY-T1010 | FS | 0
NRY-T1010 | NRY-T1020 | FS | 0
NRY-T1020 | NRY-T1100 | FS | 0
NRY-T1020 | NRY-T2010 | FS | 0
NRY-T1020 | NRY-T2020 | FS | 0
NRY-C2100 | NRY-E1130 | FS | 0
NRY-E1130 | NRY-E1140 | FS | 0
NRY-T1100 | NRY-T3010 | FS | 0
NRY-T2010 | NRY-T3010 | FS | 0
NRY-T2020 | NRY-T3010 | FS | 0
NRY-E1140 | NRY-T3010 | FS | 0
NRY-T3010 | NRY-T3100 | FS | 0
ERY-E1010 | ERY-E1020 | FS | 0
ERY-E1010 | ERY-E1030 | FS | 0
ERY-E1030 | ERY-E1040 | FS | 0
ERY-E1030 | ERY-E1050 | FS | 0
ERY-E1050 | ERY-E1060 | FS | 0
ERY-E1050 | ERY-E1070 | FS | 0
ERY-E1070 | ERY-E1080 | FS | 0
ERY-E1070 | ERY-E1090 | FS | 0
ERY-E1090 | ERY-E1100 | FS | 0
ERY-E1050 | ERY-E1110 | FS | 5
ERY-E1090 | ERY-E1110 | FF | 0
ERY-E1110 | ERY-E1120 | FS | 0
ERY-E1090 | ERY-E1200 | FS | 0
ERY-E1110 | ERY-E1200 | FS | 0
ERY-E1020 | ERY-E1210 | FS | 0
ERY-E1040 | ERY-E1210 | FS | 0
ERY-E1060 | ERY-E1210 | FS | 0
ERY-E1080 | ERY-E1210 | FS | 0
ERY-E1100 | ERY-E1210 | FS | 0
ERY-E1120 | ERY-E1210 | FS | 0
ERY-E1200 | ERY-E1210 | FS | 0
ERY-E1210 | ERY-P1010 | FS | 0
ERY-E1210 | ERY-P1020 | FS | 0
ERY-E1210 | ERY-P1030 | FS | 0
ERY-E1210 | ERY-P1040 | FS | 0
ERY-P1010 | ERY-P1050 | FS | 0
ERY-P1020 | ERY-P1050 | FS | 0
ERY-P1030 | ERY-P1050 | FS | 0
ERY-P1040 | ERY-P1050 | FS | 0
ERY-P1050 | ERY-P1060 | FS | 0
ERY-P1060 | ERY-P1070 | FS | 0
ERY-P1070 | ERY-P1100 | FS | 0
ERY-P1100 | ERY-C2010 | FS | 0
ERY-E1210 | ERY-C1010 | FS | 0
ERY-C2010 | ERY-C2020 | SS | 3
ERY-C1010 | ERY-C2020 | SS | 40
ERY-C1010 | ERY-C1020 | SS | 36
ERY-C2020 | ERY-C2030 | FS | 0
ERY-C1020 | ERY-C2030 | FS | 0
ERY-C2010 | ERY-C2040 | FS | 0
ERY-C2010 | ERY-C2050 | FS | 3
ERY-C2020 | ERY-C2100 | FS | 0
ERY-C2030 | ERY-C2100 | FS | 0
ERY-C2040 | ERY-C2100 | FS | 0
ERY-C2050 | ERY-C2100 | FS | 0
ERY-C1020 | ERY-C2100 | FS | 0
ERY-C2100 | ERY-T1010 | FS | 0
ERY-T1010 | ERY-T1020 | FS | 0
ERY-T1020 | ERY-T1100 | FS | 0
ERY-T1020 | ERY-T2010 | FS | 0
ERY-T1020 | ERY-T2020 | FS | 0
ERY-C2100 | ERY-E1130 | FS | 0
ERY-E1130 | ERY-E1140 | FS | 0
ERY-T1100 | ERY-T3010 | FS | 0
ERY-T2010 | ERY-T3010 | FS | 0
ERY-T2020 | ERY-T3010 | FS | 0
ERY-E1140 | ERY-T3010 | FS | 0
ERY-T3010 | ERY-T3100 | FS | 0
PRJ-M2100 | HJD-E1010 | FS | 8
HJD-E1010 | HJD-E1020 | FS | 0
HJD-E1010 | HJD-E1030 | FS | 0
HJD-E1030 | HJD-E1040 | FS | 0
HJD-E1030 | HJD-E1050 | FS | 0
HJD-E1050 | HJD-E1060 | FS | 0
HJD-E1050 | HJD-E1070 | FS | 0
HJD-E1070 | HJD-E1080 | FS | 0
HJD-E1070 | HJD-E1090 | FS | 0
HJD-E1090 | HJD-E1100 | FS | 0
HJD-E1050 | HJD-E1110 | FS | 8
HJD-E1090 | HJD-E1110 | FF | 0
HJD-E1110 | HJD-E1120 | FS | 0
HJD-E1090 | HJD-E1200 | FS | 0
HJD-E1110 | HJD-E1200 | FS | 0
HJD-E1020 | HJD-E1210 | FS | 0
HJD-E1040 | HJD-E1210 | FS | 0
HJD-E1060 | HJD-E1210 | FS | 0
HJD-E1080 | HJD-E1210 | FS | 0
HJD-E1100 | HJD-E1210 | FS | 0
HJD-E1120 | HJD-E1210 | FS | 0
HJD-E1200 | HJD-E1210 | FS | 0
HJD-E1210 | HJD-P1010 | FS | 0
HJD-E1210 | HJD-P1020 | FS | 0
HJD-E1210 | HJD-P1030 | FS | 0
HJD-E1210 | HJD-P1040 | FS | 0
HJD-P1010 | HJD-P1050 | FS | 0
HJD-P1020 | HJD-P1050 | FS | 0
HJD-P1030 | HJD-P1050 | FS | 0
HJD-P1040 | HJD-P1050 | FS | 0
HJD-P1050 | HJD-P1060 | FS | 0
HJD-P1060 | HJD-P1070 | FS | 0
HJD-P1070 | HJD-P1100 | FS | 0
HJD-P1100 | HJD-C2010 | FS | 0
HJD-E1210 | HJD-C1010 | FS | 0
HJD-C2010 | HJD-C2020 | SS | 9
HJD-C1010 | HJD-C2020 | SS | 33
HJD-C1010 | HJD-C1020 | SS | 29
HJD-C2020 | HJD-C2030 | FS | 0
HJD-C1020 | HJD-C2030 | FS | 0
HJD-C2010 | HJD-C2040 | FS | 0
HJD-C2010 | HJD-C2050 | FS | 9
HJD-C2020 | HJD-C2100 | FS | 0
HJD-C2030 | HJD-C2100 | FS | 0
HJD-C2040 | HJD-C2100 | FS | 0
HJD-C2050 | HJD-C2100 | FS | 0
HJD-C1020 | HJD-C2100 | FS | 0
HJD-C2100 | HJD-T1010 | FS | 0
HJD-T1010 | HJD-T1020 | FS | 0
HJD-T1020 | HJD-T1100 | FS | 0
HJD-T1020 | HJD-T2010 | FS | 0
HJD-T1020 | HJD-T2020 | FS | 0
HJD-C2100 | HJD-E1130 | FS | 0
HJD-E1130 | HJD-E1140 | FS | 0
HJD-T1100 | HJD-T3010 | FS | 0
HJD-T2010 | HJD-T3010 | FS | 0
HJD-T2020 | HJD-T3010 | FS | 0
HJD-E1140 | HJD-T3010 | FS | 0
HJD-T3010 | HJD-T3100 | FS | 0
PRJ-M2100 | EDM-E1010 | FS | 78
EDM-E1010 | EDM-E1020 | FS | 0
EDM-E1010 | EDM-E1030 | FS | 0
EDM-E1030 | EDM-E1040 | FS | 0
EDM-E1030 | EDM-E1050 | FS | 0
EDM-E1050 | EDM-E1060 | FS | 0
EDM-E1050 | EDM-E1070 | FS | 0
EDM-E1070 | EDM-E1080 | FS | 0
EDM-E1070 | EDM-E1090 | FS | 0
EDM-E1090 | EDM-E1100 | FS | 0
EDM-E1050 | EDM-E1110 | FS | 5
EDM-E1090 | EDM-E1110 | FF | 0
EDM-E1110 | EDM-E1120 | FS | 0
EDM-E1090 | EDM-E1200 | FS | 0
EDM-E1110 | EDM-E1200 | FS | 0
EDM-E1020 | EDM-E1210 | FS | 0
EDM-E1040 | EDM-E1210 | FS | 0
EDM-E1060 | EDM-E1210 | FS | 0
EDM-E1080 | EDM-E1210 | FS | 0
EDM-E1100 | EDM-E1210 | FS | 0
EDM-E1120 | EDM-E1210 | FS | 0
EDM-E1200 | EDM-E1210 | FS | 0
EDM-E1210 | EDM-P1010 | FS | 0
EDM-E1210 | EDM-P1020 | FS | 0
EDM-E1210 | EDM-P1030 | FS | 0
EDM-E1210 | EDM-P1040 | FS | 0
EDM-P1010 | EDM-P1050 | FS | 0
EDM-P1020 | EDM-P1050 | FS | 0
EDM-P1030 | EDM-P1050 | FS | 0
EDM-P1040 | EDM-P1050 | FS | 0
EDM-P1050 | EDM-P1060 | FS | 0
EDM-P1060 | EDM-P1070 | FS | 0
EDM-P1070 | EDM-P1100 | FS | 0
EDM-P1100 | EDM-C2010 | FS | 0
EDM-E1210 | EDM-C1010 | FS | 0
EDM-C2010 | EDM-C2020 | SS | 3
EDM-C1010 | EDM-C2020 | SS | 40
EDM-C1010 | EDM-C1020 | SS | 36
EDM-C2020 | EDM-C2030 | FS | 0
EDM-C1020 | EDM-C2030 | FS | 0
EDM-C2010 | EDM-C2040 | FS | 0
EDM-C2010 | EDM-C2050 | FS | 3
EDM-C2020 | EDM-C2100 | FS | 0
EDM-C2030 | EDM-C2100 | FS | 0
EDM-C2040 | EDM-C2100 | FS | 0
EDM-C2050 | EDM-C2100 | FS | 0
EDM-C1020 | EDM-C2100 | FS | 0
EDM-C2100 | EDM-T1010 | FS | 0
EDM-T1010 | EDM-T1020 | FS | 0
EDM-T1020 | EDM-T1100 | FS | 0
EDM-T1020 | EDM-T2010 | FS | 0
EDM-T1020 | EDM-T2020 | FS | 0
EDM-C2100 | EDM-E1130 | FS | 0
EDM-E1130 | EDM-E1140 | FS | 0
EDM-T1100 | EDM-T3010 | FS | 0
EDM-T2010 | EDM-T3010 | FS | 0
EDM-T2020 | EDM-T3010 | FS | 0
EDM-E1140 | EDM-T3010 | FS | 0
EDM-T3010 | EDM-T3100 | FS | 0
PRJ-M2100 | NQS-E1010 | FS | 118
NQS-E1010 | NQS-E1020 | FS | 0
NQS-E1010 | NQS-E1030 | FS | 0
NQS-E1030 | NQS-E1040 | FS | 0
NQS-E1030 | NQS-E1050 | FS | 0
NQS-E1050 | NQS-E1060 | FS | 0
NQS-E1050 | NQS-E1070 | FS | 0
NQS-E1070 | NQS-E1080 | FS | 0
NQS-E1070 | NQS-E1090 | FS | 0
NQS-E1090 | NQS-E1100 | FS | 0
NQS-E1050 | NQS-E1110 | FS | 5
NQS-E1090 | NQS-E1110 | FF | 0
NQS-E1110 | NQS-E1120 | FS | 0
NQS-E1090 | NQS-E1200 | FS | 0
NQS-E1110 | NQS-E1200 | FS | 0
NQS-E1020 | NQS-E1210 | FS | 0
NQS-E1040 | NQS-E1210 | FS | 0
NQS-E1060 | NQS-E1210 | FS | 0
NQS-E1080 | NQS-E1210 | FS | 0
NQS-E1100 | NQS-E1210 | FS | 0
NQS-E1120 | NQS-E1210 | FS | 0
NQS-E1200 | NQS-E1210 | FS | 0
NQS-E1210 | NQS-P1010 | FS | 0
NQS-E1210 | NQS-P1020 | FS | 0
NQS-E1210 | NQS-P1030 | FS | 0
NQS-E1210 | NQS-P1040 | FS | 0
NQS-P1010 | NQS-P1050 | FS | 0
NQS-P1020 | NQS-P1050 | FS | 0
NQS-P1030 | NQS-P1050 | FS | 0
NQS-P1040 | NQS-P1050 | FS | 0
NQS-P1050 | NQS-P1060 | FS | 0
NQS-P1060 | NQS-P1070 | FS | 0
NQS-P1070 | NQS-P1100 | FS | 0
NQS-P1100 | NQS-C2010 | FS | 0
NQS-E1210 | NQS-C1010 | FS | 0
NQS-C2010 | NQS-C2020 | SS | 4
NQS-C1010 | NQS-C2020 | SS | 43
NQS-C1010 | NQS-C1020 | SS | 38
NQS-C2020 | NQS-C2030 | FS | 0
NQS-C1020 | NQS-C2030 | FS | 0
NQS-C2010 | NQS-C2040 | FS | 0
NQS-C2010 | NQS-C2050 | FS | 4
NQS-C2020 | NQS-C2100 | FS | 0
NQS-C2030 | NQS-C2100 | FS | 0
NQS-C2040 | NQS-C2100 | FS | 0
NQS-C2050 | NQS-C2100 | FS | 0
NQS-C1020 | NQS-C2100 | FS | 0
NQS-C2100 | NQS-T1010 | FS | 0
NQS-T1010 | NQS-T1020 | FS | 0
NQS-T1020 | NQS-T1100 | FS | 0
NQS-T1020 | NQS-T2010 | FS | 0
NQS-T1020 | NQS-T2020 | FS | 0
NQS-C2100 | NQS-E1130 | FS | 0
NQS-E1130 | NQS-E1140 | FS | 0
NQS-T1100 | NQS-T3010 | FS | 0
NQS-T2010 | NQS-T3010 | FS | 0
NQS-T2020 | NQS-T3010 | FS | 0
NQS-E1140 | NQS-T3010 | FS | 0
NQS-T3010 | NQS-T3100 | FS | 0
PRJ-M2100 | EHF-E1010 | FS | 118
EHF-E1010 | EHF-E1020 | FS | 0
EHF-E1010 | EHF-E1030 | FS | 0
EHF-E1030 | EHF-E1040 | FS | 0
EHF-E1030 | EHF-E1050 | FS | 0
EHF-E1050 | EHF-E1060 | FS | 0
EHF-E1050 | EHF-E1070 | FS | 0
EHF-E1070 | EHF-E1080 | FS | 0
EHF-E1070 | EHF-E1090 | FS | 0
EHF-E1090 | EHF-E1100 | FS | 0
EHF-E1050 | EHF-E1110 | FS | 5
EHF-E1090 | EHF-E1110 | FF | 0
EHF-E1110 | EHF-E1120 | FS | 0
EHF-E1090 | EHF-E1200 | FS | 0
EHF-E1110 | EHF-E1200 | FS | 0
EHF-E1020 | EHF-E1210 | FS | 0
EHF-E1040 | EHF-E1210 | FS | 0
EHF-E1060 | EHF-E1210 | FS | 0
EHF-E1080 | EHF-E1210 | FS | 0
EHF-E1100 | EHF-E1210 | FS | 0
EHF-E1120 | EHF-E1210 | FS | 0
EHF-E1200 | EHF-E1210 | FS | 0
EHF-E1210 | EHF-P1010 | FS | 0
EHF-E1210 | EHF-P1020 | FS | 0
EHF-E1210 | EHF-P1030 | FS | 0
EHF-E1210 | EHF-P1040 | FS | 0
EHF-P1010 | EHF-P1050 | FS | 0
EHF-P1020 | EHF-P1050 | FS | 0
EHF-P1030 | EHF-P1050 | FS | 0
EHF-P1040 | EHF-P1050 | FS | 0
EHF-P1050 | EHF-P1060 | FS | 0
EHF-P1060 | EHF-P1070 | FS | 0
EHF-P1070 | EHF-P1100 | FS | 0
EHF-P1100 | EHF-C2010 | FS | 0
EHF-E1210 | EHF-C1010 | FS | 0
EHF-C2010 | EHF-C2020 | SS | 3
EHF-C1010 | EHF-C2020 | SS | 38
EHF-C1010 | EHF-C1020 | SS | 34
EHF-C2020 | EHF-C2030 | FS | 0
EHF-C1020 | EHF-C2030 | FS | 0
EHF-C2010 | EHF-C2040 | FS | 0
EHF-C2010 | EHF-C2050 | FS | 3
EHF-C2020 | EHF-C2100 | FS | 0
EHF-C2030 | EHF-C2100 | FS | 0
EHF-C2040 | EHF-C2100 | FS | 0
EHF-C2050 | EHF-C2100 | FS | 0
EHF-C1020 | EHF-C2100 | FS | 0
EHF-C2100 | EHF-T1010 | FS | 0
EHF-T1010 | EHF-T1020 | FS | 0
EHF-T1020 | EHF-T1100 | FS | 0
EHF-T1020 | EHF-T2010 | FS | 0
EHF-T1020 | EHF-T2020 | FS | 0
EHF-C2100 | EHF-E1130 | FS | 0
EHF-E1130 | EHF-E1140 | FS | 0
EHF-T1100 | EHF-T3010 | FS | 0
EHF-T2010 | EHF-T3010 | FS | 0
EHF-T2020 | EHF-T3010 | FS | 0
EHF-E1140 | EHF-T3010 | FS | 0
EHF-T3010 | EHF-T3100 | FS | 0
PRJ-M2100 | NMJ-E1010 | FS | 153
NMJ-E1010 | NMJ-E1020 | FS | 0
NMJ-E1010 | NMJ-E1030 | FS | 0
NMJ-E1030 | NMJ-E1040 | FS | 0
NMJ-E1030 | NMJ-E1050 | FS | 0
NMJ-E1050 | NMJ-E1060 | FS | 0
NMJ-E1050 | NMJ-E1070 | FS | 0
NMJ-E1070 | NMJ-E1080 | FS | 0
NMJ-E1070 | NMJ-E1090 | FS | 0
NMJ-E1090 | NMJ-E1100 | FS | 0
NMJ-E1050 | NMJ-E1110 | FS | 5
NMJ-E1090 | NMJ-E1110 | FF | 0
NMJ-E1110 | NMJ-E1120 | FS | 0
NMJ-E1090 | NMJ-E1200 | FS | 0
NMJ-E1110 | NMJ-E1200 | FS | 0
NMJ-E1020 | NMJ-E1210 | FS | 0
NMJ-E1040 | NMJ-E1210 | FS | 0
NMJ-E1060 | NMJ-E1210 | FS | 0
NMJ-E1080 | NMJ-E1210 | FS | 0
NMJ-E1100 | NMJ-E1210 | FS | 0
NMJ-E1120 | NMJ-E1210 | FS | 0
NMJ-E1200 | NMJ-E1210 | FS | 0
NMJ-E1210 | NMJ-P1010 | FS | 0
NMJ-E1210 | NMJ-P1020 | FS | 0
NMJ-E1210 | NMJ-P1030 | FS | 0
NMJ-E1210 | NMJ-P1040 | FS | 0
NMJ-P1010 | NMJ-P1050 | FS | 0
NMJ-P1020 | NMJ-P1050 | FS | 0
NMJ-P1030 | NMJ-P1050 | FS | 0
NMJ-P1040 | NMJ-P1050 | FS | 0
NMJ-P1050 | NMJ-P1060 | FS | 0
NMJ-P1060 | NMJ-P1070 | FS | 0
NMJ-P1070 | NMJ-P1100 | FS | 0
NMJ-P1100 | NMJ-C2010 | FS | 0
NMJ-E1210 | NMJ-C1010 | FS | 0
NMJ-C2010 | NMJ-C2020 | SS | 4
NMJ-C1010 | NMJ-C2020 | SS | 43
NMJ-C1010 | NMJ-C1020 | SS | 38
NMJ-C2020 | NMJ-C2030 | FS | 0
NMJ-C1020 | NMJ-C2030 | FS | 0
NMJ-C2010 | NMJ-C2040 | FS | 0
NMJ-C2010 | NMJ-C2050 | FS | 4
NMJ-C2020 | NMJ-C2100 | FS | 0
NMJ-C2030 | NMJ-C2100 | FS | 0
NMJ-C2040 | NMJ-C2100 | FS | 0
NMJ-C2050 | NMJ-C2100 | FS | 0
NMJ-C1020 | NMJ-C2100 | FS | 0
NMJ-C2100 | NMJ-T1010 | FS | 0
NMJ-T1010 | NMJ-T1020 | FS | 0
NMJ-T1020 | NMJ-T1100 | FS | 0
NMJ-T1020 | NMJ-T2010 | FS | 0
NMJ-T1020 | NMJ-T2020 | FS | 0
NMJ-C2100 | NMJ-E1130 | FS | 0
NMJ-E1130 | NMJ-E1140 | FS | 0
NMJ-T1100 | NMJ-T3010 | FS | 0
NMJ-T2010 | NMJ-T3010 | FS | 0
NMJ-T2020 | NMJ-T3010 | FS | 0
NMJ-E1140 | NMJ-T3010 | FS | 0
NMJ-T3010 | NMJ-T3100 | FS | 0
PRJ-M2100 | HMK-E1010 | FS | 153
HMK-E1010 | HMK-E1020 | FS | 0
HMK-E1010 | HMK-E1030 | FS | 0
HMK-E1030 | HMK-E1040 | FS | 0
HMK-E1030 | HMK-E1050 | FS | 0
HMK-E1050 | HMK-E1060 | FS | 0
HMK-E1050 | HMK-E1070 | FS | 0
HMK-E1070 | HMK-E1080 | FS | 0
HMK-E1070 | HMK-E1090 | FS | 0
HMK-E1090 | HMK-E1100 | FS | 0
HMK-E1050 | HMK-E1110 | FS | 8
HMK-E1090 | HMK-E1110 | FF | 0
HMK-E1110 | HMK-E1120 | FS | 0
HMK-E1090 | HMK-E1200 | FS | 0
HMK-E1110 | HMK-E1200 | FS | 0
HMK-E1020 | HMK-E1210 | FS | 0
HMK-E1040 | HMK-E1210 | FS | 0
HMK-E1060 | HMK-E1210 | FS | 0
HMK-E1080 | HMK-E1210 | FS | 0
HMK-E1100 | HMK-E1210 | FS | 0
HMK-E1120 | HMK-E1210 | FS | 0
HMK-E1200 | HMK-E1210 | FS | 0
HMK-E1210 | HMK-P1010 | FS | 0
HMK-E1210 | HMK-P1020 | FS | 0
HMK-E1210 | HMK-P1030 | FS | 0
HMK-E1210 | HMK-P1040 | FS | 0
HMK-P1010 | HMK-P1050 | FS | 0
HMK-P1020 | HMK-P1050 | FS | 0
HMK-P1030 | HMK-P1050 | FS | 0
HMK-P1040 | HMK-P1050 | FS | 0
HMK-P1050 | HMK-P1060 | FS | 0
HMK-P1060 | HMK-P1070 | FS | 0
HMK-P1070 | HMK-P1100 | FS | 0
HMK-P1100 | HMK-C2010 | FS | 0
HMK-E1210 | HMK-C1010 | FS | 0
HMK-C2010 | HMK-C2020 | SS | 11
HMK-C1010 | HMK-C2020 | SS | 35
HMK-C1010 | HMK-C1020 | SS | 32
HMK-C2020 | HMK-C2030 | FS | 0
HMK-C1020 | HMK-C2030 | FS | 0
HMK-C2010 | HMK-C2040 | FS | 0
HMK-C2010 | HMK-C2050 | FS | 11
HMK-C2020 | HMK-C2100 | FS | 0
HMK-C2030 | HMK-C2100 | FS | 0
HMK-C2040 | HMK-C2100 | FS | 0
HMK-C2050 | HMK-C2100 | FS | 0
HMK-C1020 | HMK-C2100 | FS | 0
HMK-C2100 | HMK-T1010 | FS | 0
HMK-T1010 | HMK-T1020 | FS | 0
HMK-T1020 | HMK-T1100 | FS | 0
HMK-T1020 | HMK-T2010 | FS | 0
HMK-T1020 | HMK-T2020 | FS | 0
HMK-C2100 | HMK-E1130 | FS | 0
HMK-E1130 | HMK-E1140 | FS | 0
HMK-T1100 | HMK-T3010 | FS | 0
HMK-T2010 | HMK-T3010 | FS | 0
HMK-T2020 | HMK-T3010 | FS | 0
HMK-E1140 | HMK-T3010 | FS | 0
HMK-T3010 | HMK-T3100 | FS | 0
PRJ-M2100 | HKA-E1010 | FS | 241
HKA-E1010 | HKA-E1020 | FS | 0
HKA-E1010 | HKA-E1030 | FS | 0
HKA-E1030 | HKA-E1040 | FS | 0
HKA-E1030 | HKA-E1050 | FS | 0
HKA-E1050 | HKA-E1060 | FS | 0
HKA-E1050 | HKA-E1070 | FS | 0
HKA-E1070 | HKA-E1080 | FS | 0
HKA-E1070 | HKA-E1090 | FS | 0
HKA-E1090 | HKA-E1100 | FS | 0
HKA-E1050 | HKA-E1110 | FS | 8
HKA-E1090 | HKA-E1110 | FF | 0
HKA-E1110 | HKA-E1120 | FS | 0
HKA-E1090 | HKA-E1200 | FS | 0
HKA-E1110 | HKA-E1200 | FS | 0
HKA-E1020 | HKA-E1210 | FS | 0
HKA-E1040 | HKA-E1210 | FS | 0
HKA-E1060 | HKA-E1210 | FS | 0
HKA-E1080 | HKA-E1210 | FS | 0
HKA-E1100 | HKA-E1210 | FS | 0
HKA-E1120 | HKA-E1210 | FS | 0
HKA-E1200 | HKA-E1210 | FS | 0
HKA-E1210 | HKA-P1010 | FS | 0
HKA-E1210 | HKA-P1020 | FS | 0
HKA-E1210 | HKA-P1030 | FS | 0
HKA-E1210 | HKA-P1040 | FS | 0
HKA-P1010 | HKA-P1050 | FS | 0
HKA-P1020 | HKA-P1050 | FS | 0
HKA-P1030 | HKA-P1050 | FS | 0
HKA-P1040 | HKA-P1050 | FS | 0
HKA-P1050 | HKA-P1060 | FS | 0
HKA-P1060 | HKA-P1070 | FS | 0
HKA-P1070 | HKA-P1100 | FS | 0
HKA-P1100 | HKA-C2010 | FS | 0
HKA-E1210 | HKA-C1010 | FS | 0
HKA-C2010 | HKA-C2020 | SS | 7
HKA-C1010 | HKA-C2020 | SS | 23
HKA-C1010 | HKA-C1020 | SS | 20
HKA-C2020 | HKA-C2030 | FS | 0
HKA-C1020 | HKA-C2030 | FS | 0
HKA-C2010 | HKA-C2040 | FS | 0
HKA-C2010 | HKA-C2050 | FS | 7
HKA-C2020 | HKA-C2100 | FS | 0
HKA-C2030 | HKA-C2100 | FS | 0
HKA-C2040 | HKA-C2100 | FS | 0
HKA-C2050 | HKA-C2100 | FS | 0
HKA-C1020 | HKA-C2100 | FS | 0
HKA-C2100 | HKA-T1010 | FS | 0
HKA-T1010 | HKA-T1020 | FS | 0
HKA-T1020 | HKA-T1100 | FS | 0
HKA-T1020 | HKA-T2010 | FS | 0
HKA-T1020 | HKA-T2020 | FS | 0
HKA-C2100 | HKA-E1130 | FS | 0
HKA-E1130 | HKA-E1140 | FS | 0
HKA-T1100 | HKA-T3010 | FS | 0
HKA-T2010 | HKA-T3010 | FS | 0
HKA-T2020 | HKA-T3010 | FS | 0
HKA-E1140 | HKA-T3010 | FS | 0
HKA-T3010 | HKA-T3100 | FS | 0
PRJ-M2100 | HMD-E1010 | FS | 241
HMD-E1010 | HMD-E1020 | FS | 0
HMD-E1010 | HMD-E1030 | FS | 0
HMD-E1030 | HMD-E1040 | FS | 0
HMD-E1030 | HMD-E1050 | FS | 0
HMD-E1050 | HMD-E1060 | FS | 0
HMD-E1050 | HMD-E1070 | FS | 0
HMD-E1070 | HMD-E1080 | FS | 0
HMD-E1070 | HMD-E1090 | FS | 0
HMD-E1090 | HMD-E1100 | FS | 0
HMD-E1050 | HMD-E1110 | FS | 8
HMD-E1090 | HMD-E1110 | FF | 0
HMD-E1110 | HMD-E1120 | FS | 0
HMD-E1090 | HMD-E1200 | FS | 0
HMD-E1110 | HMD-E1200 | FS | 0
HMD-E1020 | HMD-E1210 | FS | 0
HMD-E1040 | HMD-E1210 | FS | 0
HMD-E1060 | HMD-E1210 | FS | 0
HMD-E1080 | HMD-E1210 | FS | 0
HMD-E1100 | HMD-E1210 | FS | 0
HMD-E1120 | HMD-E1210 | FS | 0
HMD-E1200 | HMD-E1210 | FS | 0
HMD-E1210 | HMD-P1010 | FS | 0
HMD-E1210 | HMD-P1020 | FS | 0
HMD-E1210 | HMD-P1030 | FS | 0
HMD-E1210 | HMD-P1040 | FS | 0
HMD-P1010 | HMD-P1050 | FS | 0
HMD-P1020 | HMD-P1050 | FS | 0
HMD-P1030 | HMD-P1050 | FS | 0
HMD-P1040 | HMD-P1050 | FS | 0
HMD-P1050 | HMD-P1060 | FS | 0
HMD-P1060 | HMD-P1070 | FS | 0
HMD-P1070 | HMD-P1100 | FS | 0
HMD-P1100 | HMD-C2010 | FS | 0
HMD-E1210 | HMD-C1010 | FS | 0
HMD-C2010 | HMD-C2020 | SS | 7
HMD-C1010 | HMD-C2020 | SS | 25
HMD-C1010 | HMD-C1020 | SS | 23
HMD-C2020 | HMD-C2030 | FS | 0
HMD-C1020 | HMD-C2030 | FS | 0
HMD-C2010 | HMD-C2040 | FS | 0
HMD-C2010 | HMD-C2050 | FS | 7
HMD-C2020 | HMD-C2100 | FS | 0
HMD-C2030 | HMD-C2100 | FS | 0
HMD-C2040 | HMD-C2100 | FS | 0
HMD-C2050 | HMD-C2100 | FS | 0
HMD-C1020 | HMD-C2100 | FS | 0
HMD-C2100 | HMD-T1010 | FS | 0
HMD-T1010 | HMD-T1020 | FS | 0
HMD-T1020 | HMD-T1100 | FS | 0
HMD-T1020 | HMD-T2010 | FS | 0
HMD-T1020 | HMD-T2020 | FS | 0
HMD-C2100 | HMD-E1130 | FS | 0
HMD-E1130 | HMD-E1140 | FS | 0
HMD-T1100 | HMD-T3010 | FS | 0
HMD-T2010 | HMD-T3010 | FS | 0
HMD-T2020 | HMD-T3010 | FS | 0
HMD-E1140 | HMD-T3010 | FS | 0
HMD-T3010 | HMD-T3100 | FS | 0
PRJ-M2100 | EAB-E1010 | FS | 276
EAB-E1010 | EAB-E1020 | FS | 0
EAB-E1010 | EAB-E1030 | FS | 0
EAB-E1030 | EAB-E1040 | FS | 0
EAB-E1030 | EAB-E1050 | FS | 0
EAB-E1050 | EAB-E1060 | FS | 0
EAB-E1050 | EAB-E1070 | FS | 0
EAB-E1070 | EAB-E1080 | FS | 0
EAB-E1070 | EAB-E1090 | FS | 0
EAB-E1090 | EAB-E1100 | FS | 0
EAB-E1050 | EAB-E1110 | FS | 5
EAB-E1090 | EAB-E1110 | FF | 0
EAB-E1110 | EAB-E1120 | FS | 0
EAB-E1090 | EAB-E1200 | FS | 0
EAB-E1110 | EAB-E1200 | FS | 0
EAB-E1020 | EAB-E1210 | FS | 0
EAB-E1040 | EAB-E1210 | FS | 0
EAB-E1060 | EAB-E1210 | FS | 0
EAB-E1080 | EAB-E1210 | FS | 0
EAB-E1100 | EAB-E1210 | FS | 0
EAB-E1120 | EAB-E1210 | FS | 0
EAB-E1200 | EAB-E1210 | FS | 0
EAB-E1210 | EAB-P1010 | FS | 0
EAB-E1210 | EAB-P1020 | FS | 0
EAB-E1210 | EAB-P1030 | FS | 0
EAB-E1210 | EAB-P1040 | FS | 0
EAB-P1010 | EAB-P1050 | FS | 0
EAB-P1020 | EAB-P1050 | FS | 0
EAB-P1030 | EAB-P1050 | FS | 0
EAB-P1040 | EAB-P1050 | FS | 0
EAB-P1050 | EAB-P1060 | FS | 0
EAB-P1060 | EAB-P1070 | FS | 0
EAB-P1070 | EAB-P1100 | FS | 0
EAB-P1100 | EAB-C2010 | FS | 0
EAB-E1210 | EAB-C1010 | FS | 0
EAB-C2010 | EAB-C2020 | SS | 3
EAB-C1010 | EAB-C2020 | SS | 28
EAB-C1010 | EAB-C1020 | SS | 25
EAB-C2020 | EAB-C2030 | FS | 0
EAB-C1020 | EAB-C2030 | FS | 0
EAB-C2010 | EAB-C2040 | FS | 0
EAB-C2010 | EAB-C2050 | FS | 3
EAB-C2020 | EAB-C2100 | FS | 0
EAB-C2030 | EAB-C2100 | FS | 0
EAB-C2040 | EAB-C2100 | FS | 0
EAB-C2050 | EAB-C2100 | FS | 0
EAB-C1020 | EAB-C2100 | FS | 0
EAB-C2100 | EAB-T1010 | FS | 0
EAB-T1010 | EAB-T1020 | FS | 0
EAB-T1020 | EAB-T1100 | FS | 0
EAB-T1020 | EAB-T2010 | FS | 0
EAB-T1020 | EAB-T2020 | FS | 0
EAB-C2100 | EAB-E1130 | FS | 0
EAB-E1130 | EAB-E1140 | FS | 0
EAB-T1100 | EAB-T3010 | FS | 0
EAB-T2010 | EAB-T3010 | FS | 0
EAB-T2020 | EAB-T3010 | FS | 0
EAB-E1140 | EAB-T3010 | FS | 0
EAB-T3010 | EAB-T3100 | FS | 0
PRJ-M2100 | NHL-E1010 | FS | 294
NHL-E1010 | NHL-E1020 | FS | 0
NHL-E1010 | NHL-E1030 | FS | 0
NHL-E1030 | NHL-E1040 | FS | 0
NHL-E1030 | NHL-E1050 | FS | 0
NHL-E1050 | NHL-E1060 | FS | 0
NHL-E1050 | NHL-E1070 | FS | 0
NHL-E1070 | NHL-E1080 | FS | 0
NHL-E1070 | NHL-E1090 | FS | 0
NHL-E1090 | NHL-E1100 | FS | 0
NHL-E1050 | NHL-E1110 | FS | 5
NHL-E1090 | NHL-E1110 | FF | 0
NHL-E1110 | NHL-E1120 | FS | 0
NHL-E1090 | NHL-E1200 | FS | 0
NHL-E1110 | NHL-E1200 | FS | 0
NHL-E1020 | NHL-E1210 | FS | 0
NHL-E1040 | NHL-E1210 | FS | 0
NHL-E1060 | NHL-E1210 | FS | 0
NHL-E1080 | NHL-E1210 | FS | 0
NHL-E1100 | NHL-E1210 | FS | 0
NHL-E1120 | NHL-E1210 | FS | 0
NHL-E1200 | NHL-E1210 | FS | 0
NHL-E1210 | NHL-P1010 | FS | 0
NHL-E1210 | NHL-P1020 | FS | 0
NHL-E1210 | NHL-P1030 | FS | 0
NHL-E1210 | NHL-P1040 | FS | 0
NHL-P1010 | NHL-P1050 | FS | 0
NHL-P1020 | NHL-P1050 | FS | 0
NHL-P1030 | NHL-P1050 | FS | 0
NHL-P1040 | NHL-P1050 | FS | 0
NHL-P1050 | NHL-P1060 | FS | 0
NHL-P1060 | NHL-P1070 | FS | 0
NHL-P1070 | NHL-P1100 | FS | 0
NHL-P1100 | NHL-C2010 | FS | 0
NHL-E1210 | NHL-C1010 | FS | 0
NHL-C2010 | NHL-C2020 | SS | 4
NHL-C1010 | NHL-C2020 | SS | 43
NHL-C1010 | NHL-C1020 | SS | 38
NHL-C2020 | NHL-C2030 | FS | 0
NHL-C1020 | NHL-C2030 | FS | 0
NHL-C2010 | NHL-C2040 | FS | 0
NHL-C2010 | NHL-C2050 | FS | 4
NHL-C2020 | NHL-C2100 | FS | 0
NHL-C2030 | NHL-C2100 | FS | 0
NHL-C2040 | NHL-C2100 | FS | 0
NHL-C2050 | NHL-C2100 | FS | 0
NHL-C1020 | NHL-C2100 | FS | 0
NHL-C2100 | NHL-T1010 | FS | 0
NHL-T1010 | NHL-T1020 | FS | 0
NHL-T1020 | NHL-T1100 | FS | 0
NHL-T1020 | NHL-T2010 | FS | 0
NHL-T1020 | NHL-T2020 | FS | 0
NHL-C2100 | NHL-E1130 | FS | 0
NHL-E1130 | NHL-E1140 | FS | 0
NHL-T1100 | NHL-T3010 | FS | 0
NHL-T2010 | NHL-T3010 | FS | 0
NHL-T2020 | NHL-T3010 | FS | 0
NHL-E1140 | NHL-T3010 | FS | 0
NHL-T3010 | NHL-T3100 | FS | 0
PRJ-M2100 | NJF-E1010 | FS | 347
NJF-E1010 | NJF-E1020 | FS | 0
NJF-E1010 | NJF-E1030 | FS | 0
NJF-E1030 | NJF-E1040 | FS | 0
NJF-E1030 | NJF-E1050 | FS | 0
NJF-E1050 | NJF-E1060 | FS | 0
NJF-E1050 | NJF-E1070 | FS | 0
NJF-E1070 | NJF-E1080 | FS | 0
NJF-E1070 | NJF-E1090 | FS | 0
NJF-E1090 | NJF-E1100 | FS | 0
NJF-E1050 | NJF-E1110 | FS | 5
NJF-E1090 | NJF-E1110 | FF | 0
NJF-E1110 | NJF-E1120 | FS | 0
NJF-E1090 | NJF-E1200 | FS | 0
NJF-E1110 | NJF-E1200 | FS | 0
NJF-E1020 | NJF-E1210 | FS | 0
NJF-E1040 | NJF-E1210 | FS | 0
NJF-E1060 | NJF-E1210 | FS | 0
NJF-E1080 | NJF-E1210 | FS | 0
NJF-E1100 | NJF-E1210 | FS | 0
NJF-E1120 | NJF-E1210 | FS | 0
NJF-E1200 | NJF-E1210 | FS | 0
NJF-E1210 | NJF-P1010 | FS | 0
NJF-E1210 | NJF-P1020 | FS | 0
NJF-E1210 | NJF-P1030 | FS | 0
NJF-E1210 | NJF-P1040 | FS | 0
NJF-P1010 | NJF-P1050 | FS | 0
NJF-P1020 | NJF-P1050 | FS | 0
NJF-P1030 | NJF-P1050 | FS | 0
NJF-P1040 | NJF-P1050 | FS | 0
NJF-P1050 | NJF-P1060 | FS | 0
NJF-P1060 | NJF-P1070 | FS | 0
NJF-P1070 | NJF-P1100 | FS | 0
NJF-P1100 | NJF-C2010 | FS | 0
NJF-E1210 | NJF-C1010 | FS | 0
NJF-C2010 | NJF-C2020 | SS | 4
NJF-C1010 | NJF-C2020 | SS | 43
NJF-C1010 | NJF-C1020 | SS | 38
NJF-C2020 | NJF-C2030 | FS | 0
NJF-C1020 | NJF-C2030 | FS | 0
NJF-C2010 | NJF-C2040 | FS | 0
NJF-C2010 | NJF-C2050 | FS | 4
NJF-C2020 | NJF-C2100 | FS | 0
NJF-C2030 | NJF-C2100 | FS | 0
NJF-C2040 | NJF-C2100 | FS | 0
NJF-C2050 | NJF-C2100 | FS | 0
NJF-C1020 | NJF-C2100 | FS | 0
NJF-C2100 | NJF-T1010 | FS | 0
NJF-T1010 | NJF-T1020 | FS | 0
NJF-T1020 | NJF-T1100 | FS | 0
NJF-T1020 | NJF-T2010 | FS | 0
NJF-T1020 | NJF-T2020 | FS | 0
NJF-C2100 | NJF-E1130 | FS | 0
NJF-E1130 | NJF-E1140 | FS | 0
NJF-T1100 | NJF-T3010 | FS | 0
NJF-T2010 | NJF-T3010 | FS | 0
NJF-T2020 | NJF-T3010 | FS | 0
NJF-E1140 | NJF-T3010 | FS | 0
NJF-T3010 | NJF-T3100 | FS | 0
PRJ-M2100 | NQR-E1010 | FS | 382
NQR-E1010 | NQR-E1020 | FS | 0
NQR-E1010 | NQR-E1030 | FS | 0
NQR-E1030 | NQR-E1040 | FS | 0
NQR-E1030 | NQR-E1050 | FS | 0
NQR-E1050 | NQR-E1060 | FS | 0
NQR-E1050 | NQR-E1070 | FS | 0
NQR-E1070 | NQR-E1080 | FS | 0
NQR-E1070 | NQR-E1090 | FS | 0
NQR-E1090 | NQR-E1100 | FS | 0
NQR-E1050 | NQR-E1110 | FS | 5
NQR-E1090 | NQR-E1110 | FF | 0
NQR-E1110 | NQR-E1120 | FS | 0
NQR-E1090 | NQR-E1200 | FS | 0
NQR-E1110 | NQR-E1200 | FS | 0
NQR-E1020 | NQR-E1210 | FS | 0
NQR-E1040 | NQR-E1210 | FS | 0
NQR-E1060 | NQR-E1210 | FS | 0
NQR-E1080 | NQR-E1210 | FS | 0
NQR-E1100 | NQR-E1210 | FS | 0
NQR-E1120 | NQR-E1210 | FS | 0
NQR-E1200 | NQR-E1210 | FS | 0
NQR-E1210 | NQR-P1010 | FS | 0
NQR-E1210 | NQR-P1020 | FS | 0
NQR-E1210 | NQR-P1030 | FS | 0
NQR-E1210 | NQR-P1040 | FS | 0
NQR-P1010 | NQR-P1050 | FS | 0
NQR-P1020 | NQR-P1050 | FS | 0
NQR-P1030 | NQR-P1050 | FS | 0
NQR-P1040 | NQR-P1050 | FS | 0
NQR-P1050 | NQR-P1060 | FS | 0
NQR-P1060 | NQR-P1070 | FS | 0
NQR-P1070 | NQR-P1100 | FS | 0
NQR-P1100 | NQR-C2010 | FS | 0
NQR-E1210 | NQR-C1010 | FS | 0
NQR-C2010 | NQR-C2020 | SS | 4
NQR-C1010 | NQR-C2020 | SS | 43
NQR-C1010 | NQR-C1020 | SS | 38
NQR-C2020 | NQR-C2030 | FS | 0
NQR-C1020 | NQR-C2030 | FS | 0
NQR-C2010 | NQR-C2040 | FS | 0
NQR-C2010 | NQR-C2050 | FS | 4
NQR-C2020 | NQR-C2100 | FS | 0
NQR-C2030 | NQR-C2100 | FS | 0
NQR-C2040 | NQR-C2100 | FS | 0
NQR-C2050 | NQR-C2100 | FS | 0
NQR-C1020 | NQR-C2100 | FS | 0
NQR-C2100 | NQR-T1010 | FS | 0
NQR-T1010 | NQR-T1020 | FS | 0
NQR-T1020 | NQR-T1100 | FS | 0
NQR-T1020 | NQR-T2010 | FS | 0
NQR-T1020 | NQR-T2020 | FS | 0
NQR-C2100 | NQR-E1130 | FS | 0
NQR-E1130 | NQR-E1140 | FS | 0
NQR-T1100 | NQR-T3010 | FS | 0
NQR-T2010 | NQR-T3010 | FS | 0
NQR-T2020 | NQR-T3010 | FS | 0
NQR-E1140 | NQR-T3010 | FS | 0
NQR-T3010 | NQR-T3100 | FS | 0
NRY-T3100 | PRJ-C1010 | FS | 0
ERY-T3100 | PRJ-C1010 | FS | 0
HJD-T3100 | PRJ-C1010 | FS | 0
EDM-T3100 | PRJ-C1010 | FS | 0
NQS-T3100 | PRJ-C1010 | FS | 0
EHF-T3100 | PRJ-C1010 | FS | 0
NMJ-T3100 | PRJ-C1010 | FS | 0
HMK-T3100 | PRJ-C1010 | FS | 0
HKA-T3100 | PRJ-C1010 | FS | 0
HMD-T3100 | PRJ-C1010 | FS | 0
EAB-T3100 | PRJ-C1010 | FS | 0
NHL-T3100 | PRJ-C1010 | FS | 0
NJF-T3100 | PRJ-C1010 | FS | 0
NQR-T3100 | PRJ-C1010 | FS | 0
PRJ-C1010 | PRJ-MX99 | FS | 0
PRJ-M0000 | PRJ-MX99 | FS | 750